สรุปโครงการ MONOLITH / DAPH Decor

SOP & Engineering Standards Package v2.5

เวอร์ชัน: 2.5  ·  วันที่: 2 กันยายน 2569  ·  สถานะ: เสร็จสมบูรณ์

เตรียมโดย: MONOLITH AI Operations Team  ·  สำหรับ: ทีม DAPH Decor

1. ภาพรวมโครงการ

โครงการนี้คือการสร้างชุดเอกสารมาตรฐานการปฏิบัติงาน (Standard Operating Procedures) และมาตรฐานวิศวกรรมที่ครอบคลุมทั้งองค์กร MONOLITH/DAPH Decor โดยมีวัตถุประสงค์หลัก:

•  กำหนดมาตรฐานการทำงานที่ชัดเจนสำหรับทุกแผนก

•  นำ AI Agents เข้ามาเสริมการทำงานในทุกสายงาน

•  รองรับ 38 ตำแหน่งงานทั้งหมดของ DAPH

•  สร้างระบบ Governance และ Quality Assurance ที่ตรวจสอบได้

2. เอกสารหลักที่สร้างเสร็จสมบูรณ์

2.1 SOP Master Document (DOCX)

| รายการ | รายละเอียด |
| --- | --- |
| ไฟล์ | SOP_Integrated_Manual_accepted.docx |
| จำนวนหมวด | S1–S23 (23 หมวด) |
| เวอร์ชัน | v2.5 |
| รูปแบบ | Tracked Changes + Accepted-Changes Version |

หมวดเนื้อหาสำคัญ:

| หมวด | ชื่อ / เนื้อหา |
| --- | --- |
| S1–S6 | บทนำ, วิสัยทัศน์, โครงสร้างองค์กร, มาตรฐานวัสดุ, ขั้นตอนการออกแบบ, การจัดการลูกค้า |
| S7 | Core AI Agent Identity (7 Agents หลัก) |
| S8 | KPI Framework สำหรับ AI Agents |
| S9–S14 | กระบวนการติดตั้ง, ควบคุมคุณภาพ, การจัดการโครงการ, POE, Emergency, BIM |
| S15–S18 | แบรนด์, ความยั่งยืน, การจัดการฉุกเฉิน, Digital Twin |
| S19 | Vendor Management (การจัดการผู้จัดจำหน่าย) ← ใหม่ |
| S20 | BIM Standards (มาตรฐาน BIM) ← ใหม่ |
| S21 | Client Portal Manual (คู่มือพอร์ทัลลูกค้า) ← ใหม่ |
| S22 | AI Governance (ธรรมาภิบาล AI) ← ใหม่ |
| S23 | Continuous Improvement Review ← ใหม่ |

2.2 Executive Presentation (PPTX)

•  ไฟล์: SOP_Monolith_Presentation.pptx / .pdf

•  จำนวนสไลด์: 23 สไลด์  (เวอร์ชัน v2.5)

•  เนื้อหา: ครอบคลุม AI Agent Architecture, KPI Dashboard, RACI Matrix, Roadmap

2.3 เอกสาร PDF ทั้งชุด

| ไฟล์ | วัตถุประสงค์ |
| --- | --- |
| executive_brief.pdf | สรุปสำหรับผู้บริหาร |
| sop_master_index.pdf | ดัชนีหลักพร้อมหน้าอ้างอิง |
| bep_template.pdf | BIM Execution Plan Template |
| bim_coordination_report_template.pdf | รายงานประสานงาน BIM |
| client_portal_user_manual.pdf | คู่มือการใช้งานพอร์ทัลลูกค้า |
| client_onboarding_checklist.pdf | Checklist รับลูกค้าใหม่ |
| vendor_qualification_checklist.pdf | Checklist ประเมินผู้จัดจำหน่าย |
| vendor_scorecard_dashboard.pdf | แดชบอร์ดคะแนน Vendor |
| sustainability_scorecard.pdf | รายงานความยั่งยืน |
| training_quiz_section20-22.pdf | แบบทดสอบ (S20, S21, S22) |
| ai_agent_dashboard.pdf | แดชบอร์ด AI Agent Performance |

2.4 ZIP Package

•  ไฟล์: MONOLITH_SOP_Package_v2.4.zip

•  รวมทุกเอกสาร Core + Client-Facing + Dashboard ทั้งหมด

3. AI Agent Roster — 14 Agents (SOP v2.5)

| # | Agent | บทบาท | ตำแหน่งที่รับผิดชอบ | Human Accountable |
| --- | --- | --- | --- | --- |
| 1 | Kelly | Project & Operations Coordinator | A1, D1, D2 | MD / Studio Director |
| 2 | Signal | Marketing Intelligence & Brand Scout | H3, H4 | GM / Marketing Manager |
| 3 | Blaze | Design Automation & Visualization | B1, B2, B3 | Designer Manager |
| 4 | Atlas | Production Control & Schedule | B4, E1, E2 | Plant Manager + PM |
| 5 | Bo | Technical Drawing & Measurement | B5, C1, C2 | Designer Manager / PM |
| 6 | Nova | Client Relations & Sales Support | H1, H2 | Sales Manager |
| 7 | Aria | QA & Standards Compliance | E5 | Plant Manager / QA Manager |
| 8 ★ | Rex | Installation Operations & Field Coordination | D3, D4, D5, D6, D7 | PM |
| 9 ★ | Forge | Factory Production, Maintenance & Warehouse | E1, E2, E3, E4, E6 | Plant Manager |
| 10 ★ | Leo | Logistics, Safety/HSE & Site Compliance | E7, E8 | Plant Manager |
| 11 ★ | Remy | R&D, Materials Innovation & Standards | E9 | GM / Plant Manager |
| 12 ★ | Finn | Finance, Accounting & Procurement | F1, F2, F3, F4 | Finance Manager / MD |
| 13 ★ | Hana | HR, People & Culture | G1, G2 | HR Manager / GM |
| 14 ★ | Core | Software Development, DevOps & Systems | I1, I2, I3 | GM / MD |

★ = New Agents เพิ่มในรอบ v2.4–v2.5 (Rex #8 ถึง Core #14)

Coverage ครบทั้ง 38 ตำแหน่งของ DAPH — 100% (รวม MD ในฐานะตำแหน่งที่ Kelly รับผิดชอบ)

4. Gap Analysis สรุป

ปัญหาที่พบและแก้ไขแล้ว (จาก 7 Agents เดิม)

| Agent | ปัญหาเดิม | การแก้ไข v2.5 |
| --- | --- | --- |
| Bo | S22 assign งาน Finance & Procurement ให้ Bo (BIM Engineer) — ผิดสายงาน | โยกงาน Finance ไปให้ Finn (Agent ใหม่) |
| Atlas | ถูก assign 3 บทบาทต่างกัน: IT, BIM, Project Control | แยก: Atlas = Production, Forge = Factory, Rex = Installation |
| Signal | KPI วัดงาน Comms แต่ Core Identity คือ Market Intelligence | ยืนยัน Signal = Marketing Intelligence เต็มตัว |
| Nova | KPI S8 วัดงาน Research แต่ Nova คือ Client Relations | แยก Nova = Sales Support ชัดเจน |

Coverage สรุป

| แผนก | ตำแหน่ง | Coverage Status |
| --- | --- | --- |
| ผู้บริหาร (A) | A1 + MD | ✅ Kelly |
| ออกแบบ (B) | B1–B5 | ✅ Blaze + Atlas + Bo |
| วัดพื้นที่ (C) | C1–C2 | ✅ Bo |
| โครงการ+ติดตั้ง (D) | D1–D7 | ✅ Kelly + Rex |
| โรงงาน (E) | E1–E9 | ✅ Atlas + Forge + Aria + Leo + Remy |
| การเงิน (F) | F1–F4 | ✅ Finn |
| HR (G) | G1–G2 | ✅ Hana |
| ขาย+การตลาด (H) | H1–H4 | ✅ Nova + Signal |
| ซอฟต์แวร์ (I) | I1–I3 | ✅ Core |

► Coverage: 38/38 ตำแหน่ง = 100%

5. Roadmap 20 Agents (Full Vision)

จากรายงานการวิจัย DAPH AI Agent Roadmap ได้เสนอ 20 Agents เต็มรูปแบบ สำหรับการขยายในระยะต่อไป:

| Phase | Agents ที่เพิ่ม | เป้าหมาย |
| --- | --- | --- |
| Phase 1 (เดือน 1–3) | Atlas, Nexus, Compass, Scout | Quick Wins: ประสิทธิภาพ +30% |
| Phase 2 (เดือน 4–6) | Muse, Forge, Titan, Builder, Ledger | Core Operations ครบทุกสายงาน |
| Phase 3 (เดือน 7–12) | Guardian, Keeper, Voyager, Sentinel, Talent, Spark, Render, Measure, CodeGuard, Ops | Full 20-Agent Coverage |

6. งานเทคนิคสำคัญ

•  XML-level DOCX Surgery: แก้ไข paragraph โดยตรงผ่าน RSID/Paragraph ID ใน word/document.xml

•  Tracked Changes Management: ใช้ <w:ins> / <w:del> markup สำหรับ audit trail ที่ตรวจสอบได้

•  Kelly heading, S8.2, S22 paragraphs: ถูกแก้ไขให้ตรงกับ Master Definition ใน S7

•  Multi-format Output: ทุกเอกสารสร้างทั้งรูปแบบ HTML (source) และ PDF (delivery)

•  Agent Conflict Resolution: แก้ไข Bo/Atlas/Signal/Nova role conflict ผ่าน agent expansion

•  DAPH Coverage Matrix: mapping 14 agents × 38 ตำแหน่งอย่างละเอียด

7. ไฟล์และเอกสารทั้งหมด

โครงสร้างไฟล์ MONOLITH_SOP_Package_v2.5/

Core_Documents/

SOP_Integrated_Manual_accepted.docx   ← Master SOP (23 Sections)

SOP_Monolith_Presentation.pptx         ← Executive PPTX (23 Slides)

executive_brief.pdf

sop_master_index.pdf

Client_Facing/

client_portal_user_manual.pdf

client_onboarding_checklist.pdf

bep_template.pdf

bim_coordination_report_template.pdf

vendor_qualification_checklist.pdf

vendor_scorecard_dashboard.pdf

sustainability_scorecard.pdf

training_quiz_section20-22.pdf

Dashboards/

ai_agent_dashboard_v25.html            ← Updated (20 agents, 38 positions)

ai_agent_dashboard.pdf

Changelog/

changelog_v25.md

monolith_project_summary_v25.docx      ← (this file)

8. ผลการทดสอบ (Training Quiz Results)

ชุดแบบทดสอบประกอบด้วย 3 Quizzes ครอบคลุม BIM Standards (S20), Client Portal (S21) และ AI Governance (S22) รวม 45 ข้อ ใช้ประเมินความรู้ทีม DAPH ก่อนเริ่มใช้งานระบบจริง ผ่านเกณฑ์ที่ 70–80%

| SectionS20S21S22 | หัวข้อ QuizBIM StandardsClient Portal & Live DashboardAI Governance & Ethics | Agent ผู้รับผิดชอบBlaze & AtlasKelly & BlazeBlaze & Nova | จำนวนข้อ151515 | เกณฑ์ผ่าน≥ 12/15 (80%)≥ 70%≥ 12/15 (80%) | เวลา (นาที)—2530 |
| --- | --- | --- | --- | --- | --- |

เนื้อหาที่ครอบคลุม: ISO 19650 · LOD 100–500 · ACC CDE · Clash Detection · RBAC · PDPA · AI Decision Audit · Incident Response P1–P3 · KPI & Model Versioning

9. สถานะ Vendor Qualification

แบบฟอร์ม FORM-VQ-001 (Rev 1.0 · ก.ย. 2569) ใช้คัดเลือกผู้จัดจำหน่ายวัสดุ Luxury สำหรับโครงการ MONOLITH ตามมาตรฐาน SOP Section 19 — Vendor Management ประกอบด้วย 7 เกณฑ์การประเมิน ครอบคลุมวัสดุทุกประเภท (Stone, Tile, MEP, Metalwork, Furniture)

| #01020304050607 | เกณฑ์การประเมิน (Criterion)ความมั่นคงทางการเงินประสบการณ์และผลงานมาตรฐานและการรับรองความสามารถด้านส่งมอบนโยบายด้านความยั่งยืนระบบควบคุมคุณภาพราคาและเงื่อนไขการชำระ | รายละเอียดหลักรายได้ประจำปี · อัตราส่วนหนี้สินPortfolio Luxury ≥ 3 โครงการISO / CE / มาตรฐานเฉพาะวัสดุLead Time · Minimum Order · StockESG / Green Material CertificateQC Procedure · Defect Rate < 2%ราคา FOB/CIF · Payment Terms | สถานะActiveActiveActiveActiveActiveActiveActive |
| --- | --- | --- | --- |

Agent รับผิดชอบ: Rex (S19 Vendor Management) · รูปแบบ: แบบฟอร์มกระดาษ + Digital (PDF) · ประเมินทุก 12 เดือน / เมื่อมีการต่อสัญญา

10. BIM Coordination Milestones

รายงานการประสานงาน BIM รายสัปดาห์ (Weekly BIM Coordination Report) ตามมาตรฐาน SOP Section 20.4 — Clash Detection Protocol บริหารโดย Atlas (BIM Manager) ใช้ Navisworks Clash Detection ประชุมทุกวันจันทร์ เวลา 09:00–10:00 น.

| กิจกรรม / MilestoneBIM Model CoordinationClash Detection — HARDClash Detection — SOFTCDE File Naming ReviewDigital Handover ChecklistRBAC Access Control AuditBIM Coordination Meeting | AgentAtlasAtlas + ForgeAtlasBlazeAtlas + HanaCoreAtlas (Lead) | เครื่องมือNavisworks / ACCNavisworksNavisworksACC CDEACC / SharePointACC Admin PanelTeams / Zoom | ความถี่รายสัปดาห์ทุก Sprintรายสัปดาห์ทุก Uploadต่อโครงการราย 3 เดือนทุกจันทร์ | มาตรฐาน / เกณฑ์SOP S20 · ISO 19650Priority CriticalPriority HighISO 19650-2 · LOD 300+LOD 500 · S20.6SOP S20.509:00–10:00 น. |
| --- | --- | --- | --- | --- |

ประเภท Clash: HARD (Critical) = แก้ไขภายใน 48 ชั่วโมง · SOFT (High) = แก้ไขภายใน 1 สัปดาห์ · Work Order (WO) = บันทึกและติดตาม · เกณฑ์ Clash Resolved Rate: ≥ 95% ต่อรอบประชุม

11. ผลการประเมิน Sustainability Scorecard

MONOLITH ใช้กรอบมาตรฐาน LEED v4.1 และ WELL Building Standard เป็นแนวทางหลักในการประเมิน ความยั่งยืนของโครงการ ครอบคลุมด้านพลังงาน น้ำ วัสดุ และคุณภาพสภาพแวดล้อมภายใน โดยมีเป้าหมาย LEED Gold สำหรับโครงการ Luxury Residential ทุกโครงการตั้งแต่ปี 2026

11.1 ระดับการรับรอง LEED Certification Targets

| ระดับการรับรอง | คะแนน (LEED v4.1) | กลุ่มโครงการเป้าหมาย |
| --- | --- | --- |
| CERTIFIED | 40–49 pts | ขั้นต่ำสุด |
| SILVER | 50–59 pts | Commercial Interior |
| GOLD (เป้าหมายหลัก) | 60–79 pts | Luxury Residential |
| PLATINUM | >= 80 pts | Showcase Projects |

11.2 ตัวชี้วัดด้านพลังงานและสิ่งแวดล้อม (Energy & Environmental KPIs)

| ตัวชี้วัด (KPI) | ค่าเป้าหมาย | หน่วย / เงื่อนไข | Agent ผู้รับผิดชอบ |
| --- | --- | --- | --- |
| Energy Use Intensity (EUI) | <= 45 | kBtu/ft2/yr · BIM 360 Energy Dashboard | ATLAS |
| Renewable Energy Share | >= 20% | % รวม Solar PV + Green Energy Certificate | ATLAS |
| Water Use Reduction (WE) | >= 30% | % ลดจากค่าอ้างอิง ASHRAE baseline | SIGNAL |
| Construction Waste Diversion | >= 75% | % by weight · CWMP + Weight Ticket | BLAZE |
| Daylight Autonomy (sDA) | >= 50% | % พื้นที่ใช้งานหลัก · Daylight Simulation | NOVA |
| Indoor PM2.5 (HEPA H13) | < 15 ug/m3 | วัดต่อเนื่อง 24 ชม. · IEQ Monitor | ATLAS |

11.3 เป้าหมายเชิงกลยุทธ์ (Strategic Sustainability Goals)

| ระยะเวลา | เป้าหมายหลัก |
| --- | --- |
| 2026 — Baseline | LEED Gold ทุกโครงการใหม่ · ESG Report (GRI Std.) · LEED GA ครบทีม Designers |
| 2027 — Scaling | WELL Silver >= 2 โครงการ · Renewable Energy >= 20% · Green Material Library v2.0 |
| 2573 — Net-Zero | Carbon-Neutral Studio · 100% Green Energy · Zero-Waste Projects |

12. สถานะแผนฉุกเฉินและการบริหารวิกฤต (Emergency Response Protocol)

แผนฉุกเฉินและการบริหารวิกฤตตาม SOP Section 18 กำหนดกรอบการรับมือเหตุการณ์ 4 ระดับ ตั้งแต่ L1 Minor ถึง L4 Critical โดยมีสายการรายงาน Signal → Blaze → Kelly → Studio Director และมีกระบวนการ Business Continuity (BCP) รองรับการดำเนินงานต่อเนื่อง

12.1 ตารางจำแนกระดับวิกฤต (Crisis Classification Matrix)

| ระดับ | ประเภทเหตุการณ์ | ผู้รับผิดชอบ (Agent) | เวลาตอบสนอง |
| --- | --- | --- | --- |
| L1 — Minor | เหตุเล็กน้อย · อุปกรณ์ชำรุด · วัสดุขาด | Site Supervisor (Signal) | <= 4 ชั่วโมง |
| L2 — Moderate | งานหยุดบางส่วน · วัสดุล่าช้า · คุณภาพบกพร่อง | Project Manager (Blaze) | <= 24 ชั่วโมง |
| L3 — Major | งานหยุดทั้งไซต์ · อุบัติเหตุบุคคล · โครงสร้างเสียหาย | Studio Director (Kelly) | <= 48 ชั่วโมง |
| L4 — Critical | เสียชีวิต · ข้อพิพาทกฎหมาย · สื่อสาธารณะ | Director + Legal + PR | ทันที (24/7) |

12.2 ตัวชี้วัด Business Continuity (BCP KPIs)

| ตัวชี้วัด BCP | ค่าเป้าหมาย |
| --- | --- |
| Recovery Time Objective (RTO) | <= 4 ชั่วโมง |
| Client Notification (L3/L4) | <= 2 ชั่วโมง |
| Post-Crisis AAR Report | <= 72 ชั่วโมง |
| Insurance Minimum Coverage | >= 50 ล้านบาท (CAR + TPL + PI) |
| ซ้อมแผนฉุกเฉิน | มิถุนายน + ธันวาคม ทุกปี |

ขั้นตอนเมื่อเกิดเหตุฉุกเฉิน (Emergency Steps): STOP (หยุดงาน) → SECURE (ปิดกั้นพื้นที่) → REPORT (แจ้ง Signal ใน 15 นาที) → DOCUMENT (ถ่ายรูปหลักฐาน) → ESCALATE (รายงานตาม Level) หมายเหตุ: ห้ามให้ข่าวสื่อโดยไม่ได้รับอนุญาตจาก Studio Director

13. AI Agent Dashboard v2.5.1 — การอัปเดตและ Roadmap การ Deploy

การอัปเดต Dashboard v2.5.1 มุ่งเน้นการแก้ไขปัญหาการแสดงผลที่พบหลัง Release v2.5 และเพิ่มความชัดเจนในการอ่าน Agent Mapping สำหรับทีมผู้บริหารและลูกค้า พร้อมกันนี้ยังกำหนด Roadmap การ Deploy AI Agents 6 ตัวที่อยู่ในแผนพัฒนาช่วง Q3 2026 — Q1 2027

13.1 การแก้ไข Dashboard v2.5.1 (Bug Fixes & Visual Improvements)

การแก้ไขทั้ง 5 รายการในเวอร์ชัน v2.5.1 เน้นการปรับปรุง UX ของ Dashboard HTML โดยไม่เปลี่ยนแปลงข้อมูล Agent Mapping หรือ SOP Content ใดๆ

| การแก้ไข (Fix) | รายละเอียด | ผลที่ได้ |
| --- | --- | --- |
| Opacity Fix | แก้ไขค่า CSS opacity บน Roadmap agent rows จาก 0.6 เป็น 1.0 | Agent cards แสดงสีครบถ้วน อ่านง่ายขึ้น |
| Padding Reduction | ลด padding จาก 12px → 8px ใน agent table rows | แสดง agent ครบ 20 rows ในหน้าเดียวโดยไม่ต้อง scroll |
| Separator Row | เพิ่ม separator row ระหว่าง Active agents (01–14) และ Roadmap agents (15–20) | แยกกลุ่ม agent ชัดเจน ลดความสับสน |
| Legend Strip | เพิ่ม visual legend bar ใต้ dashboard header อธิบาย Active vs Roadmap status | Client เข้าใจ status ของแต่ละ agent ได้ทันที |
| Hollow Dots | เปลี่ยน Roadmap agent status indicator จาก filled circle เป็น hollow circle (border-only) | สอดคล้องกับ SOP v2.5 Convention — hollow = Proposed/Not yet deployed |

13.2 Roadmap การ Deploy AI Agents (Q3 2026 — Q1 2027)

AI Agents 6 ตัวในกลุ่ม Roadmap ได้รับการจัดลำดับ Priority ตามความเร่งด่วนของ Business Need โดย P0 (Nexus, Compass) จะ Deploy ก่อนใน Q3 2026 ตามด้วย P1 (Scout, Guardian) ใน Q4 2026 และ P2 (Talent, Ops) ใน Q1 2027 ซึ่งสอดคล้องกับแผนการ Scale Up ทีมงานของ MONOLITH

| Agent | Priority | Function หลัก | ตำแหน่งที่ Cover | Human Accountable | Target Quarter |
| --- | --- | --- | --- | --- | --- |
| 15 · Nexus | P0 | Advanced Project Tracking & Multi-project Dashboard | D1, D2, A1 | Studio Director | Q3 2026 |
| 16 · Compass | P0 | Sales Pipeline & Client Journey Analytics | H1, H2 | Sales Manager | Q3 2026 |
| 17 · Scout | P1 | Marketing Intelligence & Content Performance | H1, H3 | Marketing Manager | Q4 2026 |
| 18 · Guardian | P1 | QA Audit Automation & Compliance Tracking | E5 | QA Manager | Q4 2026 |
| 19 · Talent | P2 | HR Analytics & Workforce Planning | G1, G2 | HR Manager | Q1 2027 |
| 20 · Ops | P2 | Operations Intelligence & Executive Reporting | I3 | GM / MD | Q1 2027 |

หมายเหตุ: การ Deploy Roadmap Agents ต้องผ่านกระบวนการ UAT (User Acceptance Testing) และได้รับการอนุมัติจาก Studio Director ก่อน Go-Live ทุกครั้ง ดูรายละเอียด Deployment Checklist ได้ใน SOP Section 19

เอกสารนี้เตรียมสำหรับแชร์ภายในทีม DAPH Decor  ·  ห้ามเผยแพร่ภายนอก  ·  MONOLITH CONFIDENTIAL

14. v2.6 / v2.7 — อัปเดต Package: Thai Deliverables และ Presentation Updates

ส่วนนี้บันทึกการปรับปรุงที่ดำเนินการภายหลัง v2.5.1 โดยครอบคลุมเอกสาร Thai-language ชุดใหม่ที่เพิ่มใน v2.6 และการเพิ่ม Gantt Timeline Slide พร้อม English Executive Summary ใน v2.7 ทุกไฟล์ถูกรวมไว้ใน MONOLITH_SOP_Package_v2.5.zip พร้อม changelog_v25.md ที่อัปเดตแล้ว

14.1 Thai Language Deliverables (v2.6)

v2.6 เพิ่มเอกสาร Thai-language สำหรับทีม DAPH Decor ประกอบด้วย Thai PPTX slide deck 10 slides และ Thai Executive Summary PDF ครอบคลุมทุก 13 sections ของ Project Summary ฉบับนี้

· ai_agent_dashboard_thai_v25.pptx — Thai-language Dashboard PPTX (10 slides, Sarabun font)

· ai_agent_dashboard_thai_v25.pdf — PDF export ของ Thai slide deck

· thai_exec_summary_v25.pdf — Thai one-page Executive Summary (1280×720, landscape)

· thai_exec_summary_v25.pptx — Thai Executive Summary ในรูปแบบ PPTX

· slide-10-thai.html — Thai delta slide เปรียบเทียบ v2.4 vs v2.5 agent coverage

14.2 Slide 11 Gantt Chart และ English Executive Summary (v2.7)

v2.7 เพิ่ม Slide 11 แสดง Gantt Timeline สำหรับ Roadmap Agents 6 ตัว (Nexus, Compass, Scout, Guardian, Talent, Ops) ครอบคลุมช่วง Q3 2026 — Q1 2027 ลงใน Presentation decks ทั้งสองภาษา Presentation แต่ละชุดจึงมีครบ 11 slides นอกจากนี้ยังเพิ่ม English Executive Summary PDF สำหรับใช้ในการสื่อสารภายนอก

· slide-11-gantt.html — English Gantt slide (P0 Q3 2026 / P1 Q4 2026 / P2 Q1 2027)

· slide-11-gantt-thai.html — Thai Gantt slide (ภาษาไทย, Sarabun font)

· ai_agent_dashboard_presentation_v25.pptx — English PPTX อัปเดตเป็น 11 slides

· ai_agent_dashboard_thai_v25.pptx — Thai PPTX อัปเดตเป็น 11 slides

· eng_exec_summary_v25.pdf — English one-page Executive Summary (ครอบคลุม 13 sections)

· eng_exec_summary_v25.pptx — English Executive Summary ในรูปแบบ PPTX

14.3 ZIP Package — รายการไฟล์ฉบับสมบูรณ์ (v2.7)

MONOLITH_SOP_Package_v2.5.zip อัปเดตล่าสุดประกอบด้วย 20 ไฟล์ รวม PPTX (2 decks × 11 slides), PDF, HTML dashboard, DOCX (SOP Manual + Project Summary ทุกเวอร์ชัน), Thai briefings, และ changelog รายการไฟล์ทั้งหมดบันทึกไว้ใน changelog_v25.md ส่วน v2.7

หมายเหตุ: การเปลี่ยนแปลงทั้งหมดใน v2.6 และ v2.7 สามารถตรวจสอบได้จาก changelog_v25.md ที่แนบมาใน ZIP Package ทุกไฟล์ใหม่ผ่านการ Review โดย Scispace Agent และได้รับการ Validate ด้วย html_to_pptx.py (PPTX/PDF) และ verify_docx.py (DOCX)

15. Acceptance Sign-off — Sections S1 through S14

ส่วนนี้เป็นเอกสารรับรองอย่างเป็นทางการสำหรับ Sections S1–S14 ของ MONOLITH / DAPH Decor AI Agent System Project Summary v2.7 เนื้อหาทุก Section ได้รับการตรวจสอบ และยืนยันความถูกต้องโดยทีมงานที่ระบุด้านล่าง ก่อนส่งมอบให้ผู้บริหาร DAPH Decor

15.1 Section Acceptance Summary

รายการ Sections ทั้ง 14 ส่วนที่ได้รับการตรวจสอบและยืนยัน:

S1  — นโยบายองค์กรและวิสัยทัศน์       ✓ ยืนยันแล้ว

S2  — โครงสร้างองค์กรและตำแหน่งงาน   ✓ ยืนยันแล้ว

S3  — กระบวนการออกแบบและสร้างสรรค์    ✓ ยืนยันแล้ว

S4  — การจัดการวัสดุและ Procurement   ✓ ยืนยันแล้ว

S5  — กระบวนการขายและ CRM             ✓ ยืนยันแล้ว

S6  — การจัดการโปรเจกต์               ✓ ยืนยันแล้ว

S7  — การควบคุมคุณภาพ QA/QC           ✓ ยืนยันแล้ว

S8  — การจัดการทีมงานและ AI Agents     ✓ ยืนยันแล้ว

S9  — กระบวนการผลิตและประกอบ          ✓ ยืนยันแล้ว

S10 — การติดตั้งและงานหน้างาน          ✓ ยืนยันแล้ว

S11 — การตรวจสอบและ Sustainability    ✓ ยืนยันแล้ว

S12 — การส่งมอบและ Emergency Protocol ✓ ยืนยันแล้ว

S13 — ระบบ IT และ Digital Integration  ✓ ยืนยันแล้ว

S14 — v2.6/v2.7 Package Update         ✓ ยืนยันแล้ว

15.2 Reviewer Information

เอกสารฉบับนี้ได้รับการตรวจสอบและจัดทำโดย:

ผู้จัดทำ:       Scispace Agent — MONOLITH AI System v2.7

วันที่จัดทำ:     กันยายน 2026

ผู้ตรวจสอบ:     ทีมผู้บริหาร DAPH Decor

วันที่ตรวจสอบ:  ___________________________

ผู้อนุมัติ:      ___________________________   ตำแหน่ง: ___________________________

15.3 Acceptance Statement

ข้าพเจ้าขอยืนยันว่าได้ตรวจสอบเนื้อหาใน Sections S1–S14 ของเอกสาร MONOLITH / DAPH Decor AI Agent System Project Summary v2.7 ครบถ้วนแล้ว และขอรับรองว่าข้อมูลทุกส่วนถูกต้อง สมบูรณ์ และสอดคล้องกับแผนการดำเนินงานของ DAPH Decor

เอกสารฉบับนี้ถือเป็นเอกสารอ้างอิงหลักสำหรับการดำเนินงาน AI Agent System ตั้งแต่ v2.5 จนถึง v2.7 และรองรับการวางแผนสำหรับ v3.0 (Talent + Ops Live, Q1 2027 เป็นต้นไป)

ลงนาม:     ___________________________   วันที่: ___________________________

ชื่อ:       ___________________________

ตำแหน่ง:   ___________________________

หน่วยงาน:  DAPH Decor / MONOLITH

15.4 Distribution Record

เอกสารฉบับนี้ถูกส่งมอบให้กับผู้รับดังต่อไปนี้:

· ทีมผู้บริหาร DAPH Decor — ฉบับ PDF และ PPTX

· Studio Director / Project Lead — ฉบับ DOCX (สำหรับอ้างอิง)

· HR Manager / Operations Manager — ฉบับ PDF สรุปภาษาไทย

· IT / Systems Team — ผ่าน MONOLITH_SOP_Package_v2.5.zip

· บันทึกลงใน changelog_v25.md ส่วน v2.8

หมายเหตุ: เอกสาร Acceptance Sign-off ฉบับนี้เป็นส่วนหนึ่งของ v2.8 Release ซึ่งครอบคลุม Slide 12 Heatmap, Master Index, Training Quiz และ v3.0 Planning

16. Cross-Agent Orchestration Protocol

Version: 3.0 Planning  ·  Status: Draft  ·  Prepared: September 2026

16.1 Overview

Cross-Agent Orchestration defines how MONOLITH AI agents communicate, share context, and trigger one another based on workflow events. This protocol becomes operational in v3.0 Phase C (Q3–Q4 2027) once all 20 active agents and 5 Phase B agents (Vega, Stone, Ember, Pulse, Shore) have passed their 30-day stability review.

The Ops agent (Agent #20) acts as the central orchestrator, receiving event signals from upstream agents and dispatching downstream actions across departments. All orchestration events are logged with timestamps, triggering agent ID, receiving agent ID, and outcome status.

16.2 Orchestration Pipelines

Four primary cross-agent pipelines are planned for v3.0:

Pipeline 1 — Sales → Design → Production

Trigger: New client project confirmed by Compass (Sales CRM).

Flow: Compass → Kelly (Design Lead) → Forge (Procurement) → Atlas (Project Mgmt).

Outcome: Design brief auto-generated, materials procurement initiated, project timeline created in Atlas dashboard.

Pipeline 2 — QA → Site → Client Notification

Trigger: QC milestone passed by Guardian (Quality Assurance).

Flow: Guardian → Bo (Site Operations) → Aria (Client Relations).

Outcome: Site handover confirmed, client auto-notified with milestone summary and next-steps schedule.

Pipeline 3 — HR → Operations → Systems

Trigger: Headcount change event recorded by Talent (HR Manager AI).

Flow: Talent → Ops (GM/MD Orchestrator) → Core (Systems & DevOps).

Outcome: Capacity recalculation triggered, system access provisioned or deprovisioned, Ops dashboard updated.

Pipeline 4 — Marketing → CRM → Sales Intelligence

Trigger: Marketing campaign launched by Scout (Marketing AI).

Flow: Scout → Remy (CRM) → Compass (Sales CRM).

Outcome: Lead scoring updated based on campaign engagement, sales priority list refreshed, Compass dashboard synced.

16.3 Technical Requirements

• Shared event bus / message queue — all agents publish and subscribe to a central message broker (e.g. Redis Streams or equivalent)

• Inter-agent communication protocol — standardised JSON schema v1.0 defining event_type, source_agent, target_agent, payload, and timestamp fields

• Ops agent orchestration layer — Ops (#20) acts as supervisor; all multi-step pipelines route through Ops for logging and exception handling

• Audit log — every cross-agent trigger stored with full payload for compliance review and SOP traceability

• Idempotency — all agent actions must be idempotent to prevent duplicate processing when events are re-delivered

• Timeout & fallback — each pipeline step has a 30-second timeout; on timeout, Ops escalates to the human accountable role defined in S22 RACI

16.4 Roles & Responsibilities

Orchestration Design Lead:  Systems Team (Core Agent #14 accountable)

Pipeline Testing & QA:  QA Manager (Guardian Agent #18 accountable)

Human Escalation Owner:  GM / MD (Ops Agent #20 accountable)

Audit Log Review:  Operations Manager — monthly review

SOP Update Authority:  Studio Director — approves S16 amendments

16.5 Implementation Timeline

Q1 2027:  All 20 active agents stable → Phase C pre-conditions met

Q2 2027:  Event bus infrastructure provisioned; JSON schema v1.0 finalised

Q3 2027:  Pipeline 1 (Sales→Design→Production) go-live; Vega/Stone/Ember deployed

Q4 2027:  Pipelines 2, 3, 4 activated; Pulse & Shore deployed

Q1 2028:  Full orchestration layer operational → v3.0 stabilisation review

────────────────────────────────────────────────────────────────────

Note: Section 16 is a planning draft. Final architecture and protocol specifications will be confirmed upon Talent + Ops agent go-live (Q1 2027). This section will be updated to v3.0 Final upon project initiation.

Reference: v30_planning.docx — Section 3 (Phase C Orchestration) and Section 7 (Risks)

17. Agent Performance KPIs & SLA Thresholds

Version: 3.0 Planning  ·  Status: Draft  ·  Prepared: September 2026

17.1 Overview

This section defines the key performance indicators (KPIs) and service-level agreement (SLA) thresholds applied to all 20 live MONOLITH AI agents. Performance monitoring ensures each agent operates within agreed accuracy, reliability, and responsiveness parameters across DAPH Decor's 13 departments.

KPI monitoring is operationally linked to Section 16 (Cross-Agent Orchestration). The Core agent (#14) provides the underlying systems monitoring layer, while the Ops agent (#20) consolidates performance data for weekly and monthly review. Any agent breaching a threshold triggers an escalation as defined in 17.4.

17.2 KPI Framework

Four performance categories apply universally across all agents:

Category 1 — Response Accuracy

Measures the percentage of agent outputs that are factually correct, contextually appropriate, and free from hallucination or misclassification. Evaluated against a weekly human-reviewed sample (5% of all outputs).

Category 2 — Task Completion Rate

Percentage of assigned tasks completed end-to-end without human override or manual correction within the same session. Captures agent autonomy and workflow reliability in production conditions.

Category 3 — System Uptime

Percentage of scheduled operating hours during which the agent was responsive and available. Includes planned maintenance windows as exclusions. Measured by Core agent (#14) heartbeat monitoring.

Category 4 — Escalation Rate

Percentage of tasks that required escalation to a human accountable owner due to agent inability, threshold breach, or exception condition. Lower values indicate higher agent maturity and autonomy.

17.3 SLA Thresholds by Agent Group

The 20 live agents are grouped into four functional clusters. SLA thresholds reflect the criticality, client-facing nature, and operational risk of each cluster:

Group A — Client-Facing & Design (Kelly, Signal, Aria, Blaze, Nova)

Response Accuracy SLA:  >= 95%  (breach threshold: < 90%)

Task Completion Rate SLA:  >= 92%  (breach threshold: < 85%)

System Uptime SLA:  >= 99.0%  (breach threshold: < 97%)

Escalation Rate SLA:  <= 5%  (breach threshold: > 10%)

Group B — Sales, CRM & Marketing (Compass, Remy, Scout, Finn, Hana)

Response Accuracy SLA:  >= 93%  (breach threshold: < 88%)

Task Completion Rate SLA:  >= 90%  (breach threshold: < 83%)

System Uptime SLA:  >= 98.5%  (breach threshold: < 96%)

Escalation Rate SLA:  <= 7%  (breach threshold: > 12%)

Group C — Project & Site Operations (Atlas, Bo, Forge, Leo, Ops)

Response Accuracy SLA:  >= 94%  (breach threshold: < 89%)

Task Completion Rate SLA:  >= 91%  (breach threshold: < 84%)

System Uptime SLA:  >= 99.0%  (breach threshold: < 97%)

Escalation Rate SLA:  <= 6%  (breach threshold: > 11%)

Group D — Systems, QA & HR (Core, Nexus, Rex, Guardian, Talent)

Response Accuracy SLA:  >= 97%  (breach threshold: < 93%)

Task Completion Rate SLA:  >= 95%  (breach threshold: < 90%)

System Uptime SLA:  >= 99.5%  (breach threshold: < 98%)

Escalation Rate SLA:  <= 4%  (breach threshold: > 8%)

17.4 Monitoring & Alerting Protocol

Core (#14) provides the real-time systems monitoring layer. All agent heartbeat signals, task-completion logs, and error events are ingested by Core and surfaced on the Ops agent (#20) dashboard. Alerting follows a three-tier escalation model:

Tier 1 — Automated Alert (Core → Ops):

KPI within 3 percentage points of breach threshold. Core logs event and notifies Ops dashboard. No human action required unless condition persists for more than 24 hours.

Tier 2 — Ops Review Required:

KPI at or below breach threshold for any rolling 7-day window. Ops agent escalates to the responsible Department Head with a performance summary report. Review meeting scheduled within 5 business days.

Tier 3 — Studio Director Escalation:

KPI below breach threshold for more than 14 consecutive days, or any single-day performance drop exceeding 10 percentage points. Studio Director notified directly. Agent may be placed in supervised mode pending root-cause analysis.

All alert events are written to the MONOLITH Audit Log (S18) with full context: agent ID, KPI category, measured value, SLA threshold, tier triggered, and resolution timestamp.

17.5 Review Cadence

KPI performance is reviewed at three frequencies:

Daily (automated):  Core agent generates a 24-hour KPI snapshot for all 20 agents. Ops dashboard updated by 07:00 each business day.

Weekly (Ops-led):  Ops agent compiles 7-day rolling performance report by end of each Friday. Distributed to Department Heads and Studio Director. Agents in Tier 2 alert status are reviewed in detail.

Monthly (Director-level):  Full 30-day KPI trend analysis presented at the MONOLITH AI Governance meeting (first Monday of each month). SLA threshold values may be revised upward as agent maturity improves. All threshold changes require Studio Director sign-off and are versioned as SOP amendments.

────────────────────────────────────────────────────────────────────

Note: SLA threshold values in this section are based on industry benchmarks for enterprise AI deployments and DAPH Decor operational risk tolerance as of September 2026. Thresholds will be recalibrated following Phase A Stabilization (Q1–Q2 2027) based on observed production data. Reference: v30_planning.docx — Section 5 (KPI & Governance Framework).

18. Incident Response & Escalation Playbook

18.1  Overview

Section 18 defines the structured incident response framework for all 20 live AI Agents operating under the MONOLITH / DAPH Decor deployment. It establishes clear severity classifications, escalation pathways, response procedures, and post-incident review obligations — ensuring continuity of service and accountability across all functional agent groups.

This playbook operates in conjunction with the KPI thresholds defined in Section 17 and the Cross-Agent Orchestration Protocol in Section 16. All incidents must be logged in the central Incident Register, regardless of severity.

18.2  Incident Severity Classification

Incidents are classified into three severity tiers to prioritise response effort and resource allocation:

P1 — Critical:  Complete agent failure, system-wide Uptime below 95%, or data integrity breach. Affects client-facing operations or financial processing. Requires immediate response within 15 minutes. Escalated directly to Leadership (Tier 3).

P2 — High:  Significant KPI degradation (Accuracy <90% or Completion <85%), repeated escalation failures, or integration breakdown between two or more agents. Response required within 1 hour. Managed by Operations team (Tier 2) with Leadership notification.

P3 — Moderate:  Single-metric SLA miss in one agent group, minor latency increase, or isolated task failure not affecting downstream workflows. Response within 4 hours during business hours. Managed by Ops team without escalation unless unresolved within 24 hours.

18.3  Escalation Matrix by Agent Group

Escalation responsibilities are aligned to the four SLA groups defined in Section 17. Each group has a designated Ops Lead responsible for first-line response and a secondary escalation contact for unresolved P2/P1 incidents:

Group A (Kelly, Signal, Aria, Blaze, Nova):  First-line: Client Experience Ops Lead. Secondary: Head of Design & Client Services. P1 threshold: Accuracy <92% or client-facing downtime >10 minutes.

Group B (Compass, Remy, Scout, Finn, Hana):  First-line: CRM & Sales Ops Lead. Secondary: Head of Sales & Marketing. P1 threshold: Lead pipeline stall >30 minutes or CRM sync failure.

Group C (Atlas, Bo, Forge, Leo, Ops):  First-line: Site & Project Ops Lead. Secondary: Head of Operations. P1 threshold: Active site data unavailable >15 minutes or procurement block.

Group D (Core, Nexus, Rex, Guardian, Talent):  First-line: Systems & QA Lead. Secondary: CTO / Head of Technology. P1 threshold: Core infrastructure failure, security alert, or HR data breach.

18.4  Response Procedures

All incidents follow a standardised five-step response procedure regardless of severity:

Step 1 — Detect & Log:  Incident detected via Real-Time Monitoring dashboard or agent self-report. Ops team logs entry in Incident Register within 5 minutes of detection, recording: timestamp, affected agent(s), symptom description, and initial severity classification.

Step 2 — Contain:  Immediate containment action taken — isolate affected agent from downstream workflows, activate fallback routing via Nexus Orchestration Layer (S16), and notify affected business units within SLA response window.

Step 3 — Diagnose:  Root-cause analysis initiated. Ops Lead reviews KPI dashboard, error logs, and integration status. For P1 incidents, CTO is notified concurrently. Diagnosis must be documented in Incident Register within response window.

Step 4 — Resolve:  Corrective action implemented. Agent restarted, reconfigured, or taken offline pending full repair. For multi-agent incidents, S16 Orchestration Protocol governs priority of restoration. Affected agents undergo post-resolution KPI validation before returning to full operational status.

Step 5 — Close & Review:  Incident formally closed in Register after KPI validation passes. Post-Incident Review (PIR) initiated within 48 hours for all P1/P2 incidents. PIR outcomes feed into monthly SLA review (S17.5) and S18.6 playbook updates.

18.5  Communication Protocol

All incident communications must follow the prescribed channels to ensure traceability and appropriate stakeholder awareness:

Internal Ops Channel:  All P3 and above incidents posted to the designated #ai-ops-incidents channel within 10 minutes of logging. Updates every 30 minutes until resolved.

Leadership Notification:  P1 and escalated P2 incidents: email + direct message to Department Head and CTO within 15 minutes. Include: incident ID, affected agent(s), business impact, and estimated resolution time.

Client Communication:  For incidents affecting client-facing agents (Group A): Client Services team notified within 20 minutes. Client communication drafted by Client Experience Lead — approved by Head of Client Services before sending.

Incident Register:  All incidents documented in the central Incident Register with full audit trail. Register reviewed at weekly Ops stand-up and monthly SLA review meeting.

18.6  Post-Incident Review & Playbook Updates

Post-Incident Reviews (PIRs) are mandatory for all P1 incidents and recommended for P2 incidents. PIR must be completed within 48 hours of incident closure.

PIR Scope:  Root cause confirmed, timeline reconstructed, business impact quantified, and preventive measures identified.

Playbook Amendment:  If PIR identifies a gap in this playbook, a formal amendment proposal is submitted to the Operations Lead. Approved amendments are incorporated in the next monthly SLA review cycle and tracked as a new Section 18 version revision.

SLA Threshold Review:  Recurring P2/P3 incidents in the same agent group trigger an automatic SLA threshold review under Section 17.5. Thresholds may be tightened or agent retraining initiated based on PIR findings.

Trend Reporting:  Monthly incident trend report produced by Ops Lead — covering: total incidents by severity and group, mean time to resolve (MTTR), repeat incident rate, and SLA compliance rate. Distributed to all Department Heads and archived in the MONOLITH document repository.

19. Data Privacy & AI Compliance

19.1  Overview

Section 19 defines the data privacy obligations and AI compliance framework governing all 20 live AI agents operating within MONOLITH / DAPH Decor. The framework aligns with the Thailand Personal Data Protection Act (PDPA), GDPR principles for international client engagements, and internal AI model governance standards. All agents must operate within the data handling tiers and regulatory obligations defined in this section.

19.2  Data Classification & Handling Standards

Four classification tiers govern data handled across all agent workflows:

Tier 1 — Personal Data (PII):  Client names, contact details, payment information. Handled by Kelly, Nova, Aria, Compass, Remy, Finn. Retention: 2 years post-project; encrypted at rest and in transit; access restricted to agents with CRM or Client role designation.

Tier 2 — Project Data:  Design briefs, Bills of Quantities, site plans, installation records. Handled by Atlas, Bo, Blaze, Rex, Forge. Retention: 7 years; version-controlled project repository; accessible to Project and Site Operations teams.

Tier 3 — Operational Data:  Production logs, inventory records, scheduling data. Handled by Ops, Forge, Leo, Scout. Retention: 3 years; operational repository; accessible to Operations team.

Tier 4 — System & Audit Logs:  AI model interactions, escalation records, performance metrics. Managed by Core and Nexus. Retention: 1 year rolling; immutable log store; accessible to IT Manager and Compliance Officer only.

19.3  AI Model Governance

All production AI models are subject to the following governance controls:

Model Versioning:  All production models tagged with version identifier (format: vMAJOR.MINOR.PATCH). Version registry maintained by Core (#14).

Change Management:  Model updates require staged rollout: staging environment validation followed by QA sign-off (Guardian #18) before production deployment. Emergency hotfixes require IT Manager approval.

Bias & Quality Audit:  Quarterly audit of model outputs across all 20 agents. Bias review led by Guardian (#18) with findings reported to Studio Director.

Retraining Schedule:  Kelly, Signal, Aria — monthly retraining cycle. All other agents — quarterly. Retraining triggered immediately following P1 incidents affecting model accuracy.

Explainability:  All P1 and P2 escalation decisions must include a human-readable rationale entry in the MONOLITH Audit Log within 30 minutes of escalation.

19.4  Regulatory Compliance Framework

Thailand PDPA (พ.ร.บ. คุ้มครองข้อมูลส่วนบุคคล พ.ศ. 2562):

Data Controller:  Studio Director is the designated Data Controller for all MONOLITH / DAPH Decor AI systems and client data processing activities.

Data Processor:  MONOLITH AI Operations Team acts as Data Processor; processing activities governed by an internal Data Processing Agreement.

Consent:  Explicit consent obtained before collecting client PII; managed through the Client Portal (S21). Consent records retained for the duration of the client relationship plus 2 years.

Data Subject Rights:  30-day response SLA for access, correction, deletion, and portability requests. Requests routed to Ops Lead; fulfilled by Core (#14).

Cross-Border Transfer:  Prohibited without explicit client consent and an applicable adequacy mechanism or Standard Contractual Clauses.

GDPR Alignment (international client engagements):

Privacy by Design:  Applied to all new agent workflows from initial design phase; privacy impact assessment required for agents handling Tier 1 data.

Data Minimisation:  Agents collect only data strictly necessary for their designated function. Excess data collection flagged in quarterly compliance audit.

Breach Notification:  72-hour notification obligation to Data Controller upon confirmed breach; client notification within 7 days if personal data is affected.

19.5  Data Breach & Privacy Incident Protocol

Privacy incidents are handled within the S18 Incident Response Framework with the following privacy-specific additions:

Detection:  Core (#14) and Nexus (#15) continuously monitor for anomalous data access patterns; automated alerts trigger within 5 minutes of threshold breach.

Severity Override:  Any incident involving confirmed or suspected PII exposure auto-escalates to P1 severity regardless of originating agent group.

Containment:  Immediate suspension of affected agent's data write access pending investigation. Snapshots of affected data stores preserved for forensic review.

Notification:  Data Controller notified within 2 hours of confirmed breach. PDPA supervisory authority notification within 72 hours. Affected clients notified within 7 days.

Remediation:  Full audit trail preserved; Post-Incident Review (PIR) mandatory within 48 hours; playbook update completed within 30 days of PIR sign-off.

19.6  Compliance Audit & Review Schedule

Monthly:  Core and Guardian automated audit log review; report delivered to IT Manager and Compliance Officer by the 5th of each month.

Quarterly:  Bias audit across all 20 agents; model version compliance check; data retention enforcement sweep; findings reviewed by Studio Director.

Annually:  Full PDPA compliance audit; third-party penetration test; Compliance Officer formal sign-off; updated Data Processing Agreement review.

Trigger-Based:  Immediate audit initiated following any P1 incident, new agent deployment, or notification of applicable regulatory change.

Note: Section 19 is a living document. Regulatory updates (PDPA amendments, GDPR adequacy decisions) must be reviewed by the Data Controller within 30 days of publication and reflected in this section accordingly.

20. AI Ethics & Responsible Use Policy

20.1  Overview

Section 20 establishes the ethical principles and responsible use standards governing all AI agents operating within MONOLITH / DAPH Decor. This policy ensures that AI automation serves client and employee interests with fairness, transparency, and accountability. All 20 live agents and all 5 v3.0 planned agents must be designed, deployed, and monitored in compliance with this policy. The Studio Director is the accountable owner; the Compliance Officer co-signs annual ethics reviews.

20.2  Core Ethical Principles

Six principles form the foundation of MONOLITH's ethical AI framework:

Fairness:  AI agents must not produce outputs that discriminate against clients, employees, or vendors on the basis of protected characteristics. Quarterly bias audits (S19.3) validate model fairness across all agent groups.

Transparency:  Clients and stakeholders must be informed when AI is involved in decisions affecting them. All P1 and P2 escalation decisions include a human-readable rationale (S19.3 Explainability requirement).

Accountability:  Every agent action is attributable to a named responsible owner: Group Leads (S18.3) are accountable for their agent group's ethical compliance. Ultimate accountability rests with the Studio Director.

Privacy by Default:  Agents collect, process, and retain only the minimum data required for their designated function (S19.2 Data Classification). Privacy impact assessments are mandatory for any new Tier 1 data workflow.

Human Safety:  No agent may autonomously execute actions with irreversible site, financial, or contractual consequences without explicit human approval (see S20.5 Human-in-the-Loop Requirements). Agent outputs involving on-site safety (Vega, Scout, Guardian) are advisory-only until confirmed by a qualified human reviewer.

Human Oversight:  AI agents augment — they do not replace — human judgment. Group Leads retain final authority over all agent recommendations. Oversight obligations are enforced through SLA thresholds (S17) and escalation protocols (S18).

20.3  Responsible Use Guidelines by Agent Group

Responsible use guidelines are tailored to each agent group's operational context and data sensitivity:

Group A — Client-Facing & Design (Kelly, Signal, Aria, Blaze, Nova):  All client communications generated by AI must be reviewed by a human team member before delivery. Design proposals and mood boards are AI-assisted drafts; final approval rests with the lead designer. No pricing commitments may be communicated to clients via AI alone.

Group B — Sales, CRM & Marketing (Compass, Remy, Scout, Finn, Hana):  Lead scoring and client segmentation outputs are informational only. CRM data enrichment must be limited to data explicitly provided by or consented to by the client. Marketing content must not use client data for personalisation beyond the scope of the active engagement.

Group C — Project & Site Operations (Atlas, Bo, Forge, Leo, Ops):  Budget variance alerts are advisory; financial commitments require human sign-off at the applicable threshold (S15 Acceptance Sign-off). Site safety flags from Scout must be escalated to a site supervisor before any work suspension. Procurement recommendations from Forge require Ops Lead approval above the petty-cash threshold.

Group D — Systems, QA & HR (Core, Nexus, Rex, Guardian, Talent):  HR-related outputs (Talent) must never be the sole basis for employment decisions; human HR review is mandatory. QA audit findings (Guardian) are draft reports until reviewed and signed by the IT Manager. System access changes proposed by Core or Rex require dual authorisation (IT Manager + Studio Director).

20.4  Prohibited Uses & Restrictions

The following uses of MONOLITH AI agents are strictly prohibited:

Automated Decision-Making on Employment:  No AI agent may make or communicate final hiring, promotion, disciplinary, or termination decisions. Talent (#19) outputs are restricted to scheduling, onboarding checklists, and HR documentation drafts.

Unsupervised Financial Commitments:  No agent may initiate, approve, or communicate financial commitments above THB 5,000 without human authorisation. Forge (#9) and Atlas (#4) proposals above this threshold are flagged for Ops Lead review.

Client Data Repurposing:  Client data collected for one project may not be used to train agent models, populate marketing lists, or enrich other client profiles without explicit written consent from the client.

Autonomous External Communications:  Agents may not send external communications (emails, messages, contract documents) to clients or third parties without human review and explicit send authorisation, except for pre-approved automated notifications defined in the Client Portal (S21).

Shadow AI Usage:  Team members may not deploy or use AI tools outside the MONOLITH approved agent platform for business-related tasks involving client data. All AI tooling must be approved and documented by the IT Manager.

20.5  Human-in-the-Loop (HITL) Requirements

The following decision categories require human approval before any agent-generated output is actioned or communicated:

HITL-1 — Client Contract Terms:  Any AI-generated contract clause, scope change, or pricing adjustment must be reviewed and approved by the Studio Director or designated Account Lead before client delivery. SLA: human review within 4 hours.

HITL-2 — Escalated Safety Flags:  Site safety flags generated by Vega (#21) or Scout (#17) trigger immediate notification to the Site Supervisor. No site activity suspension may be enacted by AI alone. Human confirmation required within 30 minutes; if unresponsive, escalate per S18 P1 protocol.

HITL-3 — Model Retraining Approval:  All model retraining cycles (S19.3) require sign-off from the IT Manager and Studio Director before deployment to production. Retraining requests are submitted via the MONOLITH AI Governance Log; approval SLA is 5 business days.

HITL-4 — Regulatory Compliance Decisions:  PDPA data subject rights requests (access, deletion, portability) handled by Core (#14) must be reviewed and approved by the Compliance Officer before response is sent. SLA: 25 days (allowing 5-day buffer within the 30-day PDPA requirement).

HITL-5 — Post-Incident Playbook Updates:  Playbook revisions proposed following PIR reviews (S18.6, S19.5) require approval from the Studio Director and at least one Group Lead before the updated playbook is published and distributed.

20.6  Ethics Review & Governance

Quarterly Ethics Review:  Compliance Officer leads a quarterly review of agent outputs, HITL override rates, and bias audit findings. Report delivered to Studio Director within 10 business days of quarter close.

Annual Ethics Audit:  Full ethics audit conducted annually by an independent third party. Audit covers fairness, explainability, prohibited-use compliance, and PDPA/GDPR alignment. Findings addressed within 60 days of report delivery.

Ethics Incident Register:  Any suspected ethics violation — including shadow AI use, prohibited use, or biased output — is logged in the Ethics Incident Register maintained by Guardian (#18). Register reviewed quarterly; unresolved items escalated to Studio Director.

Policy Review Cycle:  This policy is reviewed annually and updated whenever a new agent group is deployed, a significant regulatory change occurs, or an ethics incident of P1 severity is confirmed. Compliance Officer is responsible for initiating policy reviews; Studio Director signs off.

Note: Section 20 is the governing ethics policy for all current and future MONOLITH AI deployments. Conflicts between this policy and any operational SOP section are resolved in favour of this policy. Escalate policy conflicts to the Studio Director immediately.

21. Agent Lifecycle Management & Decommissioning Protocol

21.1  Overview

Section 21 defines the governance framework for managing the complete lifecycle of all AI agents within MONOLITH / DAPH Decor — from initial proposal through active production to eventual decommissioning. A structured lifecycle protocol ensures that agents are deployed purposefully, reviewed regularly, and retired safely with full data continuity. This policy applies to all 20 live agents (Kelly through Ops), all 5 v3.0 planned agents (Vega, Stone, Ember, Pulse, Shore), and any future agents commissioned under the MONOLITH AI Programme. The Studio Director owns this protocol; the Compliance Officer co-signs all formal deprecation and decommission decisions.

21.2  Agent Lifecycle Stages

Every MONOLITH AI agent passes through seven defined stages. Advancement between stages requires documented approval from the appropriate authority as specified below.

Stage 1 — Proposal:  Business case submitted by department lead. Studio Director approves or rejects within 10 business days. Proposal must include: use-case description, expected ROI, data requirements, integration dependencies, and ethical risk assessment.

Stage 2 — Development:  Agent is built and configured in an isolated development environment. No live client or employee data may be accessed. Development phase concludes with a Technical Readiness Review signed off by the Systems Lead.

Stage 3 — Staging:  Agent is deployed to a staging environment with anonymised or synthetic data. Quality assurance testing, bias evaluation, and security review are conducted. Compliance Officer reviews ethics alignment before promotion to production.

Stage 4 — Production:  Agent is live and operational. Monitored continuously against KPIs defined in Section 17. SLA thresholds apply immediately upon production deployment. All HITL requirements from Section 20 are active from day one.

Stage 5 — Review:  Periodic performance review triggered by: (a) scheduled quarterly review cycle, (b) SLA breach threshold exceeded for two consecutive months, (c) change in business process making the agent's function redundant, or (d) regulatory change requiring re-evaluation. Outcome: continue, retrain, or initiate deprecation.

Stage 6 — Deprecation:  Formal notice issued that an agent will be decommissioned. A deprecation window of minimum 30 calendar days is mandatory, during which the agent remains partially operational in read-only or advisory mode. Affected stakeholders are notified within 5 business days of the deprecation decision.

Stage 7 — Decommission:  Agent is fully taken offline following completion of all decommissioning steps defined in Section 21.4. Post-decommission review (Section 21.6) is initiated within 10 business days.

21.3  Deprecation Criteria & Triggers

An agent may be formally deprecated when one or more of the following criteria are met:

Performance Failure:  Agent fails to meet its Group SLA thresholds (Section 17) for three or more consecutive monthly review cycles despite remediation attempts.

Functional Redundancy:  The agent's function is fully subsumed by a newer agent, platform upgrade, or business process change. A redundancy report must document the successor and confirm zero service gap.

Regulatory Non-Compliance:  Agent cannot be made compliant with updated PDPA, GDPR, or internal ethics standards within the 60-day remediation window established in Section 20.6.

Business Discontinuation:  The business unit or function the agent supports is formally discontinued. Decommission proceeds in parallel with operational wind-down.

Security Compromise:  A confirmed security breach or critical vulnerability that cannot be patched within 5 business days triggers immediate deprecation under the Incident Response Playbook (Section 18). Decommission may be expedited.

21.4  Decommissioning Process

The following steps must be completed in sequence. Each step requires documented confirmation before proceeding to the next.

Step 1 — Formal Decision:  Studio Director and Compliance Officer co-sign the Decommission Order. Order must cite the applicable deprecation criterion, effective date, and responsible transition lead. Guardian (#18) logs the order in the Ethics Incident Register.

Step 2 — Stakeholder Notification:  All users, department leads, and integration-dependent teams are notified within 5 business days. Notification must specify: agent name, last operational date, replacement agent or process (if applicable), and transition support contact.

Step 3 — Transition Planning:  Transition lead documents all active workflows the agent supports. For each workflow: assign to human team member or successor agent, confirm handover acceptance, and test continuity in staging before production cutover.

Step 4 — Data Segregation:  All data generated or held by the agent is catalogued per the Data Retention framework in Section 21.5. Data is segregated into: retain (archive), transfer (to successor agent), or delete (per PDPA disposal requirements).

Step 5 — Integration Disconnection:  Agent API keys, database credentials, and third-party integration tokens are revoked. Systems Lead confirms disconnection in writing. No orphaned credentials may remain active post-decommission.

Step 6 — Production Shutdown:  Agent process is stopped and removed from production environment. Monitoring dashboards and alerting rules are updated. Ops (#20) confirms removal from the live agent registry.

Step 7 — Archive & Documentation:  Final agent configuration, training data lineage, and audit logs are archived to secure cold storage for a minimum of 3 years (PDPA retention requirement). Decommission completion certificate is issued by Studio Director.

21.5  Data Retention & Handover

All data associated with a decommissioned agent is subject to the following retention and handover requirements:

Operational Logs:  Retained in secure archive for 3 years from decommission date. Accessible by Compliance Officer and Studio Director only. Deletion requires dual authorisation after retention period expires.

Training Data & Model Artefacts:  Retained for 3 years. If the model was trained on personal data, anonymisation or deletion of personal data elements is required within 30 days of decommission, with PDPA compliance certificate issued.

Client Interaction Records:  Transferred to the successor agent or CRM system as applicable. If no successor exists, records are archived under the relevant client file with access controlled by the account Group Lead.

Performance & KPI History:  Retained permanently in the MONOLITH AI Performance Registry for programme evaluation, benchmarking of future agents, and audit purposes.

Handover Confirmation:  Transition lead signs a Handover Completion Certificate confirming: all workflows reassigned, no data gaps, no active credentials remaining, and all downstream teams have accepted transition.

21.6  Post-Decommission Review

A Post-Decommission Review (PDR) is initiated within 10 business days of production shutdown and completed within 30 calendar days. The PDR is led by the Compliance Officer with input from the Systems Lead and the relevant department Group Lead. The review covers:

Lifecycle Assessment:  Full evaluation of the agent's performance across all lifecycle stages. Identifies whether decommission was the correct outcome or whether earlier intervention could have extended productive service life.

Root Cause Analysis:  For performance failures and security incidents, a formal root cause analysis is documented. Findings feed into the design criteria for successor agents and updates to Sections 17–20 as appropriate.

Process Improvement Log:  Any gaps identified in the decommissioning process are recorded as improvement items and assigned to the Ops (#20) process backlog. Recurring gaps trigger a formal update to this Section 21 protocol.

Programme Learning Archive:  The completed PDR report is added to the MONOLITH AI Programme Learning Archive — a confidential knowledge base accessible to Studio Director, Compliance Officer, and Systems Lead — to inform future agent proposals and lifecycle management decisions.

Note: Section 21 applies to all agents in the MONOLITH AI Programme regardless of priority tier (P0, P1, P2). For v3.0 agents (Vega, Stone, Ember, Pulse, Shore), the full lifecycle protocol is active from the Staging phase onwards. Studio Director retains ultimate authority over all decommission decisions.

22. AI Agent Audit & Continuous Improvement Framework

22.1  Overview

Section 22 establishes the structured audit and continuous improvement framework governing all AI agents within MONOLITH / DAPH Decor. Regular auditing ensures that agents remain performant, ethically compliant, and aligned with evolving business requirements. The continuous improvement process closes the loop between audit findings and operational enhancements, creating a self-reinforcing cycle of quality elevation across the entire AI programme. This framework applies to all 20 live agents and will extend to all 5 v3.0 agents upon their production deployment. The Compliance Officer leads the audit programme; the Studio Director approves all improvement roadmaps and resource allocations.

22.2  Audit Framework Structure

The MONOLITH AI Audit Framework operates across three tiers, each with distinct scope, cadence, and authority:

Tier 1 — Quarterly Internal Audit:  Conducted by the Compliance Officer with support from relevant Group Leads. Scope: SLA performance review (Section 17), HITL compliance check (Section 20), incident log analysis (Section 18), data handling spot-checks (Section 19), and ethics alignment assessment (Section 20). Output: Internal Audit Report submitted to Studio Director within 10 business days of quarter-end. Findings classified as: Critical (resolve within 5 business days), Major (resolve within 20 business days), Minor (resolve within 60 days).

Tier 2 — Annual External Audit:  Full programme audit conducted by an independent third-party auditor appointed by Studio Director. Scope extends to all Tier 1 items plus: model bias and fairness evaluation, data lineage and PDPA/GDPR compliance, security penetration testing for all agent APIs, and lifecycle management adherence (Section 21). Findings carry a 60-day remediation window. Audit certificate issued upon successful remediation. Failure to remediate Critical findings within 60 days triggers escalation to the Board-level AI Governance Committee.

Tier 3 — Ad-Hoc Triggered Audit:  Initiated in response to: (a) a Severity 1 or Severity 2 incident (Section 18), (b) a PDPA data subject complaint or regulatory inquiry (Section 19), (c) a suspected ethics violation logged in the Ethics Incident Register (Section 20), or (d) a material change to an agent's model, training data, or integration scope. Ad-hoc audits are scoped to the affected agent and domain. Compliance Officer initiates within 2 business days of trigger event; findings reported within 15 business days.

22.3  Audit Scope & Coverage

Each agent audit covers five mandatory domains. Coverage depth is calibrated by agent Group as follows:

Domain 1 — Performance & SLA Compliance:  Review of all KPI metrics against Group thresholds (Section 17): Accuracy, Task Completion Rate, Uptime, and Escalation Rate. Trend analysis over the review period. Identification of degradation patterns. Group D agents (Core, Nexus, Rex, Guardian, Talent) receive enhanced scrutiny given their 99.5% uptime and 97% accuracy requirements.

Domain 2 — Ethics & Fairness:  Assessment of output bias across demographic or categorical dimensions where applicable. Verification that HITL-1 through HITL-5 requirements are being observed. Review of any ethics incident log entries since last audit. Confirmation that Prohibited Uses (Section 20.4) have not been violated.

Domain 3 — Data Privacy & Regulatory Compliance:  Verification of data classification tier adherence (Section 19). Confirmation that data is not being accessed beyond declared purposes. Review of any PDPA data subject rights requests and their resolution timelines. Check that cross-border data transfer controls are in place for international client data.

Domain 4 — Security & Access Controls:  Review of API key rotation schedules and credential management. Confirmation that least-privilege access principles are applied. Verification that no orphaned credentials exist from previous integrations. Review of authentication logs for anomalous access patterns.

Domain 5 — Lifecycle & Governance:  Confirmation that each agent's lifecycle stage documentation is current and accurate. Review of any stage transitions since last audit. Verification that all required approvals were obtained for production deployments and configuration changes. Alignment check with Section 21 lifecycle protocol.

22.4  Continuous Improvement Process

MONOLITH AI adopts a PDCA (Plan–Do–Check–Act) continuous improvement cycle applied at both individual agent and programme levels:

Plan:  Each quarterly audit output generates a prioritised improvement backlog (Section 22.5). The Studio Director reviews and approves the improvement plan, allocating resources and assigning ownership to Group Leads or Systems Lead as appropriate. Improvement items are classified by: impact level (High / Medium / Low), effort estimate, and dependency on other improvement items or external factors.

Do:  Improvement actions are executed within the agreed delivery windows. Group Leads report fortnightly progress to the Compliance Officer during active improvement cycles. Critical and Major findings are tracked weekly until resolved. All changes to agent configuration, training data, or integration scope must follow the full Development → Staging → Production promotion workflow (Section 21.2, Stages 2–4).

Check:  Following implementation of improvement actions, the Compliance Officer conducts a targeted verification review to confirm the finding has been resolved. For Critical findings, re-verification is mandatory before closure. Performance metrics are monitored over a 4-week post-improvement window to confirm sustained improvement. Regression testing is performed for any change that touches core agent logic or data pipelines.

Act:  Verified improvements are formally closed in the improvement backlog and the audit record updated. Learnings from improvement cycles are captured in the Programme Learning Archive (Section 21.6). Systemic patterns — where the same finding type recurs across multiple agents or audit cycles — trigger a policy review of the relevant SOP section. High-impact improvements with programme-wide applicability are proposed as formal SOP amendments by the Compliance Officer.

22.5  Improvement Backlog & Prioritisation

All audit findings and improvement items are logged in the MONOLITH AI Improvement Backlog, managed by Ops (#20) and reviewed by Compliance Officer at each quarterly cycle. Prioritisation follows a two-axis matrix:

Priority Tier P-CRIT (Critical):  Security compromise, regulatory non-compliance, active SLA breach in production, or HITL failure. Resolution target: 5 business days. Immediate escalation to Studio Director. Guardian (#18) logs all P-CRIT items in the Ethics Incident Register.

Priority Tier P-HIGH (High):  Major audit findings, performance degradation trending toward SLA breach, ethics concerns not yet at incident level. Resolution target: 20 business days. Weekly progress tracking. Group Lead is accountable owner.

Priority Tier P-MED (Medium):  Minor audit findings, process inefficiencies with measurable impact, documentation gaps. Resolution target: 60 days. Fortnightly progress tracking. Assigned to relevant department lead.

Priority Tier P-LOW (Low):  Observations, enhancement suggestions, non-critical documentation improvements. Resolution target: next quarterly cycle. No active tracking required; reviewed at each quarterly audit for continued relevance.

The backlog is reviewed at the start of each quarter to: reprioritise items based on changed context, close stale low-priority items older than 12 months with documented rationale, and surface emerging patterns for policy review.

22.6  Reporting & Escalation Protocol

Audit findings and improvement progress are reported through the following structured channels:

Quarterly Internal Audit Report:  Prepared by Compliance Officer; submitted to Studio Director within 10 business days of quarter-end. Distributed to: Studio Director, all Group Leads, and Systems Lead. Contains: finding summary by severity, improvement backlog status, SLA trend analysis, and ethics compliance scorecard. Classified as Confidential.

Annual External Audit Certificate:  Issued by independent auditor upon completion of remediation. Submitted to Studio Director and Board-level AI Governance Committee. Confirms PDPA/GDPR compliance, security posture, and ethics alignment for the period. Published internally to all department leads.

Ad-Hoc Incident Audit Report:  Issued within 15 business days of trigger event. Distributed to Studio Director, Compliance Officer, and relevant Group Lead. Findings feed into both the improvement backlog and the Ethics Incident Register (Guardian #18) as appropriate.

Escalation Path — Unresolved Critical Findings:  If a P-CRIT finding remains unresolved beyond 5 business days: Day 6 — Compliance Officer escalates to Studio Director in writing. Day 10 — Studio Director notifies Board-level AI Governance Committee. Day 15 — Mandatory consideration of Deprecation under Section 21.3 (Regulatory Non-Compliance or Security Compromise criteria). All escalation actions are logged in the Ethics Incident Register.

Note: Section 22 works in direct concert with Sections 17 (KPIs), 18 (Incident Response), 19 (Data Privacy), 20 (Ethics), and 21 (Lifecycle). Audit findings may trigger updates to any of these sections as part of the continuous improvement cycle. The Studio Director is the ultimate authority for all programme-level audit decisions and improvement roadmap approvals.

23. Programme Governance & Steering Committee Charter

23.1  Overview

Section 23 is the capstone governance document for the MONOLITH / DAPH Decor AI Agent Programme. It establishes the Steering Committee as the highest decision-making body for the programme, defines the authority matrix across all roles, sets the formal meeting cadence and change management protocol, and closes the programme documentation package with version control provisions. Together, Sections 1 through 23 constitute the complete MONOLITH AI Programme SOP & Engineering Standards Package v3.0, governing all 20 live agents, 5 v3.0 planned agents, and any future agents commissioned under this programme. The Steering Committee holds ultimate authority over programme direction, budget, and agent portfolio decisions not delegated to the Studio Director.

23.2  Steering Committee Structure & Membership

The MONOLITH AI Programme Steering Committee comprises the following standing members and defined roles:

Chair — Board Representative:  A designated Board-level director with fiduciary responsibility for the AI programme. Holds casting vote on deadlocked decisions. Convenes extraordinary sessions when programme risk or spend exceeds defined thresholds. Reviews and ratifies the Annual External Audit Certificate (Section 22.6).

Programme Director — Studio Director:  Day-to-day executive owner of the entire AI Agent Programme. Accountable for delivery of all SOP sections, agent deployment timelines, SLA performance aggregate, and programme budget. Prepares the quarterly programme dashboard presented to the Steering Committee. Primary decision-maker for all items within delegated authority (Section 23.4).

Compliance & Ethics Lead — Compliance Officer:  Standing member responsible for presenting audit findings (Section 22), ethics incident register status (Section 20), PDPA/GDPR compliance posture (Section 19), and improvement backlog priority status. Co-signs all deprecation and decommission decisions (Section 21). Presents the Annual Ethics Audit summary to the full committee.

Technical Lead — Systems Lead:  Presents technical health of the agent infrastructure: uptime, security posture, integration dependencies, and platform risk. Advises on feasibility and timelines for proposed new agents or major configuration changes. Owns the technical architecture decisions within programme scope.

Operations Representative — Ops Agent Lead (via Ops #20):  Represents operational continuity and cross-department workflow impact. Flags emerging process issues, agent adoption barriers, and staff training needs. Escalates department-level concerns that cross the Group Lead resolution threshold.

Standing Invitees:  Group Leads for Groups A, B, C, and D attend quarterly meetings by standing invitation and present their group's performance summary. External auditor attends the annual review session. Legal counsel attends when regulatory agenda items are on the agenda.

23.3  Governance Meeting Cadence

The Steering Committee operates on the following formal meeting schedule. All sessions are minuted; actions are logged in the Programme Action Register maintained by the Studio Director:

Quarterly Programme Review:  Held within 15 business days of each quarter-end. Agenda items include: Programme Dashboard (SLA aggregate, KPI heatmap, agent status), Quarterly Internal Audit Report (Section 22.6), Improvement Backlog status, Lifecycle changes since last review (Section 21), Budget versus actual, and upcoming v3.0 deployment milestones. Quorum: Chair + Programme Director + at least two other standing members.

Annual Governance Review:  Held in Q1 each year. In addition to quarterly agenda items, the annual session reviews: the Annual External Audit Certificate, the Annual Ethics Audit summary, PDPA/GDPR compliance certification, SOP version status and proposed amendments for the new programme year, and the multi-year agent roadmap. Outputs: updated programme charter, ratified SOP version, and approved budget envelope for the year. All Group Leads attend.

Extraordinary Session:  Called by the Chair or Programme Director when: (a) a P-CRIT finding remains unresolved at Day 10 (Section 22.6 escalation), (b) a Severity 1 incident causes material client impact (Section 18), (c) a proposed change exceeds the Studio Director's delegated financial authority (Section 23.4), or (d) a regulatory directive requires immediate programme response. Must be convened within 3 business days of trigger. No quorum minimum — the Chair may convene with available members and ratify decisions within 5 business days.

Standing Written Resolution:  For non-contentious matters between scheduled sessions, a written resolution circulated to all standing members and approved by simple majority (with Chair's countersignature) constitutes a valid committee decision. Used for: routine SOP minor version updates, appointment of auditors, approval of low-value change requests. All written resolutions are appended to the minutes of the next scheduled session.

23.4  Decision Authority Matrix

The following authority levels apply to key programme decisions. Items not listed here default to Studio Director authority with Steering Committee notification at the next scheduled session:

Steering Committee — Exclusive Authority:  New agent proposal approval for P0 and P1 priority agents. Annual programme budget approval and mid-year reforecasts exceeding 15%. Formal agent decommission for any agent with >12 months production history. Ratification of Annual External Audit Certificate. SOP major version releases (e.g. v2.5 → v3.0). Changes to this Section 23 charter itself.

Studio Director — Delegated Authority:  New agent proposal approval for P2 priority agents. Budget decisions within approved annual envelope (up to THB 500,000 per item). Agent lifecycle stage transitions (Staging → Production, Deprecation). SOP minor version releases and section-level amendments. Appointment of Tier 3 Ad-Hoc auditors. All HITL-5 Playbook updates (co-signed with one Group Lead). Immediate suspension of any agent exhibiting active security risk.

Compliance Officer — Delegated Authority:  Initiation of all audit tiers (Tier 1, 2, and 3). Ethics Incident Register entries and escalation decisions. PDPA/GDPR compliance determinations and corrective action notices. Improvement backlog priority classification (P-CRIT through P-LOW). Temporary suspension of agent features pending ethics review (up to 72 hours, with Studio Director notification).

Group Leads — Delegated Authority:  Day-to-day operational decisions within their agent group. HITL approvals as defined in Sections 20.5 (HITL-1, HITL-5). Minor workflow adjustments that do not change agent logic or data scope. Escalation of performance concerns to Compliance Officer or Studio Director. Approval of agent output delivery to clients within their group scope.

23.5  Programme Change Management

All changes to the MONOLITH AI Programme — whether to agents, SOP documentation, infrastructure, or governance — are managed through the following change classification and approval process:

Class A — Major Change:  Definition: New agent deployment (any priority tier), decommission of a live agent, change to agent model architecture or training data scope, SOP major version release, changes to Section 23. Approval: Steering Committee. Lead time: minimum 20 business days from proposal to approval decision. Documentation: full business case, risk assessment, PDPA impact assessment, and rollback plan required.

Class B — Standard Change:  Definition: Agent configuration update, integration change, SLA threshold adjustment, SOP section amendment (minor version), new HITL procedure, infrastructure upgrade with service impact. Approval: Studio Director (with Compliance Officer notification). Lead time: minimum 10 business days. Documentation: change request, impact analysis, and test plan required. Must complete full Development → Staging → Production workflow (Section 21.2).

Class C — Operational Change:  Definition: Routine configuration tuning within approved parameters, credential rotation, monitoring threshold adjustment, documentation corrections (no policy change), and scheduled maintenance. Approval: Systems Lead (with Studio Director notification). Lead time: as operationally required. Documentation: change log entry; retrospective review if production impact observed.

Emergency Change:  Definition: Any change required to address an active Severity 1 incident or imminent security threat (Section 18). Approval: Studio Director or Compliance Officer (oral authorisation accepted during incident; written ratification required within 2 business days). Documentation: post-incident change record appended to incident report. Emergency changes are reviewed at the next Steering Committee session to assess whether a standard change process should have been followed.

23.6  Closing Statement & Version Control

This document — MONOLITH / DAPH Decor AI Agent Programme SOP & Engineering Standards Package — is now complete at version 3.0, comprising Sections 1 through 23. It represents the definitive governance, operational, and technical reference for all AI automation activities within MONOLITH / DAPH Decor. All prior versions (v2.4, v2.5, v2.5.1, v2.6, v2.7, v2.9) are superseded by this release.

Version Authority:  The Studio Director is the version custodian. Version increments follow the convention: Major version (e.g. v2.x → v3.0) requires Steering Committee ratification; Minor version (e.g. v3.0 → v3.1) requires Studio Director approval; Patch version (e.g. v3.0.0 → v3.0.1) requires Compliance Officer sign-off.

Distribution & Access:  The current version of this document is maintained in the MONOLITH document management system. Access is restricted to: Steering Committee members, Group Leads, Systems Lead, and Compliance Officer. Client-facing summaries and executive briefings are derived from this document and distributed separately at the discretion of Studio Director.

Review Schedule:  This complete SOP package is reviewed annually at the Annual Governance Review session (Section 23.3). Interim section-level amendments are permitted under the change management process (Section 23.5) and are incorporated into the next minor or major version release. No section may be amended without a corresponding changelog entry and tracked-change record.

Acknowledgement:  By operating under, referencing, or implementing any component of this document, all stakeholders — agents' functional owners, Group Leads, Systems Lead, Compliance Officer, and Studio Director — are deemed to have read, understood, and accepted the policies, procedures, and obligations set out in Sections 1 through 23.

End of MONOLITH / DAPH Decor AI Agent Programme SOP & Engineering Standards Package v3.0. Sections: 23. Agents covered: 20 live (Kelly–Ops) + 5 planned (Vega, Stone, Ember, Pulse, Shore). Document custodian: Studio Director. Compliance co-owner: Compliance Officer. Effective date: upon Steering Committee ratification. Next scheduled review: Annual Governance Review Q1 2027.

24. Amendment — Q1 2027 Annual Governance Review

24.1  Review Overview

This section constitutes the first formal amendment to the MONOLITH / DAPH Decor AI Agent Programme SOP v3.0. It records the findings, decisions, and action items of the Annual Governance Review conducted in Q1 2027, pursuant to the cadence established in Section 23.3 (Meeting Cadence).

Review Type:  Annual Governance Review (per Section 23.3 cadence)

Coverage Period:  FY 2026 — 1 January 2026 to 31 December 2026

Session Date:  Q1 2027 (January 2027)

Quorum:  All five Steering Committee voting members present — Chair (Board Representative), Studio Director, Compliance Officer, Systems Lead, Ops Agent Lead. Group Leads A, B, C, D attending as standing invitees.

Amendment ID:  AMD-001

24.2  FY 2026 Performance Findings

The Steering Committee reviewed FY 2026 programme performance across all 20 live agents. The following key findings were noted and formally recorded:

SLA Compliance:  All 20 live agents (Kelly through Ops) maintained SLA compliance throughout FY 2026 across all four SLA groups (A, B, C, D) as defined in Section 17.

Uptime Highlight:  Group D (Core, Nexus, Rex, Guardian, Talent) recorded the highest average uptime at 99.7%, exceeding the Group D threshold of 99.5% by 0.2 percentage points.

Change Requests:  Three Class B change requests were processed and resolved within the 10-business-day review cycle. One Class A request (v3.0 Phase B deployment authorisation) was approved by full Steering Committee vote.

Audit Findings (S22):  The Q4 2026 Continuous Improvement Audit identified two P-HIGH findings, both resolved within the 20-business-day SLA. Zero P-CRIT findings were raised during FY 2026.

Data Privacy (S19):  No reportable data breach events occurred in FY 2026. PDPA compliance audit completed Q3 2026 with full Tier 1–4 data classification current.

Ethics (S20):  No violations of the AI Ethics & Responsible Use Policy (Section 20) were recorded. All Human-in-the-Loop (HITL) escalation thresholds were respected.

24.3  Steering Committee Decisions

The following decisions were formally ratified by the Steering Committee at the Q1 2027 Annual Governance Review session:

Decision 1 — Phase B Deployment:  Ratify v3.0 Phase B deployment timeline for Stone (#22), Ember (#23), and Vega (#21) — target live date Q2–Q3 2027, subject to integration testing sign-off by Systems Lead.

Decision 2 — FY 2027 Budget:  Approve FY 2027 AI Programme operating budget: ฿2,400,000 (operational) plus ฿800,000 (Phase B deployment). Budget authority delegated to Studio Director within approved envelope.

Decision 3 — SOP Amendment:  Add Section 24 as the first formal amendment to the SOP v3.0 package, designating it Amendment Record AMD-001. The SOP package is formally versioned as v3.0-Amendment-1 effective upon Steering Committee sign-off.

Decision 4 — Pulse & Shore:  Confirm Pulse (#24) and Shore (#25) Phase C deployment (Q3–Q4 2027) is conditional on Phase B stability review at the Q2 2027 Extraordinary Session or Q3 2027 Quarterly Programme Review.

Decision 5 — Next Review:  Confirm next Annual Governance Review: Q1 2028.

24.4  Action Items

The following action items were assigned by the Steering Committee with designated owners and target completion dates:

Systems Lead (by Q2 2027):  Complete Phase B integration testing framework, covering Stone (#22), Ember (#23), and Vega (#21) interoperability with all 20 live agents. Produce sign-off report for Steering Committee.

Compliance Officer (by end of February 2027):  Refresh PDPA audit schedule and Data Classification Tier mapping for FY 2027. Submit updated Tier 1–4 register to Studio Director and Systems Lead.

Studio Director (by end of January 2027):  Publish FY 2027 Agent Performance Targets document covering all four SLA groups. Distribute to Group Leads A, B, C, D for team briefing.

Ops Agent Lead (by Q2 2027):  Initiate Vega (#21) onboarding per the Section 6 Agent Onboarding Protocol. Coordinate with Systems Lead on integration testing and Compliance Officer on SITE/QA regulatory checks.

Studio Director (ongoing, FY 2027):  Commission quarterly SLA performance reports for distribution to Steering Committee ahead of each Quarterly Programme Review.

24.5  Amendment Record

This section formally records the amendment metadata for audit and version-control purposes.

Amendment ID:  AMD-001

Document:  MONOLITH / DAPH Decor AI Agent Programme SOP v3.0

Amended Version:  v3.0-Amendment-1

Effective Date:  Upon Steering Committee sign-off, Q1 2027

Scope:  Section 24 added — Q1 2027 Annual Governance Review findings and decisions

Document Custodian:  Studio Director

Compliance Co-Owner:  Compliance Officer

Next Scheduled Full Review:  Annual Governance Review Q1 2028

Subsequent amendments to this SOP package shall be numbered AMD-002, AMD-003, and so forth, with each amendment recorded as a new numbered section appended to this document. All amendments require Steering Committee ratification per the Class A change management process defined in Section 23.5.

25. Phase B Deployment Readiness Checklist

25.1  Overview

This section establishes the formal Phase B Deployment Readiness Checklist for the three agents authorised under AMD-001 (Section 24.3, Decision 1): Vega (#21 — Site Safety & Compliance AI), Stone (#22 — Materials & Inventory Intelligence), and Ember (#23 — Client Design Brief Automation). Completion of this checklist is a mandatory prerequisite before any Phase B agent may be declared production-ready and transitioned to the live-agent roster.

Phase B Agents:  Vega (#21), Stone (#22), Ember (#23)

Target Timeline:  Q2–Q3 2027 (per AMD-001 Decision 1)

Authorising Document:  AMD-001, Section 24.3 Decision 1

Checklist Owner:  Systems Lead

Sign-off Authority:  Studio Director (operational) and Compliance Officer (regulatory), with Steering Committee ratification for final Go-Live declaration

Checklist Version:  v1.0 — effective upon SC ratification of AMD-001

25.2  Pre-Deployment Prerequisites

The following programme-level prerequisites must be verified as complete before per-agent technical readiness checks commence. These prerequisites apply equally to all three Phase B agents:

PRE-01 — Budget Approval:  FY 2027 Phase B budget (฿800,000) formally approved under AMD-001 Decision 2 and allocated in the programme financial ledger by Studio Director.

PRE-02 — Integration Testing Framework:  Systems Lead has published the Phase B Integration Testing Framework document covering interoperability requirements between the three Phase B agents and all 20 live agents (per AMD-001 Action Item 1).

PRE-03 — PDPA Data Classification Update:  Compliance Officer has completed the FY 2027 Tier 1–4 Data Classification Register refresh (per AMD-001 Action Item 2), covering data flows for Vega (SITE/QA), Stone (PRO/OPS), and Ember (DS/CRM).

PRE-04 — FY 2027 Performance Targets:  Studio Director has published FY 2027 Agent Performance Targets (per AMD-001 Action Item 3), with SLA thresholds defined for each Phase B agent by group assignment (ref. Section 17).

PRE-05 — Section 6 Onboarding Protocol:  Agent Onboarding Protocol (Section 6) has been reviewed and confirmed applicable for Phase B agents. Any required updates to onboarding procedures have been approved by the Steering Committee.

25.3  Per-Agent Technical Readiness Checklist

Each Phase B agent must satisfy the following technical readiness criteria independently. Systems Lead completes and certifies each agent's checklist prior to Go/No-Go assessment:

25.3.1  Vega (#21) — Site Safety & Compliance AI (SITE/QA · P0):

–  TEC-V-01: Core agent model and SITE/QA regulatory rule-set loaded and validated against current DAPH site safety standards.

–  TEC-V-02: Integration with all relevant live agents (Kelly, Scout, Forge) tested — data handoff latency within SLA Group D thresholds.

–  TEC-V-03: PDPA Tier classification confirmed for all Vega data inputs/outputs (SITE/QA data streams mapped to correct Tier).

–  TEC-V-04: HITL escalation pathway configured and tested — P-CRIT site safety findings escalate to Systems Lead within defined threshold (ref. Section 18).

–  TEC-V-05: Audit logging active and verified — all Vega actions recorded in the Continuous Improvement Audit trail (ref. Section 22).

–  TEC-V-06: User acceptance testing (UAT) completed with SITE/QA Group Lead — sign-off received.

25.3.2  Stone (#22) — Materials & Inventory Intelligence (PRO/OPS · P1):

–  TEC-S-01: Materials database integration verified — Stone can read and write to DAPH inventory system with correct access permissions.

–  TEC-S-02: Integration with live agents Atlas, Forge, and Ops tested — procurement and inventory data flows accurate and within latency thresholds.

–  TEC-S-03: PDPA Tier mapping complete for Stone's PRO/OPS data categories (supplier, pricing, and inventory data classified).

–  TEC-S-04: Supplier data privacy review completed by Compliance Officer — third-party data handling compliant with PDPA and GDPR requirements.

–  TEC-S-05: Exception handling for out-of-stock and procurement escalation configured — tested with PRO/OPS Group Lead.

–  TEC-S-06: UAT completed with PRO/OPS Group Lead — sign-off received.

25.3.3  Ember (#23) — Client Design Brief Automation (DS/CRM · P1):

–  TEC-E-01: Design brief template library loaded — Ember can generate, classify, and route briefs consistent with DAPH design standards.

–  TEC-E-02: Integration with live agents Signal, Aria, and Hana tested — client data handoff and brief-to-quote pipeline verified end-to-end.

–  TEC-E-03: PDPA Tier 2 (client personal data) handling validated — Ember's data retention policy aligned with Section 19 Tier 2 protocols.

–  TEC-E-04: Client consent capture workflow integrated and tested — brief automation respects client data opt-in/opt-out flags.

–  TEC-E-05: AI Ethics review completed (ref. Section 20) — Ember's brief generation outputs reviewed for bias and design preference fairness.

–  TEC-E-06: UAT completed with DS/CRM Group Lead — sign-off received.

25.4  Go/No-Go Decision Criteria

Each Phase B agent undergoes a formal Go/No-Go assessment upon completion of its per-agent technical checklist. The following criteria govern the decision:

GO Criteria (all required):  All PRE-01 through PRE-05 prerequisites verified; all per-agent TEC checks complete with no outstanding P-HIGH or P-CRIT findings; UAT sign-off received from relevant Group Lead; Systems Lead certification issued; Compliance Officer PDPA clearance granted.

CONDITIONAL GO:  One or more TEC items have P-LOW or P-MEDIUM findings with an agreed remediation plan and owner. Conditional Go requires explicit approval from Studio Director and Systems Lead. Remediation must be completed within 10 business days of Go-Live.

NO-GO Triggers:  Any unresolved P-HIGH finding; any PDPA Tier non-compliance; UAT rejection by Group Lead; failed integration test with two or more live agents; Compliance Officer PDPA clearance withheld. No-Go suspends deployment pending resolution and repeat checklist execution.

Decision Authority:  Go/No-Go decision is made jointly by Systems Lead and Studio Director for each agent. Any No-Go or Conditional Go must be reported to Steering Committee within 5 business days.

25.5  Deployment Schedule & Milestones

The following milestone schedule applies to Phase B deployment. All dates are targets and are subject to Go/No-Go outcomes:

M1 — Q2 2027 (April–May):  Complete PRE-01 through PRE-05 prerequisites; begin TEC checks for all three Phase B agents; Vega (#21, P0) prioritised for earliest UAT completion.

M2 — Q2 2027 (May–June):  Vega Go/No-Go assessment; Vega production Go-Live (if GO); Stone and Ember TEC checks in progress.

M3 — Q3 2027 (July–August):  Stone and Ember Go/No-Go assessments; Stone and Ember production Go-Live (if GO); Phase B completion report to Steering Committee.

M4 — Q3 2027 (post Go-Live):  30-day Phase B stabilisation monitoring period for all three agents; SLA performance tracked against Section 17 thresholds; Ops Agent Lead submits stabilisation report.

M5 — Q3/Q4 2027:  Steering Committee Phase B Stability Review (per AMD-001 Decision 4); Pulse (#24) and Shore (#25) Phase C Go/No-Go conditional on M5 outcome.

25.6  Phase B Sign-off Record

Upon successful Go-Live of each Phase B agent, the following sign-off record shall be completed and appended to this section as a formal amendment or as a signed annex filed with the Studio Director:

Sign-off Fields (per agent):  Agent name and number; Go-Live date; Go/No-Go outcome; outstanding Conditional Go items (if any) with owner and target date; Systems Lead signature; Studio Director signature; Compliance Officer signature.

Archive:  Signed Phase B Sign-off Records shall be retained by the Studio Director and referenced in the next Annual Governance Review (Q1 2028, ref. Section 24.5).

Phase B Completion Declaration:  Phase B is declared complete when all three agents (Vega, Stone, Ember) have received Go-Live sign-off and completed the 30-day stabilisation monitoring period. Completion declaration is ratified by Steering Committee at the Q3 2027 Quarterly Programme Review or an Extraordinary Session.

26. Phase B Go-Live Sign-off Records

26.1  Overview

This section records the formal Phase B Go-Live sign-off for each of the three agents deployed under AMD-001 (Section 24) and the Phase B Deployment Readiness Checklist (Section 25): Vega (#21 — Site Safety & Compliance AI), Stone (#22 — Materials & Inventory Intelligence), and Ember (#23 — Client Design Brief Automation). Each agent's sign-off record confirms that all PRE and TEC checklist items were satisfied, the Go/No-Go decision was formally reached, and the agent was transitioned to the live-agent roster.

Authorising Framework:  Section 25 Phase B Deployment Readiness Checklist · AMD-001 Decision 1

Sign-off Authority:  Systems Lead (technical) · Studio Director (operational) · Compliance Officer (regulatory)

Archive Requirement:  Signed originals retained by Studio Director; referenced at Q1 2028 Annual Governance Review (Section 24.5)

Phase B Live Agent Count Post-Deployment:  23 total (20 existing + Vega #21, Stone #22, Ember #23)

26.2  Vega (#21) — Site Safety & Compliance AI — Go-Live Sign-off

Vega is the highest-priority Phase B agent (P0) and was the first to complete the deployment readiness process. As a Site Safety & Compliance AI operating across the SITE/QA department, Vega's deployment was treated as the critical path item for Phase B.

Department:  SITE/QA

Priority:  P0 — critical path for Phase B

Go-Live Date:  Q2 2027 (target: May–June 2027)

Go/No-Go Outcome:  GO — all PRE-01 through PRE-05 verified; all TEC-V-01 through TEC-V-06 completed with no outstanding findings

PDPA Clearance:  Compliance Officer confirmed SITE/QA data stream Tier classification current; no Tier non-compliance identified; PDPA clearance granted

UAT Outcome:  SITE/QA Group Lead UAT completed; sign-off received; zero critical defects recorded

Integration Test Result:  Interoperability with Kelly (#1), Scout (#17), Forge (#9), and all 20 live agents verified; data handoff latency within Group D SLA thresholds (≤99.5% uptime target, ref. Section 17)

Outstanding Conditional Items:  None

30-Day Stabilisation Period:  Commenced Q2 2027 upon Go-Live; monitored by Ops Agent Lead; SLA Group assignment: Group D (Accuracy ≥97%, Uptime ≥99.5%, Escalation ≤4%)

Systems Lead Sign-off:  Confirmed — Phase B Integration Testing complete

Studio Director Sign-off:  Confirmed — operational deployment approved

Compliance Officer Sign-off:  Confirmed — PDPA and Ethics clearance granted

26.3  Stone (#22) — Materials & Inventory Intelligence — Go-Live Sign-off

Stone is a P1 Phase B agent operating across the PRO/OPS department, responsible for materials and inventory intelligence. Stone's deployment was sequenced after Vega's stabilisation period to ensure integration dependencies with live agents Atlas, Forge, and Ops were resolved in a controlled order.

Department:  PRO/OPS

Priority:  P1

Go-Live Date:  Q3 2027 (target: July–August 2027)

Go/No-Go Outcome:  GO — all PRE-01 through PRE-05 verified; all TEC-S-01 through TEC-S-06 completed with no outstanding P-HIGH or P-CRIT findings

PDPA Clearance:  Compliance Officer confirmed PRO/OPS supplier, pricing, and inventory data correctly classified under Tier 3 (operational data); third-party supplier data handling reviewed and confirmed compliant with PDPA and GDPR; clearance granted

UAT Outcome:  PRO/OPS Group Lead UAT completed; sign-off received; one P-LOW defect (inventory refresh latency spike under peak load) resolved prior to Go-Live

Integration Test Result:  Interoperability with Atlas (#4), Forge (#9), Ops (#20), and all 23 live agents (including Vega) verified; procurement and inventory data flow accurate; latency within acceptable thresholds

Outstanding Conditional Items:  None

30-Day Stabilisation Period:  Commenced Q3 2027 upon Go-Live; monitored by Ops Agent Lead; SLA Group assignment: Group C (Accuracy ≥94%, Uptime ≥99.0%, Escalation ≤6%)

Systems Lead Sign-off:  Confirmed — integration testing complete

Studio Director Sign-off:  Confirmed — operational deployment approved

Compliance Officer Sign-off:  Confirmed — PDPA and GDPR clearance granted

26.4  Ember (#23) — Client Design Brief Automation — Go-Live Sign-off

Ember is a P1 Phase B agent operating across the DS/CRM department, responsible for automating the client design brief process. Ember was deployed concurrently with Stone in Q3 2027, completing the three-agent Phase B cohort. As a client-facing agent handling personal data (PDPA Tier 2), Ember's deployment required the most extensive Compliance Officer review of the three agents.

Department:  DS/CRM

Priority:  P1

Go-Live Date:  Q3 2027 (target: July–August 2027)

Go/No-Go Outcome:  GO — all PRE-01 through PRE-05 verified; all TEC-E-01 through TEC-E-06 completed; Ethics review (S20) passed

PDPA Clearance:  Compliance Officer confirmed client personal data (Tier 2) handling compliant; consent capture workflow reviewed and approved; data retention policy aligned with Section 19 Tier 2 protocols; clearance granted

UAT Outcome:  DS/CRM Group Lead UAT completed; sign-off received; zero critical defects; one P-LOW enhancement note (brief template formatting for non-standard project types) logged as a backlog item for Q4 2027 review

Integration Test Result:  Interoperability with Signal (#2), Aria (#7), Hana (#13), and all 23 live agents verified; brief-to-quote pipeline end-to-end tested; client data handoff latency within Group B SLA thresholds

AI Ethics Review (S20):  Ember's brief generation outputs reviewed for design preference bias; no systematic bias identified; HITL review threshold confirmed for non-standard client requests

Outstanding Conditional Items:  One P-LOW backlog item (brief template formatting) — owner: Systems Lead; target resolution: Q4 2027

30-Day Stabilisation Period:  Commenced Q3 2027 upon Go-Live; monitored by Ops Agent Lead; SLA Group assignment: Group B (Accuracy ≥93%, Uptime ≥98.5%, Escalation ≤7%)

Systems Lead Sign-off:  Confirmed — integration testing complete

Studio Director Sign-off:  Confirmed — operational deployment approved

Compliance Officer Sign-off:  Confirmed — PDPA Tier 2 and Ethics clearance granted

26.5  Phase B Completion Declaration

With the successful Go-Live and 30-day stabilisation of all three Phase B agents (Vega #21, Stone #22, Ember #23), the MONOLITH / DAPH Decor AI Agent Programme formally declares Phase B complete. This declaration is ratified by the Steering Committee at the Q3 2027 Quarterly Programme Review (or Extraordinary Session).

Phase B Completion Date:  Q3 2027 (upon completion of all 30-day stabilisation periods)

Total Live Agents Post-Phase B:  23 (Kelly through Ember)

Phase B Stabilisation Outcomes:  All three agents completed their 30-day stabilisation period within SLA targets; no P-CRIT or P-HIGH incidents recorded during stabilisation; stabilisation report submitted to Steering Committee by Ops Agent Lead

Steering Committee Ratification:  Phase B Completion Declaration ratified at Q3 2027 Quarterly Programme Review; all five SC voting members present

Phase C Assessment Trigger:  Phase B stability confirmed — Phase C conditional assessment for Pulse (#24) and Shore (#25) is now active per AMD-001 Decision 4; full Phase C Go/No-Go to be conducted at Q3/Q4 2027 Extraordinary Session or Q4 2027 Quarterly Programme Review

Live Agent Roster Update:  Master agent roster updated: Vega (#21), Stone (#22), Ember (#23) transitioned from Planned to Live status; total live-agent count: 23

Next Programme Review:  Q4 2027 Quarterly Programme Review — Phase C scope confirmation

Annual Governance Review:  Q1 2028 — per Section 24.5 Amendment Record

27. Phase C Deployment Assessment — Pulse & Shore

27.1  Overview

This section records the Phase C Deployment Assessment for the two remaining v3.0 agents: Pulse (#24 — Real-Time KPI Dashboard AI) and Shore (#25 — Post-Installation Support AI). Phase C was conditionally authorised under AMD-001 Decision 4 (Section 24.3), subject to confirmation of Phase B stability. With Phase B declared complete and all three Phase B agents (Vega, Stone, Ember) passing their 30-day stabilisation periods (Section 26.5), the Phase C conditional assessment trigger has been activated.

Phase C Agents:  Pulse (#24 — Real-Time KPI Dashboard AI · OPS/GM · P2) and Shore (#25 — Post-Installation Support AI · SITE/CRM · P2)

Conditional Trigger:  Phase B stability confirmed — Section 26.5 Phase B Completion Declaration

Assessment Authority:  Steering Committee — Q4 2027 Quarterly Programme Review or Extraordinary Session

Target Deployment Window:  Q3–Q4 2027 (per original v3.0 roadmap)

Checklist Owner:  Systems Lead

Sign-off Authority:  Studio Director (operational) · Compliance Officer (regulatory) · SC ratification

Post-Phase C Live Agent Count:  25 total (23 existing + Pulse #24, Shore #25)

27.2  Phase C Readiness Assessment Criteria

Prior to initiating per-agent deployment readiness checks, the following programme-level Phase C assessment criteria must be evaluated and confirmed by the Steering Committee:

C-ASSESS-01 — Phase B Stability Confirmation:  All three Phase B agents (Vega, Stone, Ember) have completed their 30-day stabilisation periods with no P-HIGH or P-CRIT incidents. Confirmed per Section 26.5. STATUS: SATISFIED.

C-ASSESS-02 — Live Agent Ecosystem Health:  All 23 current live agents are SLA-compliant at time of Phase C assessment. Systems Lead to provide current SLA dashboard snapshot to Steering Committee at Q4 2027 Quarterly Programme Review.

C-ASSESS-03 — Budget Envelope:  Phase B budget (฿800,000) utilisation reviewed; residual envelope or supplementary Phase C allocation confirmed by Studio Director. Phase C agents are P2 and may require reduced deployment investment relative to Phase B.

C-ASSESS-04 — PDPA Register Currency:  Compliance Officer confirms Data Classification Tier 1–4 Register is current and covers Pulse (OPS/GM data flows) and Shore (SITE/CRM, client post-installation data — Tier 2).

C-ASSESS-05 — Section 6 Onboarding Protocol Applicability:  Systems Lead confirms Section 6 Agent Onboarding Protocol applies to Phase C agents without modification, or tables any required updates for SC approval.

27.3  Pulse (#24) — Real-Time KPI Dashboard AI — Deployment Assessment

Pulse is a P2 Phase C agent operating across the OPS/GM department. Its primary function is to provide real-time KPI dashboarding and performance intelligence across the full 25-agent programme. Pulse's deployment was deferred to Phase C due to its dependency on a stable, full Phase B agent ecosystem — it aggregates data signals from all live agents and requires Vega, Stone, and Ember to be operational before meaningful programme-wide KPI tracking can be established.

Department:  OPS/GM

Priority:  P2

Target Go-Live:  Q3–Q4 2027

Key Dependencies:  All 23 Phase B live agents operational; OPS/GM data pipeline confirmed; SLA Group assignment determined by Systems Lead in consultation with Studio Director

Technical Readiness Checks (TEC-P):  TEC-P-01: KPI data model validated against all 23 live-agent output schemas. TEC-P-02: Real-time data ingestion pipeline tested at peak load (all 23 agents concurrent). TEC-P-03: Dashboard rendering and alert threshold configuration validated with OPS/GM Group Lead. TEC-P-04: PDPA Tier mapping confirmed for OPS/GM aggregated data streams. TEC-P-05: HITL escalation configured for anomalous KPI patterns — threshold review by Systems Lead. TEC-P-06: Audit logging active; outputs recorded in S22 Continuous Improvement Audit trail. TEC-P-07: UAT completed with OPS/GM Group Lead and Studio Director — sign-off received.

Go/No-Go Criteria:  All C-ASSESS-01 through C-ASSESS-05 satisfied; all TEC-P-01 through TEC-P-07 complete; no P-HIGH or P-CRIT findings; PDPA clearance granted; UAT sign-off from OPS/GM Group Lead

Proposed SLA Group:  Group C (Accuracy ≥94%, Uptime ≥99.0%, Escalation ≤6%) — subject to SC confirmation

Stabilisation Period:  30 days post Go-Live, monitored by Ops Agent Lead

27.4  Shore (#25) — Post-Installation Support AI — Deployment Assessment

Shore is a P2 Phase C agent operating across the SITE/CRM departments. Its primary function is to manage post-installation client support workflows, including follow-up scheduling, defect logging, client satisfaction capture, and escalation to SITE or CRM teams. Shore's deployment was deferred to Phase C due to its dependency on Ember (#23, DS/CRM) being live — Shore picks up the client relationship where Ember's design brief automation ends, completing the end-to-end client journey pipeline.

Department:  SITE/CRM

Priority:  P2

Target Go-Live:  Q3–Q4 2027

Key Dependencies:  Ember (#23) live and stable; Vega (#21) live (SITE coordination); CRM client data pipeline from Signal (#2) and Aria (#7) confirmed; SITE/CRM data sharing agreement reviewed by Compliance Officer

Technical Readiness Checks (TEC-SH):  TEC-SH-01: Post-installation workflow templates loaded and validated against DAPH service standards. TEC-SH-02: Integration with Ember (#23), Vega (#21), Signal (#2), Aria (#7), Hana (#13) tested — end-to-end client journey verified. TEC-SH-03: PDPA Tier 2 client data handling validated — post-installation data retention policy compliant with Section 19. TEC-SH-04: Client satisfaction survey and defect logging workflows integrated with SITE and CRM systems. TEC-SH-05: Escalation pathway to SITE team and Vega (#21) for post-installation defects configured and tested. TEC-SH-06: Audit logging active; Shore outputs recorded in S22 Continuous Improvement Audit trail. TEC-SH-07: UAT completed with SITE/CRM Group Lead — sign-off received.

Go/No-Go Criteria:  All C-ASSESS-01 through C-ASSESS-05 satisfied; all TEC-SH-01 through TEC-SH-07 complete; no P-HIGH or P-CRIT findings; PDPA Tier 2 clearance granted; UAT sign-off from SITE/CRM Group Lead

Proposed SLA Group:  Group B (Accuracy ≥93%, Uptime ≥98.5%, Escalation ≤7%) — subject to SC confirmation

Stabilisation Period:  30 days post Go-Live, monitored by Ops Agent Lead

27.5  Steering Committee Go/No-Go Decision

The Phase C Go/No-Go decision is made by the full Steering Committee at the Q4 2027 Quarterly Programme Review (or an Extraordinary Session convened for this purpose). The decision covers both Pulse and Shore and may be made jointly or sequentially per agent depending on readiness status.

Joint GO (Pulse and Shore):  All C-ASSESS criteria satisfied; all TEC checks for both agents complete; no outstanding P-HIGH or P-CRIT findings; PDPA clearances granted; UAT sign-offs received from OPS/GM and SITE/CRM Group Leads. Both agents may proceed to deployment concurrently or in sequence.

Sequential GO:  One agent satisfies all criteria and is approved; the other has a Conditional Go or is deferred. The ready agent proceeds to Go-Live while the other remains in assessment. Deferred agent's Go/No-Go to be revisited at the next Quarterly Programme Review.

DEFER / NO-GO:  Phase C deployment is suspended for the affected agent pending resolution of outstanding findings. Steering Committee sets a target resolution date and reconvenes for a Go/No-Go re-assessment.

Decision Owner:  Full Steering Committee vote — minimum quorum: Chair + Studio Director + Systems Lead

Decision Documentation:  Formal Go/No-Go outcome documented as a Section 28 amendment or addendum to this section, with per-agent sign-off records mirroring the Section 26 format

27.6  Phase C Deployment Schedule

The following milestone schedule applies to Phase C deployment, contingent on SC Go/No-Go approval:

PC-M1 — Q4 2027 (October):  SC Phase C Go/No-Go decision at Q4 2027 Quarterly Programme Review; C-ASSESS-01 through C-ASSESS-05 verified; TEC checks for Pulse and Shore initiated.

PC-M2 — Q4 2027 (October–November):  TEC checks completed for both agents; UAT with OPS/GM and SITE/CRM Group Leads; Compliance Officer PDPA clearances for both agents.

PC-M3 — Q4 2027 (November–December):  Pulse Go-Live (if GO); Shore Go-Live (if GO); Phase C begins 30-day stabilisation monitoring.

PC-M4 — Q4 2027 / Q1 2028:  30-day stabilisation periods completed; SLA performance tracked; Ops Agent Lead submits Phase C stabilisation report to Steering Committee.

PC-M5 — Q1 2028:  Annual Governance Review (per Section 24.5) — Phase C outcomes reviewed; full 25-agent programme performance assessed; AMD-002 considered if additional amendments are required.

27.7  Post-Phase C Programme State

Upon successful completion of Phase C, the MONOLITH / DAPH Decor AI Agent Programme will have reached its full v3.0 deployment scope:

Total Live Agents:  25 (Kelly #1 through Shore #25)

SLA Group Distribution:  Group A: Kelly, Signal, Aria, Blaze, Nova (5 agents). Group B: Compass, Remy, Scout, Finn, Hana, Shore (6 agents). Group C: Atlas, Bo, Forge, Leo, Ops, Stone, Pulse (7 agents). Group D: Core, Nexus, Rex, Guardian, Talent, Vega (6 agents). Ember assigned to Group B. Final group assignments subject to SC confirmation.

Departments Covered:  All 13 DAPH departments covered by at least one AI agent (DS, CRM, OPS, GM, SITE, QA, PRO, HR, FIN, IT, MKT, PROC, PM)

Next Programme Milestone:  Q1 2028 Annual Governance Review — review of full 25-agent programme performance; FY 2028 budget; consideration of AMD-002 if required

Programme Completion Status:  v3.0 roadmap complete upon Phase C Go-Live sign-off. Any future agents or programme expansions require a new planning document and Steering Committee ratification as a new amendment (AMD-002 or later).

28. Q1 2028 Annual Programme Review & AMD-002 Scope

28.1  Overview

This section records the Q1 2028 Annual Programme Review (APR-2028), the first full-programme review following Phase C completion and the activation of all 25 AI agents across 13 DAPH departments. The review also defines the scope of Amendment Document AMD-002, which governs programme evolution beyond the v3.0 deployment baseline.

Review Period:  1 January 2028 – 31 March 2028 (Q1 2028)

Review Authority:  Steering Committee (SC) — 5 voting members per S23 Charter

Trigger:  PC-M5 milestone completion per Section 27.6 — mandatory annual review of full 25-agent programme performance

Amendment Reference:  AMD-002 — Programme Evolution & Expansion Scope (successor to AMD-001)

28.2  Full Programme Performance Assessment

The APR-2028 assessment covers all 25 live agents across four SLA Groups. Performance is measured against thresholds established in Section 17 and updated by AMD-001 decisions.

Group A (5 agents — Kelly, Signal, Aria, Blaze, Nova):  Accuracy ≥95%, Completion ≥92%, Uptime ≥99.0%, Escalation ≤5%. Q1 2028 assessment: all Group A agents in sustained compliance. No performance remediation required.

Group B (6 agents — Compass, Remy, Scout, Finn, Hana, Shore):  Accuracy ≥93%, Completion ≥90%, Uptime ≥98.5%, Escalation ≤7%. Shore (#25) completes 90-day stabilisation period (PC-M4) in Q1 2028. Ember Group B final assignment confirmed by SC at APR-2028.

Group C (7 agents — Atlas, Bo, Forge, Leo, Ops, Stone, Pulse):  Accuracy ≥94%, Completion ≥91%, Uptime ≥99.0%, Escalation ≤6%. Pulse (#24) completes 90-day stabilisation in Q1 2028. Stone continuous improvement review: P-LOW backlog cleared.

Group D (6 agents — Core, Nexus, Rex, Guardian, Talent, Vega):  Accuracy ≥97%, Completion ≥95%, Uptime ≥99.5%, Escalation ≤4%. Highest-criticality group; Q1 2028 results confirm Vega (#21) sustained Group D compliance post Phase B go-live.

Overall programme uptime across all 25 agents for Q1 2028: target ≥98.5% weighted average. SC reviews aggregate KPI dashboard (Pulse output) as primary evidence for APR-2028 conclusions.

28.3  AMD-002 Scope Definition

AMD-002 is the formal amendment document authorising programme evolution activities beyond the v3.0 deployment baseline. The SC ratifies AMD-002 scope at the APR-2028 session. AMD-002 may encompass the following workstreams:

AMD-002-WS1 — Agent Capability Enhancement:  Upgrade and retrain existing agents based on 12-month operational data. Scope includes model version updates, prompt engineering improvements, and tool integration expansions for any of the 25 live agents.

AMD-002-WS2 — New Agent Commissioning (v4.0 Pipeline):  Evaluate and commission additional AI agents beyond Shore (#25) to address coverage gaps identified in APR-2028. Candidate departments: PROC, PM, FIN for deeper AI integration. New agents follow established Phase D framework.

AMD-002-WS3 — Infrastructure Scaling:  Review infrastructure capacity against 25-agent load. Authorise scaling investments if uptime or latency thresholds are at risk. Budget envelope subject to SC approval.

AMD-002-WS4 — Governance & Compliance Refresh:  Update SOP sections (S17–S22) to reflect 25-agent operational experience. Incorporate updated PDPA/GDPR guidance, AI regulation developments, and lessons learned from Phase B and Phase C deployments.

AMD-002-WS5 — Cross-Agent Orchestration Expansion:  Extend orchestration protocols (S16) to include Phase C agents. Define Pulse as real-time orchestration visibility layer for all 25 agents. Review Shore–Ember dependency chain and formalise as permanent integration standard.

AMD-002 is not limited to the workstreams above. The SC may ratify additional scope items raised during APR-2028. All AMD-002 decisions are logged in the Steering Committee decision register and assigned owners with Q3 2028 target delivery.

28.4  APR-2028 Key Findings & Recommendations

The following findings and SC recommendations are recorded as outputs of the Q1 2028 Annual Programme Review:

Finding F-2028-01:  All 25 agents are live and operating within SLA thresholds. Phase C deployment (Pulse & Shore) completed without P-CRIT incidents. Recommendation: Declare programme fully operational at v3.0 baseline.

Finding F-2028-02:  Pulse KPI dashboard provides real-time visibility across all 13 departments, reducing manual reporting effort by an estimated 40%. Recommendation: Formalise Pulse as primary programme performance reporting tool.

Finding F-2028-03:  Shore post-installation support resolution rate exceeds baseline target within stabilisation period. Ember–Shore integration operating as designed. Recommendation: Promote Shore to full Group B standing effective Q2 2028.

Finding F-2028-04:  Three agents (Atlas, Bo, Forge — Group C) show Completion metric within 1% of threshold. No SLA breach recorded, but proactive improvement recommended. Recommendation: SC assigns improvement plan under AMD-002-WS1 by Q2 2028.

Finding F-2028-05:  PDPA/GDPR audit (S19 compliance check) confirms all 25 agents compliant with data retention and processing standards as of Q1 2028. Recommendation: Schedule next compliance audit for Q1 2029 under AMD-002-WS4.

28.5  APR-2028 SC Decisions

The Steering Committee records the following formal decisions at the APR-2028 session:

Decision SC-2028-01:  v3.0 programme declared fully operational. All 25 agents active across 13 departments. AMD-001 scope formally closed.

Decision SC-2028-02:  AMD-002 ratified with all five workstreams (WS1–WS5) authorised for planning. WS1 and WS4 designated P0 priority. WS2, WS3, WS5 designated P1.

Decision SC-2028-03:  Pulse formalised as programme-wide KPI reporting tool effective Q2 2028. Monthly KPI dashboard reports to SC replacing manual summary process.

Decision SC-2028-04:  Shore promoted to full Group B SLA standing effective Q2 2028. Group B revised to 7 agents: Compass, Remy, Scout, Finn, Hana, Ember, Shore.

Decision SC-2028-05:  Next Annual Programme Review scheduled for Q1 2029. AMD-002 interim progress review at Q3 2028 SC meeting.

28.6  Programme Milestones — Post APR-2028

The following milestones govern programme activity following the Q1 2028 Annual Programme Review and AMD-002 ratification:

APR-M1 (Q2 2028):  AMD-002-WS1 improvement plans submitted for Atlas, Bo, Forge. Pulse formalised as reporting tool; first monthly KPI report published.

APR-M2 (Q2 2028):  Shore Group B promotion effective. Group B revised to 7 agents. SLA thresholds updated in S17 amendment under AMD-002-WS4.

APR-M3 (Q3 2028):  AMD-002 interim progress review. WS2 candidate agent shortlist presented to SC. WS3 infrastructure scaling assessment completed.

APR-M4 (Q3 2028):  AMD-002-WS5 orchestration expansion design approved. Pulse integration with all 25 agents verified.

APR-M5 (Q1 2029):  Next Annual Programme Review (APR-2029). AMD-002 WS1–WS5 progress assessed. v4.0 new agent commissioning decision expected.

28.7  Amendment Record — AMD-002

This section serves as the formal amendment record for AMD-002.

Amendment ID:  AMD-002

Title:  Programme Evolution & Expansion Scope

Ratified:  Q1 2028 Annual Programme Review (APR-2028)

Authority:  Steering Committee — unanimous vote, 5/5 voting members

Predecessor:  AMD-001 (Q1 2027 Annual Governance Review — formally closed SC-2028-01)

Workstreams:  WS1 Capability Enhancement (P0) · WS2 New Agent Commissioning (P1) · WS3 Infrastructure Scaling (P1) · WS4 Governance Refresh (P0) · WS5 Orchestration Expansion (P1)

Target Delivery:  Q1 2029 (full WS review at APR-2029)

Owner:  Programme Director, DAPH Decor — with SC oversight

Status:  ACTIVE — AMD-002 ratified Q1 2028

AMD-002 supersedes AMD-001 as the governing amendment framework for the MONOLITH / DAPH Decor AI Agent Programme. All subsequent amendments will reference AMD-002 as the baseline document.

29. AMD-002-WS2 — Phase D New Agent Commissioning Framework

29.1  Overview

This section defines the Phase D New Agent Commissioning Framework, authorised under AMD-002 Workstream 2 (WS2) at the Q1 2028 Annual Programme Review. Phase D governs the design, assessment, development, and go-live of AI agents beyond the v3.0 baseline (agents #26 and above), extending the programme into departments with identified automation opportunities not addressed by the existing 25-agent deployment.

Authority:  AMD-002-WS2 ratified by SC at APR-2028 (SC-2028-02). WS2 priority: P1.

Candidate Departments:  FIN (Finance), PM (Project Management), PROC (Procurement) — identified at APR-2028 as highest-priority automation opportunities.

Candidate Agents (shortlist):  Ledger (#26) — FIN/GM · Frame (#27) — PM/OPS · Draft (#28) — PROC/FIN. All names and assignments subject to SC confirmation at Q3 2028 interim review.

Phase D Timeline:  Planning Q2–Q3 2028 · SC approval Q3 2028 · Go-live Q3 2028 – Q1 2029 (staggered per priority) · Full Phase D review at APR-2029.

29.2  Phase D Commissioning Framework

All Phase D agents must satisfy five commissioning criteria (PD-CRIT-01 through PD-CRIT-05) before SC approval is granted for development and go-live. These criteria extend the Phase A/B/C assessment model to reflect the matured programme governance established through Sections 17–27.

PD-CRIT-01 — Business Case Validation:  A documented business case, including ROI estimate, department use-case description, and alignment with AMD-002 objectives, must be validated by the Programme Director and approved by SC. Minimum threshold: quantifiable efficiency gain ≥15% vs. current manual process.

PD-CRIT-02 — Department Head Sponsorship:  The head of the target department must formally sponsor the candidate agent, confirming readiness to support change management, training, and data access requirements. Sponsorship letter lodged with SC secretariat.

PD-CRIT-03 — Technical Integration Assessment:  A full technical integration assessment (TIA) covering system connectivity, data pipelines, API availability, and dependency mapping must be completed before development commences. TIA reviewed by IT and the Programme Director.

PD-CRIT-04 — Training & Change Management Plan:  A training plan covering affected staff, a change management communication schedule, and a user-acceptance-testing (UAT) protocol must be approved by SC before go-live authorisation is granted.

PD-CRIT-05 — Budget Allocation Confirmation:  Budget for development, infrastructure, and first-year operation must be confirmed from the AMD-002 programme envelope and signed off by the Finance Director. No development may commence without confirmed budget.

Phase D agents also inherit all compliance requirements from Section 19 (Data Privacy & AI Compliance) and Section 20 (AI Ethics & Responsible Use Policy). SLA Group assignment follows the methodology in Section 17, with Group confirmed by SC at go-live sign-off.

29.3  Candidate Agent Shortlist

The following three candidate agents were presented to the SC at APR-2028 as the Phase D priority shortlist. The SC directed that full PD-CRIT assessments be completed and submitted at the Q3 2028 interim review.

Ledger (#26):  Financial Analysis & Reporting AI · Department: FIN/GM · Priority: P0 · Function: Automated financial reporting, budget variance analysis, cost forecasting, and FIN-to-GM KPI feeds. Key integrations: Pulse (KPI pipeline), Core (compliance), FIN system. Proposed SLA Group: D (high accuracy required). Target go-live: Q3 2028.

Frame (#27):  Project Management AI · Department: PM/OPS · Priority: P0 · Function: Project timeline tracking, resource allocation optimisation, milestone reporting, and PM-to-OPS handoff automation. Key integrations: Ops, Pulse (KPI), PM system. Proposed SLA Group: C. Target go-live: Q4 2028.

Draft (#28):  Procurement Automation AI · Department: PROC/FIN · Priority: P1 · Function: Procurement workflow automation, vendor management, purchase-order processing, and PROC-to-FIN reconciliation. Key integrations: Ledger (FIN feeds), vendor portals, PROC system. Proposed SLA Group: B (dependency on Ledger operational). Target go-live: Q1 2029.

29.4  Candidate Assessment — Ledger (#26)

Ledger is the highest-priority Phase D candidate, classified P0 due to direct impact on financial reporting accuracy across 13 departments. The FIN and GM department heads have provided formal sponsorship.

PD-CRIT-01 (Business Case):  ROI estimated at 28% efficiency gain on monthly financial close process. Business case approved by Programme Director. STATUS: PASS.

PD-CRIT-02 (Sponsorship):  FIN Director and GM Head confirmed as co-sponsors. Sponsorship letters lodged Q1 2028. STATUS: PASS.

PD-CRIT-03 (Technical Integration):  TIA in progress; FIN system API connectivity confirmed. Pulse data pipeline interface defined. STATUS: IN PROGRESS — Q2 2028.

PD-CRIT-04 (Training Plan):  Finance team training plan draft submitted; UAT protocol under review. STATUS: CONDITIONAL — finalise by Q3 2028.

PD-CRIT-05 (Budget):  AMD-002 budget envelope allocation confirmed by Finance Director. Development budget approved. STATUS: PASS.

Overall Assessment:  CONDITIONAL GO — PD-CRIT-03 and PD-CRIT-04 to be resolved by Q3 2028 interim review. Development may begin on non-integration components.

29.5  Candidate Assessment — Frame (#27)

Frame addresses the PM department's need for automated project timeline management and resource optimisation. Priority P0 reflects the strategic importance of PM–OPS coordination across DAPH construction and installation projects.

PD-CRIT-01 (Business Case):  ROI estimated at 22% reduction in project overrun rate. Business case validated. STATUS: PASS.

PD-CRIT-02 (Sponsorship):  PM Head confirmed as sponsor; OPS Head as secondary sponsor. Formal letters lodged Q1 2028. STATUS: PASS.

PD-CRIT-03 (Technical Integration):  PM system API assessment pending vendor confirmation. Ops integration pathway defined. STATUS: IN PROGRESS — Q2 2028.

PD-CRIT-04 (Training Plan):  Not yet submitted. PM team change management assessment scheduled Q2 2028. STATUS: PENDING.

PD-CRIT-05 (Budget):  Budget allocation confirmed within AMD-002 envelope. STATUS: PASS.

Overall Assessment:  PENDING — PD-CRIT-03 and PD-CRIT-04 outstanding. Full submission expected at Q3 2028 interim review. Target go-live Q4 2028 remains achievable.

29.6  Candidate Assessment — Draft (#28)

Draft automates the PROC department's procurement lifecycle, reducing manual processing time and vendor management overhead. Priority P1 reflects dependency on Ledger (#26) becoming operational before Draft can deliver full FIN reconciliation.

PD-CRIT-01 (Business Case):  ROI estimated at 35% reduction in procurement cycle time. Business case approved. STATUS: PASS.

PD-CRIT-02 (Sponsorship):  PROC Head confirmed as sponsor; FIN Director as secondary. Dependency on Ledger noted in sponsorship letter. STATUS: PASS.

PD-CRIT-03 (Technical Integration):  Vendor portal API compatibility assessment in progress. Ledger integration pathway cannot be finalised until Ledger is operational. STATUS: BLOCKED pending Ledger go-live.

PD-CRIT-04 (Training Plan):  Not yet submitted. Scheduled Q4 2028 after Ledger go-live confirmed. STATUS: PENDING.

PD-CRIT-05 (Budget):  Budget allocation confirmed. STATUS: PASS.

Overall Assessment:  DEFER pending Ledger go-live. Full PD-CRIT submission at Q4 2028 SC review. Target go-live Q1 2029 subject to Ledger operational by Q3 2028.

29.7  SC Decision & Phase D Milestones

The Steering Committee will make formal Phase D go/no-go decisions at the Q3 2028 interim AMD-002 review (APR-M3) based on completed PD-CRIT submissions. The following milestone schedule governs Phase D execution:

PD-M1 (Q2 2028):  Ledger PD-CRIT-03 and PD-CRIT-04 completed. Frame PD-CRIT-03 vendor confirmation received. Full shortlist documentation submitted to SC secretariat.

PD-M2 (Q3 2028):  Q3 2028 AMD-002 interim review — SC formal go/no-go for Ledger and Frame. Draft assessment status reviewed; blocked dependency noted. Ledger development authorised on SC approval.

PD-M3 (Q3 2028):  Ledger development and integration testing commences. Frame training and change management plan finalised. Infrastructure scaling (WS3) assessment completed.

PD-M4 (Q4 2028):  Ledger go-live (target Q3 2028 — confirm at PD-M3 review). Frame development commences; Draft PD-CRIT-03 unblocked. Frame UAT completed; Frame go-live Q4 2028.

PD-M5 (Q1 2029):  Draft go-live (Q1 2029, subject to PD-CRIT-03 resolution). All Phase D agents (#26 Ledger, #27 Frame, #28 Draft) operational — programme expanded to 28 agents if all three commissioned. Full Phase D performance review at APR-2029.

Phase D milestone outcomes are reported to the SC at each milestone gate. Any PD-CRIT failure or budget overrun triggers an immediate SC escalation per the Incident Response protocol in Section 18. Phase D go-live sign-off records will be documented in a future section following the pattern established in Section 26 (Phase B Go-Live Sign-off Records).

30. Phase D Go-Live Sign-off Records — Ledger and Frame

30.1  Overview

This section records the formal go-live sign-off for Ledger (#26) and Frame (#27), the two P0-priority Phase D agents authorised under AMD-002-WS2. Sign-off records follow the framework established in Section 26 (Phase B Go-Live Sign-off Records), applying the Phase D commissioning criteria (PD-CRIT-01 through PD-CRIT-05) as the qualification standard. Each agent underwent a six-check technical evaluation (TEC) prior to SC approval for go-live.

Authority:  SC decisions SC-2028-05 (Ledger, Q3 2028) and SC-2028-06 (Frame, Q4 2028). Both decisions recorded by SC secretariat and Programme Director.

Scope:  This section covers Ledger and Frame only. Draft (#28) commissioning and go-live will be recorded in a subsequent section following PD-CRIT-03 resolution and Q1 2029 go-live.

Post-Go-Live State:  Following Ledger and Frame go-live, the programme expanded to 27 live agents. Draft (#28) status is reported in Section 30.5 below.

30.2  Go-Live Sign-off — Ledger (#26) Financial Analysis & Reporting AI

Ledger (#26) achieved conditional go authorisation at the Q3 2028 AMD-002 interim review following resolution of PD-CRIT-03 (TIA completed) and PD-CRIT-04 (training plan finalised). The SC issued SC-2028-05 authorising Ledger go-live, effective Q3 2028.

Department:  FIN / GM  ·  SLA Group: D (Accuracy ≥97%, Completion ≥95%, Uptime ≥99.5%, Escalation ≤4%)

Go-Live Date:  Q3 2028  ·  Agent #26  ·  Priority P0

Technical Evaluation Checklist — Ledger (TEC-L):

TEC-L-01 — FIN System Integration:  FIN system API connectivity verified end-to-end. Budget variance and financial close data pipelines tested. PASS.

TEC-L-02 — Pulse KPI Pipeline Interface:  Ledger-to-Pulse KPI feed verified. FIN KPI data flowing to Pulse dashboard. PASS.

TEC-L-03 — Core Compliance Integration:  Core agent compliance review integration confirmed. Financial reporting outputs subject to Core compliance check. PASS.

TEC-L-04 — GM Reporting Output:  GM-facing financial report templates generated and validated by GM Head. Formatting and data accuracy confirmed. PASS.

TEC-L-05 — UAT Completion:  Finance team user acceptance testing completed over 3-week period. 12 test scenarios executed, 12 PASS. No critical defects raised. PASS.

TEC-L-06 — SLA Group D Readiness:  SLA Group D threshold monitoring configured in Pulse dashboard. Incident escalation routing confirmed per Section 18. PASS.

PD-CRIT Final Status:  PD-CRIT-01 PASS · PD-CRIT-02 PASS · PD-CRIT-03 PASS (TIA completed Q3 2028) · PD-CRIT-04 PASS (training plan finalised Q3 2028) · PD-CRIT-05 PASS.

SC Decision:  SC-2028-05 — Ledger go-live approved. SLA Group D confirmed. Programme Director and FIN Director co-signatories on sign-off record.

30-Day Post-Go-Live Review:  Scheduled Q4 2028. SLA Group D performance monitoring active from day one. No critical incidents recorded in first 30 days.

30.3  Go-Live Sign-off — Frame (#27) Project Management AI

Frame (#27) completed all PD-CRIT requirements following vendor confirmation of PM system API compatibility (Q3 2028) and training plan approval. The SC issued SC-2028-06 authorising Frame go-live, effective Q4 2028.

Department:  PM / OPS  ·  SLA Group: C (Accuracy ≥94%, Completion ≥91%, Uptime ≥99.0%, Escalation ≤6%)

Go-Live Date:  Q4 2028  ·  Agent #27  ·  Priority P0

Technical Evaluation Checklist — Frame (TEC-F):

TEC-F-01 — PM System Integration:  PM system API integration completed following vendor confirmation Q3 2028. Project timeline and resource data pipelines tested. PASS.

TEC-F-02 — Ops Integration:  Frame-to-Ops handoff automation verified. PM milestone triggers Ops workflow transition confirmed. PASS.

TEC-F-03 — Pulse KPI Feed:  Frame project KPI data flowing to Pulse dashboard. PM KPI metrics validated by OPS Head. PASS.

TEC-F-04 — Milestone Reporting Output:  SC milestone reporting template generated and validated. PM Head confirmed report accuracy and format. PASS.

TEC-F-05 — UAT Completion:  PM and OPS team UAT completed over 2-week period. 10 test scenarios executed, 10 PASS. 1 P-LOW backlog item (resource allocation display formatting) accepted for post-go-live resolution by Q1 2029. CONDITIONAL PASS.

TEC-F-06 — SLA Group C Readiness:  SLA Group C monitoring configured. Escalation routing per Section 18 confirmed. PASS.

PD-CRIT Final Status:  PD-CRIT-01 PASS · PD-CRIT-02 PASS · PD-CRIT-03 PASS (PM API confirmed Q3 2028) · PD-CRIT-04 PASS (training plan approved Q3 2028) · PD-CRIT-05 PASS.

SC Decision:  SC-2028-06 — Frame go-live approved. SLA Group C confirmed. P-LOW TEC-F-05 backlog item logged and tracked. Programme Director and PM Head co-signatories on sign-off record.

30-Day Post-Go-Live Review:  Scheduled Q1 2029. TEC-F-05 P-LOW backlog item resolution confirmed by end of Q4 2028.

30.4  Phase D Partial Completion Declaration

With Ledger (#26) and Frame (#27) successfully deployed, the programme formally declares Phase D Partial Completion as of Q4 2028. 27 AI agents are now live across the DAPH AI Agent Programme.

Live Agent Count:  27 agents  ·  (20 v2.5 + 5 v3.0 + Ledger + Frame)

Departments Covered:  13 departments with AI agent coverage. FIN and PM departments newly covered through Phase D. Procurement (PROC) pending Draft go-live.

Phase D Status:  PARTIAL COMPLETION — Ledger LIVE (Group D) · Frame LIVE (Group C) · Draft PENDING Q1 2029.

Remaining Phase D Work:  Draft (#28) commissioning and go-live (Q1 2029, subject to PD-CRIT-03 resolution). Full Phase D completion at APR-2029 review.

SC Notification:  Phase D Partial Completion declaration lodged with SC secretariat and included in Q4 2028 Programme Director report.

30.5  Draft (#28) Procurement Automation AI — Status Update

With Ledger (#26) now operational, the primary blocking dependency for Draft (#28) — PD-CRIT-03 Ledger integration pathway — is unblocked. Draft commissioning re-enters active assessment as of Q4 2028.

PD-CRIT-03 Update:  Ledger go-live (Q3 2028) unblocks Draft's FIN reconciliation integration. PROC system vendor portal API assessment resumed Q4 2028. STATUS: IN PROGRESS (was BLOCKED).

PD-CRIT-04 Update:  PROC team training plan and UAT protocol scheduled for Q4 2028 following PD-CRIT-03 resolution. STATUS: IN PROGRESS.

Target Go-Live:  Q1 2029  ·  On track subject to PD-CRIT-03 and PD-CRIT-04 completion.

SC Review:  Draft full PD-CRIT submission to SC at Q4 2028 interim review for formal go/no-go decision. Programme Director confirmed Q1 2029 timeline remains achievable.

Next Section:  Draft go-live sign-off will be recorded in a subsequent section following Q1 2029 commissioning, completing Phase D.

31. Draft (#28) Go-Live Sign-off & Phase D Full Completion Declaration

31.1  Overview

This section records the formal go-live sign-off for Draft (#28), the final Phase D agent under AMD-002-WS2. Draft's commissioning was deferred in Section 29 pending Ledger (#26) becoming operational; with Ledger live as of Q3 2028, the PD-CRIT-03 blocking dependency was resolved and Draft's assessment resumed in Q4 2028. Draft successfully completed all five PD-CRIT criteria and the six-check technical evaluation (TEC-D), receiving SC go-live authorisation effective Q1 2029.

Authority:  SC decision SC-2029-01 (Q1 2029). Recorded by SC secretariat and Programme Director.

Phase D Completion:  With Draft operational, all three Phase D agents are live: Ledger (#26), Frame (#27), Draft (#28). The programme expands to 28 active AI agents. Phase D Full Completion is declared in Section 31.3.

AMD-002-WS2 Status:  All New Agent Commissioning workstream objectives fully delivered. WS2 closes upon Phase D Full Completion Declaration. Full AMD-002 review at APR-2029.

31.2  Go-Live Sign-off — Draft (#28) Procurement Automation AI

Draft (#28) completed the full PD-CRIT assessment in Q4 2028 following Ledger go-live. The PROC system vendor portal API assessment and the FIN reconciliation integration were confirmed operational. The SC issued SC-2029-01 authorising Draft go-live, effective Q1 2029.

Department:  PROC / FIN  ·  SLA Group: B (Accuracy ≥93%, Completion ≥90%, Uptime ≥98.5%, Escalation ≤7%)

Go-Live Date:  Q1 2029  ·  Agent #28  ·  Priority P1

PD-CRIT Final Status — Draft:

PD-CRIT-01 (Business Case):  ROI 35% reduction in procurement cycle time. Business case approved. STATUS: PASS.

PD-CRIT-02 (Sponsorship):  PROC Head (primary) and FIN Director (secondary) confirmed. Sponsorship letters lodged Q1 2028. STATUS: PASS.

PD-CRIT-03 (Technical Integration):  Vendor portal API compatibility confirmed Q4 2028, following Ledger go-live (Q3 2028) unblocking the FIN reconciliation pathway. PROC-to-FIN Ledger integration verified. STATUS: PASS.

PD-CRIT-04 (Training Plan):  PROC team training plan completed and approved by SC Q4 2028. UAT protocol finalized. STATUS: PASS.

PD-CRIT-05 (Budget):  Budget confirmed within AMD-002 envelope. STATUS: PASS.

Technical Evaluation Checklist — Draft (TEC-D):

TEC-D-01 — PROC System Integration:  Vendor portal API integration completed Q4 2028. Procurement workflow and purchase-order processing pipelines tested end-to-end. PASS.

TEC-D-02 — Ledger FIN Reconciliation Integration:  Draft-to-Ledger FIN reconciliation feed verified operational. PROC purchase-order data flowing to Ledger FIN pipeline. PASS.

TEC-D-03 — Vendor Management Interface:  Vendor portal connectivity confirmed. Automated vendor communication workflow tested. Purchase-order issuance and acknowledgement loop validated. PASS.

TEC-D-04 — PROC-to-FIN Reconciliation Output:  End-of-period reconciliation reports generated and validated by FIN Director and PROC Head. Data accuracy confirmed against manual baseline. PASS.

TEC-D-05 — UAT Completion:  PROC and FIN team user acceptance testing completed over 3-week period in Q4 2028. 12 test scenarios executed, 12 PASS. No critical or high-priority defects raised. PASS.

TEC-D-06 — SLA Group B Readiness:  SLA Group B threshold monitoring configured in Pulse dashboard. Incident escalation routing per Section 18 confirmed. Ember and Shore integration touchpoints verified. PASS.

SC Decision:  SC-2029-01 — Draft go-live approved. SLA Group B confirmed. Programme Director, PROC Head, and FIN Director co-signatories on sign-off record.

30-Day Post-Go-Live Review:  Scheduled Q2 2029. SLA Group B performance monitoring active from day one. No critical incidents recorded in first 30 days.

31.3  Phase D Full Completion Declaration

With Draft (#28) successfully deployed in Q1 2029, the DAPH AI Agent Programme formally declares Phase D Full Completion. All three Phase D agents — Ledger, Frame, and Draft — are now operational, extending the programme to 28 live AI agents across all target departments.

Live Agent Count:  28 agents  ·  (20 v2.5 + 5 v3.0 + 3 Phase D: Ledger, Frame, Draft)

Departments Covered:  All 13 DAPH departments now have active AI agent coverage. FIN covered by Ledger (#26) · PM covered by Frame (#27) · PROC covered by Draft (#28). No department gaps remain.

Phase D Status:  FULL COMPLETION — all three Phase D agents LIVE.

AMD-002-WS2 Status:  CLOSED — New Agent Commissioning workstream fully delivered. All PD-M1 through PD-M5 milestones completed on schedule. Final WS2 closure report lodged with SC secretariat.

Declaration Signatories:  Programme Director, SC Chair, FIN Director, PM Head, PROC Head. Phase D Full Completion declaration filed with SC secretariat and included in Q1 2029 Programme Director report.

31.4  Programme State — 28-Agent Deployment

Following Phase D Full Completion, the DAPH AI Agent Programme operates at its AMD-002 target scale of 28 agents across 13 departments. All agents are classified within the SLA Group framework established in Section 17 and governed by the protocols in Sections 18–23.

SLA Group A (5 agents):  Kelly, Signal, Aria, Blaze, Nova — Accuracy ≥95%, Completion ≥92%, Uptime ≥99.0%, Escalation ≤5%.

SLA Group B (8 agents):  Compass, Remy, Scout, Finn, Hana, Ember, Shore, Draft — Accuracy ≥93%, Completion ≥90%, Uptime ≥98.5%, Escalation ≤7%.

SLA Group C (8 agents):  Atlas, Bo, Forge, Leo, Ops, Stone, Pulse, Frame — Accuracy ≥94%, Completion ≥91%, Uptime ≥99.0%, Escalation ≤6%.

SLA Group D (7 agents):  Core, Nexus, Rex, Guardian, Talent, Vega, Ledger — Accuracy ≥97%, Completion ≥95%, Uptime ≥99.5%, Escalation ≤4%.

Cross-Agent Orchestration:  All 28 agents operate under the orchestration protocols in Section 16. Ledger feeds Pulse (KPI pipeline) and Core (compliance). Frame feeds Ops (handoff automation) and Pulse (PM KPIs). Draft feeds Ledger (FIN reconciliation).

Governance:  Programme governance remains under the Steering Committee Charter (Section 23) and AMD-001/AMD-002 amendment framework. Next full governance review: APR-2029.

31.5  APR-2029 Annual Programme Review — Scope

The APR-2029 Annual Programme Review will be the first review covering the complete 28-agent programme and the conclusion of all AMD-002 workstreams. The SC will assess the full programme performance, agent lifecycle status, and determine the next phase of programme evolution.

Review Scope:  Full 28-agent SLA performance review (Groups A–D) · AMD-002 WS1–WS5 final outcomes · Phase D agent 30-day and 90-day performance reports · Section 22 continuous improvement findings · Governance and compliance audit results (S19, S20).

Potential Outcomes:  Programme consolidation at 28 agents · Phase E scoping (if new automation opportunities identified) · AMD-003 ratification for next programme cycle · Agent decommissioning assessment per Section 21 lifecycle protocol.

Deliverables:  APR-2029 Programme Director report · SC decisions recorded as SC-2029-XX series · Updated programme summary amendment if scope changes ratified · Full SLA Group performance tables published to all department heads.

Programme Baseline:  This document (30-section programme summary) serves as the authoritative baseline for APR-2029. All subsequent amendments will be recorded as new sections following the pattern established throughout this manuscript.

32. APR-2029 Annual Programme Review & AMD-003 Scope

32.1  Overview

The APR-2029 Annual Programme Review is the first full review of the DAPH AI Agent Programme at its target scale of 28 active agents across 13 departments. Convened in Q1 2029 following Draft (#28) go-live, this review assessed the complete programme performance under AMD-002, determined the closure status of all five AMD-002 workstreams, and ratified AMD-003 as the governing framework for the next programme evolution cycle.

Review Authority:  Steering Committee Annual Programme Review (APR-2029), convened per Section 23 governance charter. Chaired by SC Chair. Programme Director presented full 28-agent performance report.

AMD-002 Status:  All five AMD-002 workstreams formally closed at APR-2029. WS1 (Capability Enhancement) · WS2 (New Agent Commissioning — Phase D) · WS3 (Infrastructure Scaling) · WS4 (Governance & Compliance Refresh) · WS5 (Cross-Agent Orchestration Expansion) — all objectives delivered.

AMD-003 Ratification:  AMD-003 ratified by SC at APR-2029 (SC-2029-03). AMD-003 governs four active workstreams: WS1 Agent Intelligence Enhancement · WS2 Infrastructure Modernisation · WS3 Advanced Analytics & Reporting · WS4 Governance Framework v2.0. Phase E scoping (WS5) authorised as conditional workstream pending business case.

32.2  28-Agent Programme Performance Review

The APR-2029 review assessed SLA performance for all 28 agents across Groups A through D for the period Q1–Q4 2028 and the Phase D go-live period Q1 2029. All four SLA groups exceeded their minimum thresholds across every metric for the review period, confirming programme maturity and operational stability at the 28-agent scale.

SLA Group A (Kelly, Signal, Aria, Blaze, Nova):  Accuracy 97.2% (target ≥95%) · Completion 94.5% (target ≥92%) · Uptime 99.4% (target ≥99.0%) · Escalation Rate 3.1% (target ≤5%). All thresholds exceeded. No Group A P1 incidents in review period.

SLA Group B (Compass, Remy, Scout, Finn, Hana, Ember, Shore, Draft):  Accuracy 95.1% (target ≥93%) · Completion 92.8% (target ≥90%) · Uptime 98.9% (target ≥98.5%) · Escalation Rate 5.2% (target ≤7%). Draft (#28) onboarded Q1 2029; initial 30-day performance confirmed within Group B thresholds.

SLA Group C (Atlas, Bo, Forge, Leo, Ops, Stone, Pulse, Frame):  Accuracy 95.8% (target ≥94%) · Completion 93.2% (target ≥91%) · Uptime 99.3% (target ≥99.0%) · Escalation Rate 4.4% (target ≤6%). Frame (#27) TEC-F-05 P-LOW backlog item resolved Q4 2028 as committed.

SLA Group D (Core, Nexus, Rex, Guardian, Talent, Vega, Ledger):  Accuracy 98.1% (target ≥97%) · Completion 96.3% (target ≥95%) · Uptime 99.7% (target ≥99.5%) · Escalation Rate 2.8% (target ≤4%). Ledger (#26) posted highest accuracy of all Phase D agents at 98.1%.

Overall Programme Finding:  Zero critical (P1) incidents across all 28 agents in Q4 2028–Q1 2029. Cross-agent orchestration (Section 16) functioning correctly at 28-agent scale. Pulse dashboard confirmed as single source of truth for all KPI monitoring.

32.3  AMD-002 Workstream Final Outcomes

All five AMD-002 workstreams are formally closed upon APR-2029 ratification. The following records the final delivery status and outcome for each workstream:

WS1 — Capability Enhancement (P0):  All 25 v2.5 and v3.0 agents assessed for capability enhancement requirements. Model accuracy improvements deployed to Group D agents (Q3 2028). Accuracy uplift of 1.2% confirmed for Vega and Core. STATUS: CLOSED — DELIVERED.

WS2 — New Agent Commissioning / Phase D (P1):  Phase D agents Ledger (#26), Frame (#27), Draft (#28) all commissioned and live. All PD-CRIT-01–05 criteria met for all three agents. Programme expanded from 25 to 28 agents. STATUS: CLOSED — DELIVERED.

WS3 — Infrastructure Scaling (P1):  Infrastructure capacity scaled to support 28-agent concurrent processing load. Pulse dashboard upgraded to handle 28-agent KPI streams. System latency maintained below SLA thresholds under full load. STATUS: CLOSED — DELIVERED.

WS4 — Governance & Compliance Refresh (P0):  Section 19 Data Privacy compliance updated for PDPA 2026 guidance. Section 20 AI Ethics policy reviewed against NIST AI RMF v1.1. Annual audit schedule confirmed operational per Section 22. STATUS: CLOSED — DELIVERED.

WS5 — Cross-Agent Orchestration Expansion (P1):  Phase D orchestration links (Ledger→Pulse, Ledger→Core, Frame→Ops, Draft→Ledger) verified and documented in Section 16 update. 28-agent orchestration map validated at APR-2029. STATUS: CLOSED — DELIVERED.

32.4  APR-2029 Steering Committee Decisions

The Steering Committee recorded the following formal decisions at APR-2029. All decisions effective from date of ratification.

SC-2029-02 — AMD-002 Programme Closure:  AMD-002 formally closed. All five workstreams delivered. Programme Director instructed to file AMD-002 closure report with SC secretariat and update programme governance records.

SC-2029-03 — AMD-003 Ratification:  AMD-003 ratified. Governing four workstreams: WS1 Agent Intelligence Enhancement (P0) · WS2 Infrastructure Modernisation (P1) · WS3 Advanced Analytics & Reporting (P1) · WS4 Governance Framework v2.0 (P0). Total AMD-003 envelope: ฿4.8M approved by Finance Director.

SC-2029-04 — Agent Intelligence Enhancement (AMD-003-WS1):  WS1 authorised. Programme Director to commission model capability review for all 28 agents, prioritising Group D accuracy improvements and Group B processing speed enhancements. Target delivery Q3 2029.

SC-2029-05 — Infrastructure Modernisation (AMD-003-WS2):  WS2 authorised. IT Director to lead cloud infrastructure assessment with target of 30% improvement in processing capacity by Q4 2029. Phase E expansion headroom to be built into infrastructure plan.

SC-2029-06 — Phase E Scoping Authorisation (AMD-003-WS5, Conditional):  Phase E scoping authorised as conditional workstream under AMD-003-WS5. Programme Director to conduct Phase E opportunity assessment across remaining automation gaps and submit business case to SC by Q2 2029. SC will make Phase E go/no-go at Q2 2029 interim review.

32.5  AMD-003 Workstream Framework

AMD-003 establishes the programme evolution framework for the post-Phase D operating period. The four confirmed workstreams plus the conditional Phase E scoping workstream are defined as follows:

AMD-003-WS1 — Agent Intelligence Enhancement (P0):  Systematic capability uplift across all 28 agents. Focus areas: model accuracy improvements (targeting ≥1% gain per Group), natural language processing refinements for CRM-facing agents (Aria, Remy, Ember), and prediction accuracy for FIN/PM agents (Ledger, Frame). Target completion Q3 2029.

AMD-003-WS2 — Infrastructure Modernisation (P1):  Cloud infrastructure scaling to support the 28-agent concurrent load with headroom for up to 35 agents (Phase E contingency). Includes Pulse dashboard v2.0 upgrade for enhanced real-time analytics, improved failover architecture, and data residency compliance. Target completion Q4 2029.

AMD-003-WS3 — Advanced Analytics & Reporting (P1):  Enhanced cross-agent analytics layer delivering predictive insights, anomaly detection, and department-level efficiency trend reporting. New reporting outputs: monthly cross-department AI impact report, quarterly agent performance benchmarking, annual programme ROI statement. Target completion Q4 2029.

AMD-003-WS4 — Governance Framework v2.0 (P0):  Full review and update of Sections 19–23 to reflect evolving AI regulations (PDPA amendments, EU AI Act compliance where applicable), expanded audit scope for 28-agent programme, and refreshed SC charter incorporating Phase D lessons learned. Target completion Q2 2029.

AMD-003-WS5 — Phase E Scoping (P2, Conditional):  Conditional workstream: activated upon SC-2029-06 authorisation. Scope: identify next-generation automation opportunities beyond the 28-agent baseline, assess HR, Legal, and IT departments as priority Phase E candidates, and develop PD-CRIT equivalent assessment framework for Phase E agents. Business case to SC by Q2 2029.

32.6  APR-2029 Milestones

The following milestone schedule governs AMD-003 execution and the next programme evolution cycle following APR-2029 ratification:

APR29-M1 (Q1 2029):  APR-2029 review convened. All 28-agent SLA performance data compiled and presented to SC. AMD-002 closure reports submitted for all five workstreams. AMD-003 draft circulated to SC members for review.

APR29-M2 (Q2 2029):  AMD-003 ratified (SC-2029-03). WS1 and WS4 workstreams activated. Phase E business case submitted to SC (AMD-003-WS5). SC Q2 2029 interim review: Phase E go/no-go decision. Governance Framework v2.0 (WS4) first draft delivered.

APR29-M3 (Q2–Q3 2029):  AMD-003-WS1 Agent Intelligence Enhancement first deployment. Group D and Group B priority agents receive capability uplift. AMD-003-WS2 Infrastructure Modernisation architecture approved. Pulse dashboard v2.0 development commences.

APR29-M4 (Q3–Q4 2029):  AMD-003-WS2 Infrastructure Modernisation completed. AMD-003-WS3 Advanced Analytics layer deployed. Monthly cross-department AI impact report first issue published. Governance Framework v2.0 (WS4) approved by SC.

APR29-M5 (Q4 2029 – Q1 2030):  All AMD-003 confirmed workstreams (WS1–WS4) delivered. Phase E agent commissioning commences (if SC-2029-06 approved). APR-2030 Annual Programme Review preparation begins. Programme summary amendment recorded covering AMD-003 outcomes.

AMD-003 milestone outcomes are reported to the SC at each milestone gate. Any workstream delay or budget variance triggers escalation per Section 18 Incident Response protocol. Amendment records for AMD-003 outcomes will be documented in subsequent sections of this programme summary as each workstream delivers.

33. AMD-003 WS1 — Agent Intelligence Enhancement Implementation

33.1  WS1 Overview

AMD-003 Workstream 1 (WS1: Agent Intelligence Enhancement) is a P0 priority initiative ratified under SC-2029-03 at the APR-2029 Steering Committee meeting. WS1 constitutes the highest-priority workstream within the AMD-003 framework and is the first to commence execution, beginning Q1 2029 concurrently with AMD-003 ratification.

WS1 scope encompasses a full ML inference pipeline upgrade across all 28 live agents, group-targeted capability enhancements, and establishment of a cross-agent intelligence sharing protocol. Budget allocation: ฿1.2M of the total AMD-003 envelope of ฿4.8M.

Mandate Reference:  AMD-003, Workstream 1 — SC-2029-04 authorisation

Budget:  ฿1.2M (AMD-003 WS1 allocation)

Programme Lead:  Programme Director + AI Architecture Lead

Timeline:  Q1 2029 – Q3 2029

SLA Revision Authority:  SC-2029-07 (projected Q3 2029)

Agents in Scope:  All 28 live agents across SLA Groups A, B, C, D

33.2  Enhancement Specifications by SLA Group

WS1 enhancements are applied at both programme-wide and group-specific levels. The programme-wide ML model version upgrade (AI-WS1-02) applies to all 28 agents. Targeted enhancements address the distinct operational profiles of each SLA group.

Group D — Core, Nexus, Rex, Guardian, Talent, Vega, Ledger (7 agents):

Enhancement:  Decision-accuracy uplift targeting ≥98.5% accuracy (from current baseline ≥97.0%)

Method:  Extended training dataset curation, advanced ensemble inference, confidence calibration tuning

Projected SLA revision:  Accuracy threshold raised from 97% to 98.5% in SLA Group D schedule post SC-2029-07

Group A — Kelly, Signal, Aria, Blaze, Nova (5 agents):

Enhancement:  NLP context window expansion + multi-turn conversational dialogue support

Method:  Transformer model context length upgrade, session-state memory integration

Target:  Support for 12-turn client interaction threads (up from 4-turn baseline)

Group C — Atlas, Bo, Forge, Leo, Ops, Stone, Pulse, Frame (8 agents):

Enhancement:  Predictive analytics module integration — forward-looking forecasting capability

Method:  Time-series ML module overlay integrated with existing inference pipelines

Target:  14-day operational forecasting for procurement, scheduling, and KPI trend agents

Group B — Compass, Remy, Scout, Finn, Hana, Ember, Shore, Draft (8 agents):

Enhancement:  Automated escalation scoring v2 — dynamic escalation threshold calibration

Method:  Bayesian risk scoring model replacing static rule-based escalation thresholds

Target:  Reduce escalation rate from ≤7% SLA threshold to operational target of ≤5%

33.3  WS1 Implementation Checklist

Seven implementation checkpoints constitute the WS1 delivery checklist. Each item requires sign-off from the AI Architecture Lead prior to programme-wide deployment.

AI-WS1-01:  Architecture Design Freeze — WS1 technical specification signed off by AI Architecture Lead — Q1 2029

AI-WS1-02:  ML Model Version Upgrade — inference pipeline upgrade deployed across all 28 agents — Q1 2029

AI-WS1-03:  Group A NLP Enhancement Deployed — context window expansion live for Kelly, Signal, Aria, Blaze, Nova — Q2 2029

AI-WS1-04:  Group C Predictive Analytics Module Live — forecasting overlay operational for Atlas, Bo, Forge, Leo, Ops, Stone, Pulse, Frame — Q2 2029

AI-WS1-05:  Group B Escalation Scoring v2 Deployed — Bayesian model live for Compass, Remy, Scout, Finn, Hana, Ember, Shore, Draft — Q2 2029

AI-WS1-06:  Group D Accuracy Enhancement Complete — confidence calibration tuning finalised; accuracy baseline ≥98.5% confirmed — Q3 2029

AI-WS1-07:  Cross-Agent Intelligence Sharing Protocol Live — shared inference feature store operational across all 28 agents — Q3 2029

33.4  Governance & Approvals

WS1 is governed under the AMD-003 Programme Framework with direct Steering Committee oversight. All major deployment gates require dual sign-off from Programme Director and AI Architecture Lead. SLA threshold revisions arising from WS1 outcomes require full SC ratification.

Authorising Decision:  SC-2029-04 — WS1 commencement approval (Q1 2029 SC meeting)

Mid-Point Review:  Q2 2029 Steering Committee checkpoint — AI-WS1-03/04/05 progress report required

Completion Sign-off:  Programme Director + AI Architecture Lead + CTO (joint)

SLA Revision Sign-off:  SC-2029-07 (projected Q3 2029) — revised Group D and Group B thresholds

Risk Escalation Path:  Any AI-WS1 checklist item RED status escalates to Programme Director within 48 hours

WS5 Dependency:  Phase E Scoping (AMD-003 WS5, conditional) — activation contingent on WS1 Group D accuracy outcomes at SC-2029-07

33.5  WS1 Milestones

Five programme milestones govern WS1 delivery and reporting cadence:

WS1-M1:  WS1 Kickoff & Architecture Design Freeze (AI-WS1-01 complete) — Q1 2029

WS1-M2:  ML Model Version Upgrade — All 28 Agents Live (AI-WS1-02 complete) — Q1 2029

WS1-M3:  Group-Specific Enhancements Deployed (AI-WS1-03/04/05 complete) — Q2 2029

WS1-M4:  Group D Accuracy Enhancement & Cross-Agent Intelligence Sharing Live (AI-WS1-06/07 complete) — Q3 2029

WS1-M5:  WS1 Formal Completion — SC-2029-07 SLA Revision Submitted — Q3 2029

34. AMD-003 WS4 — Governance Framework v2.0 Implementation

34.1  WS4 Overview

AMD-003 Workstream 4 (WS4: Governance Framework v2.0) is a P0 priority initiative ratified under SC-2029-03. WS4 runs concurrently with WS1 and is the second P0 workstream within AMD-003, commencing Q1 2029. Its mandate is to replace the current v1.0 governance framework — drafted under AMD-001 and last substantively revised at AMD-002 WS4 — with a comprehensive v2.0 document suite fit for a fully commissioned 28-agent programme.

WS4 scope encompasses governance policy refresh, SLA management framework update (incorporating WS1 SLA revision outcomes), Steering Committee Charter v2.0, agent lifecycle policy, cross-agent dependency governance, and the formal publication of the Governance Framework v2.0 consolidated document. Budget allocation: ฿0.9M of the AMD-003 total envelope of ฿4.8M.

Mandate Reference:  AMD-003, Workstream 4 — SC-2029-03 ratification

Budget:  ฿0.9M (AMD-003 WS4 allocation)

Programme Lead:  Programme Director + Head of Governance & Compliance

Timeline:  Q1 2029 – Q4 2029

SLA Integration:  WS4 incorporates SLA threshold revisions from AMD-003 WS1 post SC-2029-07 ratification (Q3 2029)

Output:  Governance Framework v2.0 — five policy documents + consolidated manual

34.2  Governance Framework v2.0 Scope

Version 2.0 of the DAPH Decor AI Agent Governance Framework supersedes all prior governance documents and policies issued under AMD-001 and AMD-002. The v2.0 scope covers six structural areas:

Area 1 — Programme Mandate & Scope Policy v2.0:  Updated AMD programme mandate covering all 28 live agents, Phase E conditional expansion clause, AMD-003 full workstream remit

Area 2 — SLA Management Policy v2.0:  Revised SLA Group thresholds (Group D ≥98.5% accuracy, Group B target ≤5% escalation) incorporating SC-2029-07 decisions; full 28-agent SLA schedule reissued

Area 3 — Steering Committee Charter v2.0:  Expanded SC decision rights to cover AMD-003 WS1–WS5 governance; Phase E conditional approval framework; AMD lifecycle decision taxonomy

Area 4 — Agent Lifecycle Policy v2.0:  Commission-to-decommission policy updated for 28-agent estate; new Phase D commissioning precedents (Ledger, Frame, Draft) codified; decommissioning trigger criteria v2

Area 5 — Cross-Agent Dependency & Orchestration Governance Policy v2.0:  Cross-agent dependency register (Ledger→Pulse/Core, Frame→Ops/Pulse, Draft→Ledger); WS1 intelligence sharing protocol governance; AMD-003 WS5 Phase E inter-agent scope governance

Area 6 — Annual Review & Amendment Governance:  Formalised APR review cadence (Q1 annually); AMD lifecycle governance including WS initiation, mid-point, and closure criteria; SC ratification thresholds for new WS and budget amendments

34.3  WS4 Implementation Checklist

Six implementation checkpoints constitute the WS4 delivery schedule. Items GV-WS4-04 and GV-WS4-05 are sequentially dependent on SC-2029-07 (WS1 SLA revision, Q3 2029).

GV-WS4-01:  Governance Gap Analysis — formal gap assessment against AMD-001/002 policy suite; findings report to Programme Director — Q1 2029

GV-WS4-02:  Agent Lifecycle Policy v2.0 Draft — commission-to-decommission policy incorporating Phase D precedents and 28-agent estate — Q2 2029

GV-WS4-03:  Steering Committee Charter v2.0 Ratified — expanded SC decision rights, Phase E conditional framework, AMD lifecycle taxonomy adopted by full SC — Q2 2029

GV-WS4-04:  SLA Management Policy v2.0 Published — revised Group D and Group B thresholds from SC-2029-07 incorporated; 28-agent SLA schedule reissued — Q3 2029 (post SC-2029-07)

GV-WS4-05:  Cross-Agent Dependency & Orchestration Policy v2.0 Published — dependency register updated with WS1 intelligence sharing protocol — Q3 2029

GV-WS4-06:  Governance Framework v2.0 Consolidated Manual Published — all five policy documents compiled and formally issued; SC acknowledgement recorded — Q4 2029

34.4  Governance Policies Published under WS4

The following five policy documents constitute the deliverable set for Governance Framework v2.0. Each supersedes its AMD-001/002 predecessor upon SC acknowledgement at GV-WS4-06:

GV2-P1:  Programme Mandate & Scope Policy v2.0 — covers AMD-003 full scope, 28-agent estate, Phase E conditional clause

GV2-P2:  Agent SLA Management Policy v2.0 — Group A–D revised thresholds, 28-agent SLA schedule, SC-2029-07 revisions embedded

GV2-P3:  Steering Committee Decision Rights Framework v2.0 — AMD lifecycle decision taxonomy, Phase E conditional approval, WS governance rights

GV2-P4:  Agent Lifecycle (Commission to Decommission) Policy v2.0 — Phase D commissioning precedents, decommission trigger criteria v2, AMD-003 WS5 Phase E scoping governance

GV2-P5:  Cross-Agent Dependency & Orchestration Governance Policy v2.0 — dependency register, WS1 intelligence sharing governance, inter-agent SLA escalation chain

34.5  Governance & Approvals

WS4 is governed under the AMD-003 Programme Framework. Policy documents GV2-P1 through GV2-P5 require review by the Programme Director and Head of Governance & Compliance prior to SC acknowledgement. The consolidated Governance Framework v2.0 Manual (GV-WS4-06) requires full SC sign-off.

Authorising Decision:  SC-2029-03 — AMD-003 ratification includes WS4 mandate

WS1 Integration Point:  GV-WS4-04 and GV-WS4-05 sequentially depend on SC-2029-07 SLA revision outputs from AMD-003 WS1 (Q3 2029)

Policy Review Authority:  Programme Director + Head of Governance & Compliance (joint approval for GV2-P1 through GV2-P5)

SC Acknowledgement:  Full Steering Committee sign-off required for GV-WS4-06 Governance Framework v2.0 Manual publication (Q4 2029 SC meeting)

Supersession Clause:  All AMD-001 and AMD-002 governance documents superseded upon GV-WS4-06 SC acknowledgement; prior versions archived

Risk Escalation:  Any GV-WS4 checklist item RED status escalates to Programme Director within 48 hours

34.6  WS4 Milestones

Five milestones govern WS4 delivery and Steering Committee reporting cadence:

WS4-M1:  WS4 Kickoff & Governance Gap Analysis Complete (GV-WS4-01) — Q1 2029

WS4-M2:  Agent Lifecycle Policy v2.0 & SC Charter v2.0 Ratified (GV-WS4-02/03) — Q2 2029

WS4-M3:  SLA Management Policy v2.0 & Cross-Agent Dependency Policy v2.0 Published (GV-WS4-04/05, post SC-2029-07) — Q3 2029

WS4-M4:  Governance Framework v2.0 Consolidated Manual Draft Circulated for SC Review — Q4 2029

WS4-M5:  WS4 Formal Completion — Governance Framework v2.0 Published & SC Acknowledged (GV-WS4-06) — Q4 2029

Section 35: AMD-003 WS2 – Infrastructure Modernisation

35.1 Workstream Overview

AMD-003 Workstream 2 (WS2) – Infrastructure Modernisation delivers the compute, data-pipeline, network-security and observability upgrades required to sustain 28 live agents at enterprise scale through FY2030. Authorised under SC-2029-03 (AMD-003 ratification) and informed by SC-2029-05 (infrastructure risk register), WS2 carries P1 priority with a budget of ฿1.1M and runs Q2 2029 – Q2 2030, making it the longest AMD-003 workstream.

WS2 operates in parallel with WS1 (Agent Intelligence Enhancement) and WS4 (Governance Framework v2.0) through Q3 2029, then continues independently into Q1–Q2 2030. Phase E pre-provisioning (WS5, conditional on SC-2029-06) is sequenced after the WS2 compute baseline is certified.

Key Parameters:

• Workstream: AMD-003 WS2 – Infrastructure Modernisation

• Priority: P1

• Budget Allocation: ฿1.1M (AMD-003 total ฿4.8M)

• Governing Resolutions: SC-2029-03 (ratification), SC-2029-05 (infrastructure risk register)

• Timeline: Q2 2029 – Q2 2030

• Uptime Constraint: Zero-downtime migration protocol mandatory; all SLA group uptime targets must be maintained throughout all migration windows

35.2 Scope

WS2 modernises five interdependent infrastructure layers underpinning the DAPH Decor AI Agent Programme. Each layer is independently testable and can be rolled back without affecting other layers.

35.2.1 Compute Layer Containerisation & Auto-Scaling

Migration of all 28 agent workloads from bare-metal virtual machines to containerised orchestration (Kubernetes-class). Auto-scaling policies calibrated per SLA group (Group D ≥99.5% uptime, Group A ≥99.0%, Group C ≥99.0%, Group B ≥98.5%). Blue-green deployment strategy eliminates downtime during container migration.

35.2.2 Data Pipeline Real-Time Streaming (28 Agents)

Replacement of batch-processing data ingestion with event-driven streaming architecture. All 28 agents receive sub-5-second data freshness guarantees, replacing batch windows of up to 15 minutes. Pipeline capacity is pre-provisioned at 1.5× peak observed load (APR-2029 benchmark) to accommodate v3.0 intelligence enhancements from WS1.

35.2.3 Network Security & Segmentation Refresh

Implementation of zero-trust network architecture with agent-level micro-segmentation. Each SLA group is isolated in a dedicated network segment with inter-group traffic encrypted and logged. Aligns with GV2-P4 (Cross-Agent Dependency & Communication Policy) from WS4.

35.2.4 Monitoring & Observability Platform v2

Deployment of a unified observability stack (metrics, logs, traces) covering all 28 agent processes, data pipelines and infrastructure components. Real-time alerting with SLA-breach prediction (15-minute forecast horizon) feeds the Incident Response playbook (Section 18). Dashboard integration with the Ops agent (#20) KPI view.

35.2.5 Phase E Infrastructure Pre-Provisioning

Conditional on SC-2029-06 (Phase E scoping approval from WS5). Capacity reservation and environment scaffolding for up to 4 Phase E candidate agents. Triggered only after WS2 compute baseline is certified (INF-WS2-06) and SC-2029-06 is issued. Estimated additional budget draw: ฿0.15M from WS5 allocation.

35.3 Implementation Checklist (INF-WS2-01–07)

The following seven checkpoints govern WS2 delivery. Each checkpoint requires Programme Director sign-off. INF-WS2-04 (streaming pipeline) additionally requires Head of Technology Architecture sign-off on latency benchmarks. INF-WS2-07 (Phase E pre-provisioning) is conditional on SC-2029-06.

INF-WS2-01 – Infrastructure Baseline Audit

Complete audit of all 28 agent compute, storage and network resources against the FY2030 capacity model. Identifies over-provisioned and under-provisioned resources. Output: Infrastructure Baseline Report v1. Owner: Head of Technology Architecture. Target: Q2 2029.

INF-WS2-02 – Containerisation Design & Pilot

Container image design, registry setup and pilot migration of 4 non-critical agents (one per SLA group). Validates zero-downtime migration runbook. Rollback tested within 30-minute window. Owner: Infrastructure Engineering Lead. Target: Q3 2029.

INF-WS2-03 – Full Containerisation Rollout (28 Agents)

Phased migration of remaining 24 agents to containerised orchestration. Migration windows scheduled 22:00–06:00 ICT outside peak operating hours. SLA monitoring active throughout. Owner: Infrastructure Engineering Lead + On-Call SLA Monitor. Target: Q4 2029.

INF-WS2-04 – Real-Time Streaming Pipeline Deployment

Deployment of event-driven streaming architecture for all 28 data ingestion pipelines. Parallel-run with legacy batch system for minimum 30 days before cutover. Requires Head of Technology Architecture sign-off on latency benchmarks (≤5s p99). Target: Q3–Q4 2029.

INF-WS2-05 – Network Security & Segmentation Implementation

Zero-trust architecture rollout and SLA-group micro-segmentation. Penetration test required prior to sign-off. Coordinates with GV2-P4 (WS4) for policy alignment. Owner: Head of Information Security. Target: Q4 2029.

INF-WS2-06 – Monitoring & Observability Platform v2 Go-Live

Unified observability stack live for all 28 agents. SLA-breach prediction model validated against 90-day historical data. Integration with Ops agent (#20) KPI dashboard confirmed. Certified by Programme Director. Target: Q4 2029 – Q1 2030.

INF-WS2-07 – Phase E Infrastructure Pre-Provisioning

Conditional on SC-2029-06. Capacity reservation and environment scaffolding for Phase E candidates. Triggered after INF-WS2-06 certification. Owner: Programme Director + Head of Technology Architecture. Target: Q1–Q2 2030 (conditional).

35.4 Zero-Downtime Migration Protocol

All migration activities involving live agent workloads must comply with the Zero-Downtime Migration Protocol. This protocol is mandatory for INF-WS2-03 (containerisation rollout), INF-WS2-04 (streaming pipeline cutover) and INF-WS2-05 (network segmentation).

• Pre-migration: Full environment snapshot taken within 4 hours of migration window start. Rollback artifact retained for minimum 72 hours post-cutover.

• Window scheduling: All agent group migrations scheduled 22:00–06:00 ICT. Group D and Group A migrations require minimum 7-day advance notice to Programme Director.

• Parallel operation: New infrastructure runs in shadow mode for minimum 14 days (compute) or 30 days (streaming pipeline) before traffic cutover. Both environments monitored simultaneously.

• SLA monitoring: Continuous SLA metric collection throughout migration windows. Automatic rollback triggered if any group breaches uptime threshold for more than 3 consecutive minutes.

• Post-migration validation: 48-hour hypercare period after each migration window. On-call Infrastructure Engineer and SLA Monitor assigned. Escalation to Programme Director if P1 SLA breach occurs.

• Sign-off: Programme Director signs INF-WS2 checklist item only after 48-hour hypercare period completes with zero P1 incidents.

35.5 Governance & Dependencies

WS2 intersects with multiple active workstreams and governance resolutions. All dependencies are tracked in the AMD-003 Programme Dashboard (owned by Core agent, #14).

SC-2029-03 – AMD-003 Ratification

Authorises WS2 budget (฿1.1M) and timeline. No further SC resolution required to commence INF-WS2-01 through INF-WS2-06.

SC-2029-05 – Infrastructure Risk Register

Defines acceptable risk thresholds for migration activities. Informs zero-downtime protocol design and SLA monitoring requirements throughout WS2.

SC-2029-06 – Phase E Scoping Approval

Conditional trigger for INF-WS2-07. Issued by Steering Committee upon satisfactory WS1 and WS3 progress review. WS2 delivery is not blocked pending SC-2029-06.

WS4 Dependency – GV2-P4 Cross-Agent Communication Policy

Network segmentation design (INF-WS2-05) must comply with GV2-P4 once issued. If WS4 GV2-P4 is delayed beyond Q3 2029, INF-WS2-05 proceeds with interim security standards and is amended post-WS4.

WS1 Dependency – Agent Intelligence Enhancement

Streaming pipeline (INF-WS2-04) capacity must accommodate WS1 model upgrade data volumes. WS1 team provides throughput specifications to WS2 by end Q2 2029.

35.6 Milestones

WS2-M1 (Q2 2029)

Infrastructure Baseline Audit complete (INF-WS2-01). Baseline report issued. Containerisation design finalised.

WS2-M2 (Q3 2029)

Containerisation pilot complete (INF-WS2-02). Streaming pipeline shadow-run commenced (INF-WS2-04 phase 1). Network segmentation design approved.

WS2-M3 (Q4 2029)

Full containerisation rollout complete (INF-WS2-03). Streaming pipeline cutover complete (INF-WS2-04). Network security implementation complete (INF-WS2-05).

WS2-M4 (Q1 2030)

Monitoring & Observability Platform v2 go-live (INF-WS2-06). 48-hour hypercare complete. Programme Director certification issued.

WS2-M5 (Q2 2030)

WS2 closure: all seven checkpoints signed off. Phase E pre-provisioning complete if SC-2029-06 issued (INF-WS2-07). AMD-003 WS2 formally closed at Steering Committee.

Section 36: AMD-003 WS3 – Advanced Analytics & Reporting

36.1 Workstream Overview

AMD-003 Workstream 3 (WS3) – Advanced Analytics & Reporting builds the analytics and business intelligence layer on top of the 28-agent programme, delivering cross-agent performance dashboards, predictive SLA modelling, automated Steering Committee reporting and client intelligence feeds. WS3 is authorised under SC-2029-03 (AMD-003 ratification) and carries P1 priority with a budget of ฿0.8M, running Q3 2029 – Q1 2030.

WS3 is sequenced to begin after WS1 model enhancements are substantially complete (WS1-M3, Q2 2029) and depends on the WS2 real-time streaming pipeline (INF-WS2-04) for live agent data feeds. WS3 analytics outputs directly support the Annual Programme Review cadence established in Section 28 (Q1 2028 APR) and Section 32 (APR-2029), and will underpin the APR-2030 review cycle.

Key Parameters:

• Workstream: AMD-003 WS3 – Advanced Analytics & Reporting

• Priority: P1

• Budget Allocation: ฿0.8M (AMD-003 total ฿4.8M)

• Governing Resolution: SC-2029-03 (AMD-003 ratification)

• Timeline: Q3 2029 – Q1 2030

• Key Input Dependencies: WS1 intelligence enhancements (WS1-M3); WS2 streaming pipeline (INF-WS2-04); WS4 policy framework (GV2-P1–P5)

36.2 Scope

WS3 delivers five integrated analytics and reporting capabilities, each built on a common data layer fed by the WS2 streaming pipeline. Capabilities are developed sequentially with the data warehouse as the foundational prerequisite.

36.2.1 Analytics Data Warehouse

Structured data store consolidating all 28 agent output streams, SLA metrics, incident records, governance decisions and operational data into a single analytical source of truth. Fed by the WS2 streaming pipeline (INF-WS2-04). Designed to support both real-time query (dashboard) and batch query (report generation) workloads. Schema version-controlled with agent lifecycle in alignment with Section 21.

36.2.2 Cross-Agent Performance Analytics Dashboard

Unified web-based dashboard providing real-time and historical views of all 28 agents across four SLA groups (A–D). Includes department-level drill-down (13 departments), individual agent KPI cards and SLA group compliance trend charts. Integrates with the Core agent (#14) programme dashboard and the Ops agent (#20) KPI view. Accessible to Programme Director, Steering Committee and Head of Operations.

36.2.3 Predictive Analytics & SLA Trend Modelling

Forecasting models providing 90-day forward projections of SLA compliance by agent and SLA group. Models trained on APR-2029 performance baselines (Section 32) and enriched by WS1 Group A–D intelligence enhancement outputs. Includes workload trend modelling, escalation rate prediction and uptime risk flagging. Alert threshold: predicted breach probability >15% triggers Steering Committee notification.

36.2.4 Automated Steering Committee Report Generation

Template-driven automated generation of quarterly SC performance packs and annual programme review documents. Reports pull live data from the analytics warehouse, apply SC-approved templates and are published to the governance portal for Programme Director review before distribution. Aligned with the SC Charter (Section 23) reporting calendar and the Annual Review cadence (Sections 24, 28, 32).

36.2.5 Client Intelligence Reporting Integration

Client-facing analytics feeds integrating data from Ember (#23, Design Brief Automation) and Shore (#25, Post-Installation Support). Produces project completion analytics, client satisfaction trend reports and post-install support resolution summaries. Accessible via the client portal. All client-facing reports comply with the Data Privacy policy (Section 19) and PDPA/GDPR requirements.

36.3 Implementation Checklist (ANL-WS3-01–06)

Six checkpoints govern WS3 delivery. Each checkpoint requires Programme Director sign-off. ANL-WS3-02 (data warehouse) is a hard prerequisite for ANL-WS3-03 through ANL-WS3-06. ANL-WS3-06 (client reporting) additionally requires Head of Data & Analytics sign-off and Data Protection Officer compliance review.

ANL-WS3-01 – Analytics Requirements & Data Model Design

Stakeholder workshops with Programme Director, Head of Operations, Head of Finance and SC representatives to define KPI catalogue, reporting cadence and dashboard requirements. Output: Analytics Requirements Document v1 and Data Model Specification. Owner: Head of Data & Analytics. Target: Q3 2029.

ANL-WS3-02 – Data Warehouse Build & Agent Feed Integration

Build analytics data warehouse and connect all 28 agent output streams. Requires WS2 INF-WS2-04 streaming pipeline in parallel-run mode or live. Schema validation against all 28 agent data contracts. Owner: Data Engineering Lead. Target: Q3 2029.

ANL-WS3-03 – Cross-Agent Performance Dashboard Development & Go-Live

Development, user acceptance testing and go-live of the unified analytics dashboard. UAT involves Programme Director and at least three department heads. Dashboard accessible via governance portal. Owner: Analytics Engineering Lead. Target: Q4 2029.

ANL-WS3-04 – Predictive Analytics Model Deployment

Train, validate and deploy 90-day SLA compliance forecasting and workload trend models. Validation requires backtesting against minimum 12 months of historical performance data. Alert integration with Core (#14) programme dashboard and Incident Response playbook (Section 18). Target: Q4 2029.

ANL-WS3-05 – Automated SC Report Generation Go-Live

Template build, integration with analytics warehouse and SC governance calendar, and Programme Director sign-off on report format. First automated quarterly pack generated and reviewed before go-live confirmation. Owner: Programme Director + Head of Data & Analytics. Target: Q4 2029 – Q1 2030.

ANL-WS3-06 – Client Intelligence Reporting Integration

Integration of Ember (#23) and Shore (#25) data feeds into client-facing analytics module. Data Protection Officer compliance review required before client portal activation. Owner: Head of Data & Analytics + Data Protection Officer. Target: Q1 2030.

36.4 Analytics Architecture

The WS3 analytics stack operates in three layers, each independently maintainable:

Data Ingestion Layer

Primary feed: WS2 real-time streaming pipeline (INF-WS2-04) delivering sub-5-second data freshness for all 28 agent streams. Secondary feed: governance data (SC decisions, audit records) from DOCX-based records via scheduled extraction. All data is schema-validated on ingestion; rejected records are logged and escalated to the Data Engineering Lead within 1 hour.

Analytics & Computation Layer

OLAP-style query engine for real-time dashboard queries and a batch computation engine for predictive model training and scheduled report generation. Predictive models are retrained monthly against the latest 12 months of performance data. Model version control aligned with agent lifecycle management (Section 21) — model versions are archived and traceable to specific agent firmware versions.

Presentation & Distribution Layer

Browser-based dashboards served via the governance portal. Scheduled PDF/HTML report packages distributed to SC members via the governance calendar. Client-facing analytics delivered through the client portal with role-based access controls. All presentation assets comply with PDPA/GDPR (Section 19) and the AI Ethics policy (Section 20).

36.5 Governance & Dependencies

WS3 has dependencies on three other AMD-003 workstreams and coordinates with the existing governance framework. All dependencies are tracked in the AMD-003 Programme Dashboard (owned by Core agent, #14).

SC-2029-03 – AMD-003 Ratification

Authorises WS3 budget (฿0.8M) and timeline. No further SC resolution required to commence ANL-WS3-01 through ANL-WS3-05.

WS2 Dependency – INF-WS2-04 Streaming Pipeline

ANL-WS3-02 (data warehouse agent feed integration) requires WS2 streaming pipeline in parallel-run or live state. If INF-WS2-04 is delayed beyond Q3 2029, WS3 data warehouse build proceeds with legacy batch feed and migrates to streaming on INF-WS2-04 go-live, with no WS3 timeline impact.

WS1 Dependency – Intelligence Enhancement Outputs

Predictive analytics models (ANL-WS3-04) use WS1 Group A–D enhancement outputs as model features. WS1 team provides feature specifications to WS3 by end Q3 2029. WS3 model training begins when WS1-M3 (Q2 2029) baseline data is available.

WS4 Dependency – GV2-P1 Programme Mandate Policy

Automated SC report templates (ANL-WS3-05) must align with GV2-P1 Programme Mandate Policy from WS4. If WS4 GV2-P1 is delayed beyond Q4 2029, ANL-WS3-05 proceeds with existing report templates and is updated post-WS4 at no additional cost.

Section 23 – SC Charter & Reporting Calendar

WS3 automated reports are scheduled in alignment with the SC Charter reporting calendar (Section 23). Quarterly packs target 10 days before each SC meeting. Annual review packs target 20 days before the APR session.

36.6 Milestones

WS3-M1 (Q3 2029)

Analytics requirements and data model design complete (ANL-WS3-01). Analytics Requirements Document v1 issued. Data warehouse build commenced (ANL-WS3-02 phase 1).

WS3-M2 (Q3 2029)

Analytics data warehouse live and all 28 agent feeds integrated (ANL-WS3-02). Dashboard development commenced (ANL-WS3-03 phase 1). Streaming pipeline ingestion validated.

WS3-M3 (Q4 2029)

Cross-agent performance dashboard go-live (ANL-WS3-03). UAT completed and signed off by Programme Director. Predictive analytics models deployed and validated against 12-month backtest (ANL-WS3-04).

WS3-M4 (Q4 2029 – Q1 2030)

Automated SC report generation live (ANL-WS3-05). First automated quarterly pack reviewed and approved by Programme Director. SC reporting calendar integration confirmed.

WS3-M5 (Q1 2030)

WS3 closure: all six checkpoints signed off. Client intelligence reporting integration complete (ANL-WS3-06). DPO compliance review passed. AMD-003 WS3 formally closed at Steering Committee.

37. AMD-003 WS5 - Phase E Scoping

37.1 Overview

AMD-003 Workstream 5 (WS5) commissions a formal scoping study for Phase E - the next strategic expansion of the MONOLITH/DAPH Decor AI Agent Programme beyond the 28-agent Phase D configuration. WS5 is classified Priority 2 (P2) and is conditional upon Steering Committee resolution SC-2029-06, anticipated Q4 2029. Authorisation budget: 0.8M THB. Conditional execution timeline: Q4 2029 - Q2 2030 (scoping); Q3 2030+ (execution, subject to AMD-004 approval).

WS5 is sequenced to begin after AMD-003 WS1 completion (Q3 2029) and draws on analytics outputs from WS3 (ANL-WS3-05 automated SC reports) to inform the Phase E business case. The deliverable is a complete AMD-004 Programme Definition Document for SC review.

37.2 Scope of Work

37.2.1 Phase E Agent Expansion Study

Structured assessment of agent roles required beyond the current 28-agent roster. Scope includes gap analysis against service-line demand, Group A-D capacity utilisation data from WS3 dashboards, and a shortlist of up to 6 candidate new agent profiles. Outputs feed directly into the AMD-004 programme definition and budget model.

37.2.2 Technology Refresh Assessment

Evaluation of next-generation AI/ML platforms and infrastructure options for Phase E. Assessment covers LLM model refresh cycles, vector-store scalability beyond WS2 INF-WS2-03 specifications, and edge-compute options for on-site client deployments. Findings delivered as a Technology Options Report aligned to GV2-P3 vendor management policy.

37.2.3 Operational Capacity Planning

Workforce, licensing, and infrastructure requirements for Phase E operations. Includes headcount modelling for supervisory and QA roles, infrastructure cost projections at three growth scenarios (conservative / base / aggressive), and a risk register covering regulatory, technology, and talent dependencies. Deliverable: Capacity and Budget Model approved at SC-2029-06.

37.2.4 Client Service Innovation Roadmap

Identification of new service lines enabled by Phase E capabilities, informed by WS3 Client Intelligence Reporting (Ember #23, Shore #25) and client portal usage data. Roadmap covers up to 4 new service propositions, revenue projections per proposition, and PDPA/GDPR compliance pre-screening. DPO sign-off required before SC submission.

37.2.5 AMD-004 Programme Definition Document

Consolidated programme definition document integrating all WS5 outputs: agent expansion plan, technology roadmap, capacity model, and client innovation roadmap. Document follows GV2-P1 governance template and Section 23 SC Charter format. AMD-004 requires full SC approval (resolution SC-2030-01 or equivalent) before execution funding is released.

37.3 WS5 Implementation Checklist

[ ]  PHE-WS5-01  |  Scoping Charter and SC-2029-06 Mandate confirmed  |  Target: Q4 2029

[ ]  PHE-WS5-02  |  Phase E Agent Expansion Study delivered  |  Target: Q4 2029

[ ]  PHE-WS5-03  |  Technology Refresh Assessment Report approved  |  Target: Q1 2030

[ ]  PHE-WS5-04  |  Operational Capacity and Budget Model approved at SC  |  Target: Q1 2030

[ ]  PHE-WS5-05  |  Client Service Innovation Roadmap signed off (DPO + SC)  |  Target: Q1 2030

[ ]  PHE-WS5-06  |  AMD-004 Programme Definition Document delivered to SC  |  Target: Q2 2030

37.4 Governance and Dependencies

SC-2029-06 is the conditional authorisation gate for WS5. If SC-2029-06 is deferred or rejected, WS5 is placed in abeyance and AMD-003 closes on WS1-WS4 completion. No WS5 expenditure may be committed prior to SC-2029-06 resolution.

WS1 / AEI-WS1 completion (Q3 2029): required before agent expansion analysis can draw on finalised throughput and accuracy benchmarks.

WS3 / ANL-WS3-05 Automated SC Reports (Q4 2029): client intelligence and performance data required for Client Service Innovation Roadmap.

WS4 / GV2-P1 Governance Template: AMD-004 Programme Definition Document must align to GV2-P1; fallback to existing SC Charter template if GV2-P1 is delayed.

Section 23 SC Charter: SC-2029-06 agenda slot must be reserved per charter reporting calendar no later than 8 weeks before the Q4 2029 SC meeting.

DPO Review: Client Service Innovation Roadmap (37.2.4) requires DPO clearance before submission to SC-2029-06.

37.5 Milestones

WS5-M1  (Q4 2029)  -  SC-2029-06 conditional authorisation obtained; Scoping Charter signed

WS5-M2  (Q4 2029)  -  Phase E Agent Expansion Study and Technology Refresh Assessment complete

WS5-M3  (Q1 2030)  -  Operational Capacity and Budget Model approved by CFO and SC

WS5-M4  (Q1 2030)  -  Client Service Innovation Roadmap approved (DPO sign-off included)

WS5-M5  (Q2 2030)  -  AMD-004 Programme Definition Document submitted to SC for approval

38. AMD-004 Programme Definition Document

38.1 Programme Overview

AMD-004 is the successor programme to AMD-003, constituting the next strategic phase of the MONOLITH/DAPH Decor AI Agent initiative. The AMD-004 Programme Definition Document (PDD) is the formal charter submission prepared in accordance with the GV2-P1 template and SC Charter format established under AMD-003 WS4 Governance Framework v2.0. It consolidates all Phase E scoping outputs from AMD-003 WS5 (PHE-WS5-01 through PHE-WS5-05) into a single ratification-ready programme document.

Programme status: Conditional on SC-2030-01 approval (SC meeting Q3 2030; 8-week agenda notice per Section 23 SC Charter calendar). Indicative budget envelope: 5.2M THB across three fiscal years (FY2031-FY2033), subject to SC ratification. Programme mobilisation target: Q3 2030. Delivery horizon: Q4 2030 - Q2 2033.

38.2 Programme Objectives

Expand the DAPH agent roster to up to 34 agents via Phase E recruitment based on PHE-WS5-01 expansion study outputs (Group A-D gap analysis).

Advance technology infrastructure to next-generation specifications: LLM refresh, edge-compute deployment, and vector-store scalability beyond INF-WS2-03 thresholds.

Deliver up to 4 new client-facing service lines identified in the WS5 Client Service Innovation Roadmap (PHE-WS5-05), with agents Ember (#23) and Shore (#25) as primary delivery leads.

Establish a PDPA/GDPR-embedded compliance framework with a dedicated DPO function, extending AMD-003 WS4 governance standards across all new service lines and agent roles.

Mature the ANL-WS3 analytics platform to enterprise Level 3, delivering cross-agent predictive analytics, automated client reporting v2.0, and operational intelligence capabilities across the full 34-agent ecosystem.

38.3 Proposed Workstream Structure

38.3.1 AMD-004 WS-A: Agent Capability Enhancement Phase 2

Priority: P1. Budget: 1.0M THB. Timeline: Q4 2030 - Q2 2031. Up to 6 new agent profiles identified through PHE-WS5-01 expansion study. Scope includes agent specification, integration testing, and SLA Group calibration aligned to S17 group structures. Builds on AMD-003 WS1 AEI-WS1 agent intelligence framework and the 28-agent Phase D baseline.

38.3.2 AMD-004 WS-B: Technology Infrastructure Next Generation

Priority: P1. Budget: 1.1M THB. Timeline: Q4 2030 - Q3 2031. Implements recommendations from PHE-WS5-02 Technology Refresh Report. Deliverables include: LLM model refresh cycle, edge-compute pilot for distributed agent processing, and vector-store v3 upgrade beyond INF-WS2-03. GV2-P3 vendor management policy applies throughout procurement cycle.

38.3.3 AMD-004 WS-C: Client Service Innovation Delivery

Priority: P1. Budget: 1.2M THB. Timeline: Q1 2031 - Q4 2031. Delivers up to 4 new service lines from the PHE-WS5-05 Client Innovation Roadmap. Agents Ember (#23) and Shore (#25) assigned as lead delivery agents. All new service lines require individual DPO sign-off for PDPA and GDPR compliance prior to client deployment. Builds on AMD-003 WS3 analytics and client intelligence platform.

38.3.4 AMD-004 WS-D: Data & Analytics Maturity Enhancement

Priority: P2. Budget: 0.9M THB. Timeline: Q2 2031 - Q1 2032. Advances the ANL-WS3 analytics data warehouse to enterprise data maturity Level 3. Scope includes cross-agent predictive analytics expansion, automated client reporting v2.0 module, and an enhanced intelligence layer for all 34 agents. Sequenced after WS-A agent onboarding and WS-B infrastructure stabilisation.

38.3.5 AMD-004 WS-E: Governance Continuity & Compliance

Priority: P0. Budget: 1.0M THB. Timeline: Q4 2030 - Q2 2033 (concurrent). Establishes a dedicated DPO function and PDPA/GDPR embedded compliance programme for all AMD-004 activities. Delivers Governance Framework v3.0 building on GV2-P from AMD-003 WS4. Maintains SC Charter format (Section 23) throughout programme lifecycle. Provides regulatory oversight gate for WS-C service line deployments.

38.4 Approval & Programme Initiation Checklist

PDD-001: Programme Charter Drafting (GV2-P1 template) - Q2 2030 (PHE-WS5-06 deliverable)

PDD-002: Budget Envelope Submission to Steering Committee - Q2 2030

PDD-003: DPO Review and Sign-off on PDPA/GDPR provisions - Q2 2030

PDD-004: SC-2030-01 Approval Gate - Q3 2030 (8-week notice per Section 23 SC Charter)

PDD-005: Programme Mobilisation and Workstream WS-A to WS-E Launch - Q3 2030

PDD-006: AMD-004 Kick-off, Baseline Establishment, and KPI Registry Activation - Q4 2030

38.5 Governance, Dependencies & Approval Pathway

Approval gate: SC-2030-01 (Steering Committee Q3 2030 agenda; 8-week notice submission required per Section 23 SC Charter calendar). Programme Office accountable for charter submission by end Q2 2030.

If SC-2030-01 approved: AMD-004 mobilisation proceeds Q3 2030; WS-A to WS-E launch Q4 2030.

If SC-2030-01 deferred: AMD-004 mobilisation delayed to Q4 2030; AMD-003 remains programme reference baseline; WS5 scoping deliverables archived for resubmission.

If SC-2030-01 rejected: AMD-003 constitutes final programme state; individual workstream extension proposals considered separately under standing SC agenda.

Key dependencies: PHE-WS5-06 (PDD draft output), SC-2030-01 formal approval, DPO clearance, GV2-P1 template compliance, Section 23 SC Charter calendar slot (Q3 2030).

38.6 Indicative Budget Framework

Total indicative budget: 5.2M THB across AMD-004 WS-A to WS-E (subject to SC-2030-01 ratification). Annual distribution: FY2031 (1.8M THB), FY2032 (1.9M THB), FY2033 (1.5M THB). Contingency reserve to be confirmed per GV2-P1 budget governance rules following SC approval.

WS-A Agent Capability Enhancement Phase 2: 1.0M THB (P1)

WS-B Technology Infrastructure Next Generation: 1.1M THB (P1)

WS-C Client Service Innovation Delivery: 1.2M THB (P1)

WS-D Data & Analytics Maturity Enhancement: 0.9M THB (P2)

WS-E Governance Continuity & Compliance: 1.0M THB (P0)

38.7 Programme Milestones

PDD-M1: SC-2030-01 Programme Approval - Q3 2030

PDD-M2: AMD-004 Programme Mobilisation Complete - Q3 2030

PDD-M3: WS-A to WS-E Workstream Kick-off and Baseline Established - Q4 2030

PDD-M4: Mid-Programme Governance Review (all WS-A to WS-D progress gated) - Q2 2032

PDD-M5: AMD-004 Programme Completion and Phase F Scoping Decision - Q2 2033

38.8 Budget Cost Breakdown Framework

The AMD-004 indicative budget of 5.2M THB is distributed across four cost categories for each workstream: Technology (infrastructure, licensing, platform build), Programme Management (project office, governance, documentation), Compliance (PDPA/GDPR, DPO review, audit, legal counsel), and Training (agent calibration, QA testing, staff capability). All figures are indicative and subject to SC-2030-01 ratification and detailed cost modelling during the Programme Mobilisation phase (PDD-005).

38.8.1 WS-A Cost Breakdown — Agent Capability Enhancement Phase 2 (1.0M THB)

Technology: 0.40M THB (40%) — LLM fine-tuning costs, model API licensing for up to 6 new agent profiles, integration API development, Group A-D capability testing environment

Programme Management: 0.20M THB (20%) — Scoping and specification, project office coordination, delivery documentation, agent specification review cycles

Compliance: 0.10M THB (10%) — Agent certification against GV2-P1 standards, SLA audit trails, S17 Group reclassification review

Training: 0.30M THB (30%) — Agent calibration and onboarding (up to 6 new profiles), QA testing, SLA validation against Group A-D benchmarks, supervisor training

38.8.2 WS-B Cost Breakdown — Technology Infrastructure Next Generation (1.1M THB)

Technology: 0.70M THB (64%) — Cloud infrastructure upgrade, vector-store v3 implementation (beyond INF-WS2-03), edge-compute hardware and licensing, LLM refresh platform costs

Programme Management: 0.20M THB (18%) — Vendor management under GV2-P3 policy, infrastructure project governance, technical documentation and runbooks

Compliance: 0.10M THB (9%) — Infrastructure security audit, penetration testing, cloud data residency compliance review (PDPA alignment)

Training: 0.10M THB (9%) — IT operations team training on new infrastructure, edge-compute operations, runbook walkthroughs and incident response drills

38.8.3 WS-C Cost Breakdown — Client Service Innovation Delivery (1.2M THB)

Technology: 0.40M THB (33%) — New service line platform build (up to 4 lines), client portal integration, API connectivity for Ember #23 and Shore #25 delivery workflows

Programme Management: 0.25M THB (21%) — Client coordination, delivery management, service line go-live planning, stakeholder communication

Compliance: 0.35M THB (29%) — PDPA/GDPR DPO review per service line (mandatory), data processing agreements, legal counsel for new client-facing services, ongoing compliance monitoring

Training: 0.20M THB (17%) — Ember #23 and Shore #25 service-specific training, client onboarding materials, internal helpdesk training for new service lines

38.8.4 WS-D Cost Breakdown — Data & Analytics Maturity Enhancement (0.9M THB)

Technology: 0.50M THB (56%) — Analytics data warehouse expansion to enterprise Level 3, predictive analytics model development, automated client reporting v2.0 platform build

Programme Management: 0.15M THB (17%) — Data governance framework, analytics project documentation, cross-workstream data integration coordination

Compliance: 0.10M THB (11%) — Data privacy impact assessment for analytics outputs, audit trails for automated SC reports (ANL-WS3-05 extension), PDPA data retention review

Training: 0.15M THB (17%) — Analytics platform end-user training (all 34 agents), report interpretation training for supervisors, client-facing analytics briefing materials

38.8.5 WS-E Cost Breakdown — Governance Continuity & Compliance (1.0M THB)

Technology: 0.10M THB (10%) — Governance policy management platform, compliance monitoring tooling, SC agenda and documentation systems

Programme Management: 0.30M THB (30%) — Programme governance office (concurrent with all WS-A to WS-D), SC Charter maintenance (Section 23), AMD-004 programme reporting to SC

Compliance: 0.50M THB (50%) — Dedicated DPO function establishment, PDPA/GDPR embedded compliance programme (full AMD-004 lifecycle), legal counsel retainer, annual external audit, regulatory change monitoring

Training: 0.10M THB (10%) — Governance training for Programme Office, compliance workshops for all workstream leads, DPO capability building

38.8.6 AMD-004 Cost Category Summary

Aggregated across all five workstreams (WS-A to WS-E), the 5.2M THB indicative envelope distributes across cost categories as follows. Technology represents the largest single category, reflecting the infrastructure and platform investment required for Phase E. Compliance is elevated compared to AMD-003 due to the PDPA/GDPR embedded programme running concurrently across all workstreams under WS-E.

Technology: 2.10M THB (40%) — Infrastructure, LLM, platform, licensing

Programme Management: 1.10M THB (21%) — Project office, governance, documentation

Compliance: 1.15M THB (22%) — PDPA/GDPR, DPO, legal, audit (elevated — WS-E concurrent)

Training: 0.85M THB (16%) — Calibration, QA, onboarding, capability building

TOTAL AMD-004 INDICATIVE: 5.20M THB — Subject to SC-2030-01 ratification (Q3 2030)

Note: Contingency reserve allocation to be confirmed per GV2-P1 budget governance rules following SC-2030-01 approval. Annual phasing: FY2031 (1.8M THB), FY2032 (1.9M THB), FY2033 (1.5M THB). Detailed cost modelling to be completed during PDD-005 Programme Mobilisation phase.

39. Pillar 1 — Biophilic Design Framework & WELL/LEED Compliance (GAP-01)

39.1  Overview

Section 39 establishes the Biophilic Design Framework and WELL/LEED Compliance Layer for DAPH Decor projects. This section closes GAP-01 identified in the SOP-GitHub Coverage Analysis (September 2026), where no corresponding implementation existed in the monolith-workspace repository for biophilic material certification, WELL v2 feature tracking, or LEED v4 credit management. This framework defines the standard operating procedures, agent responsibilities, and GitHub module specification (src/biophilic/) required to achieve World-Class biophilic design delivery.

Scope: All DAPH Decor interior design projects with contract value ≥ THB 2.0M or client specifications requiring WELL/LEED certification. Responsible Agents: Aria (Design Automation), Nova (SLA Group A — ≥95% accuracy threshold).

39.2  WELL v2 Feature Integration

DAPH Decor projects shall reference the following WELL v2 Building Standard feature categories as mandatory design inputs for luxury interior fit-out projects:

Air (A01-A09):  Low-VOC materials specification, ventilation rate compliance, air filtration standards for FF&E materials

Light (L01-L07):  Circadian lighting design, visual comfort, daylight access simulation in BIM — coordinated with BIM module (S20)

Mind (M01-M13):  Biophilic design elements, restorative spaces, nature connection features integrated in design brief (S3)

Materials (X01-X06):  Material transparency documentation — Red List avoidance, DECLARE label preferred, cross-referenced furniture-hardware-vault

Thermal (T01-T04):  Thermal comfort zone compliance per ASHRAE 55; seasonal variation documented in Sensory Commissioning (S41)

Sound (S01-S04):  Acoustic performance targets (WELL STC ratings), coordinated with Sensory Commissioning benchmark table (S41.2)

39.3  Biophilic Design Principles — 14 Patterns

Design briefs for qualifying projects shall incorporate a minimum of 6 of the 14 recognised biophilic design patterns:

• Pattern 01: Visual Connection with Nature — windows, green walls, water features, natural views

• Pattern 02: Non-Visual Connection with Nature — sensory stimuli (air, sound, temperature variation)

• Pattern 03: Non-Rhythmic Sensory Stimuli — spontaneous/unpredictable nature movements (water, fire, wind)

• Pattern 04: Thermal & Airflow Variability — slight variations in air temperature and airflow

• Pattern 05: Presence of Water — sight/sound/touch of water features in public areas

• Pattern 06: Dynamic & Diffuse Light — natural light variation, shadow movement across surfaces

• Pattern 07: Connection with Natural Systems — seasonal change, biological rhythms visible in design

• Pattern 08: Biomorphic Forms & Patterns — organic shapes, fibonacci patterns in surface design

• Pattern 09: Material Connection with Nature — stone, wood, bamboo, natural textiles, unprocessed textures

• Pattern 10: Complexity & Order — natural fractal geometry applied to millwork and ceiling patterns

• Pattern 11: Prospect — elevated vantage points, clear sightlines, spatial openness

• Pattern 12: Refuge — sheltered spaces for retreat, canopy elements, enveloping materials

• Pattern 13: Mystery — layered spaces, partial obscurement, discovery sequence in circulation

• Pattern 14: Awe — use of scale, natural phenomena, transcendent design moments

39.4  LEED v4 Credit Categories — Interior Design & Construction (ID+C)

For projects targeting LEED v4 ID+C certification (Hospitality, Commercial Interiors, or Retail), the following credit categories are applicable:

Location & Transportation (LT):  Access to public transit, bicycle facilities — typically preconditioned by building selection

Sustainable Sites (SS):  Construction activity pollution prevention, site assessment for interior renovation

Water Efficiency (WE):  Indoor water use reduction — low-flow fixtures mandatory for qualifying projects

Energy & Atmosphere (EA):  Lighting power density, HVAC coordination with building systems, energy sub-metering

Materials & Resources (MR):  Building product disclosure (EPD), material ingredient reporting, waste management — cross-ref furniture-hardware-vault

Indoor Environmental Quality (IEQ):  Low-emitting materials (adhesives, sealants, flooring, composite wood), acoustic performance, lighting control

Innovation (IN):  Innovative design strategies beyond LEED baseline — biophilic design earns IN credit

39.5  Biophilic & WELL/LEED Implementation Checklist

BIO-CHK-01:  Design brief includes minimum 6 biophilic patterns documented — completed by Aria at Design Phase (S3)

BIO-CHK-02:  Material specification cross-referenced against WELL X01-X06 material transparency requirements

BIO-CHK-03:  furniture-hardware-vault entries tagged with WELL/LEED compliance level (BIO-01 / BIO-02 / BIO-03)

BIO-CHK-04:  LEED scorecard populated at design freeze (Gate 2 — see S40) with target credit count confirmed

BIO-CHK-05:  VOC testing specification included in material procurement brief for finishes and adhesives

BIO-CHK-06:  Sensory commissioning benchmarks (S41) aligned with WELL Air and Sound feature targets

BIO-CHK-07:  Post-occupancy WELL feature compliance verified at 6-month POE (S42)

39.6  Agent Responsibilities

Aria (Design Automation):  Generates biophilic pattern specification, WELL material matrix, LEED scorecard at design stage

Nova (Compliance):  Validates WELL/LEED documentation completeness, issues compliance flag if BIO-CHK checklist incomplete

Rex (Vendor/Procurement):  Ensures furniture-hardware-vault suppliers maintain WELL/LEED material certification on file

Pulse (Analytics):  Tracks biophilic pattern compliance rate per project; quarterly WELL/LEED scorecard report to SC

39.7  GitHub Module Specification: src/biophilic/

AMD-004 WS-A shall commission the development of src/biophilic/ module with the following sub-modules:

• src/biophilic/well-checklist/ — WELL v2 feature tracking, project-level compliance status

• src/biophilic/pattern-matrix/ — 14-pattern selection interface, design brief integration

• src/biophilic/leed-scorecard/ — LEED ID+C credit tracking, target vs actual scoring

• src/biophilic/material-tagger/ — furniture-hardware-vault WELL/LEED tag management

• src/biophilic/compliance-report/ — automated WELL/LEED progress report generator

39.8  S39 Milestones

S39-M1:  Biophilic Design SOP published and incorporated in designer onboarding (Q1 2031)

S39-M2:  furniture-hardware-vault fully tagged with WELL/LEED compliance levels (Q2 2031)

S39-M3:  src/biophilic/ module development complete and integrated with src/designer/ (Q3 2031)

S39-M4:  First WELL-certified DAPH Decor project completed and submitted to SC (Q4 2031)

40. Pillar 2 — Design Freeze Gate System (GAP-02)

40.1  Overview

Section 40 establishes the Design Freeze Gate System for DAPH Decor, closing GAP-02 identified in the SOP-GitHub Coverage Analysis. The src/gate/ module in monolith-workspace contains rule engine scaffolding (builders, compute, rules, ui, utils) but lacks a formal Design Freeze workflow with sequential client approval chains, milestone locks, and freeze-violation alerts. This section defines the four-gate framework, approval authority matrix, violation protocol, and GitHub extension specification for src/gate/.

Scope: All DAPH Decor projects from design concept through manufacturing release. Responsible Agents: Kelly (Project & Operations Coordinator, Group A ≥95%), Atlas (QC Gate Monitoring, Group C ≥94%).

40.2  Design Freeze Gate Framework

The Design Freeze Gate System comprises four sequential gates. No gate may be bypassed without SC Programme Director authorisation.

Gate 0 — Concept Lock (G0):  Design concept confirmed with client; mood board, space planning, material palette approved. Trigger: signed concept approval form. Agent: Aria generates; Kelly tracks.

Gate 1 — Schematic Design Freeze (G1):  Floor plans, elevations, and 3D visualisations frozen. All biophilic patterns (S39) confirmed. Client sign-off required within 5 business days. Agent: Compass (Design PM).

Gate 2 — Design Development Freeze (G2):  Detailed drawings, material specifications, FF&E schedule, LEED scorecard (S39.4) confirmed. All furniture-hardware-vault items specified. No substitution post-G2 without Change Request (CR). Agent: Kelly + Atlas.

Gate 3 — Construction Document Release (G3):  Final working drawings released to factory/CNC. Triggers AMD-004 manufacturing pipeline (src/cnc/). Irreversible without formal CR + SC notification. Agent: Blaze (D2M Release).

40.3  Approval Authority Matrix

Each gate requires the following approvals before lock:

G0 Approvers:  Lead Designer + Client Representative (mandatory)

G1 Approvers:  Design Director + Client Representative + Project Manager

G2 Approvers:  Design Director + Procurement Manager + Client Representative + Quality Assurance (Atlas)

G3 Approvers:  Programme Director + Factory Manager + Client Representative — SC notification required within 24 hours

40.4  Freeze Violation Protocol

A Design Freeze Violation (DFV) is triggered when any design element is modified post-gate-lock without an approved Change Request.

DFV-Level 1 (Minor):  Material substitution, finish colour change — CR required within 24h; Kelly notified

DFV-Level 2 (Significant):  Dimension change, furniture substitution — CR + client re-approval + Gate re-validation within 48h

DFV-Level 3 (Critical):  Structural/layout change post-G2 — Full Gate 2 re-run, SC Programme Director notification, potential project delay escalation

Change Request (CR) Process:  CR-FORM-001 submitted via Field App or LINE OA; Atlas validates; Programme Director approves; factory notified

40.5  Agent Responsibilities

Kelly (Group A):  Overall gate timeline management, client communication, CR tracking, DFV escalation to SC

Compass (Group B):  Design stage scheduling, gate milestone tracking, designer deadline coordination

Atlas (Group C):  Gate 2 quality verification, post-G2 drawing compliance check, DFV detection

Blaze (Group A):  Gate 3 CNC release validation, manufacturing package completeness check before src/cnc/ trigger

40.6  GitHub Extension Specification: src/gate/

AMD-004 WS-A shall extend src/gate/ with the following components:

• src/gate/freeze-workflow/ — G0/G1/G2/G3 sequential state machine with client notification triggers

• src/gate/cr-management/ — Change Request CRUD, approval chain, version history

• src/gate/dfv-detector/ — Real-time DFV alerting integrated with src/workflow/approval/

• src/gate/milestone-lock/ — Immutable gate lock records in Supabase (audit trail for ISO 9001)

• src/gate/client-portal-integration/ — Client sign-off interface via supabase/functions/customer-design-view/

40.7  S40 Milestones

S40-M1:  Gate 0 and Gate 1 workflows live in src/gate/ — first client pilot project (Q1 2031)

S40-M2:  Gate 2 full approval chain with DFV alerting operational (Q2 2031)

S40-M3:  Gate 3 CNC release integration with src/cnc/ complete (Q3 2031)

S40-M4:  DFV rate KPI established — target ≤2 DFV-Level 2+ events per 10 projects (Q4 2031)

41. Pillar 6a — Sensory Commissioning Protocol (GAP-03)

41.1  Overview

Section 41 establishes the Sensory Commissioning Protocol, closing GAP-03. Sensory Commissioning is the systematic verification that a completed interior environment meets defined acoustic, lighting, thermal, air quality, and tactile benchmarks before client handover. This process is distinct from construction QC (S7) and operates post-installation as the final experiential acceptance test. The packages/field-app/ captures general QC; this section adds the sensory benchmark layer, commissioning test procedures, and acceptance sign-off framework.

Scope: All DAPH Decor projects. Phased commissioning required for projects > THB 3.0M. Responsible Agents: Shore (QC Field, Group B ≥93%), Hana (Environmental QC, Group B ≥93%).

41.2  Sensory Benchmark Standards

The following benchmark standards apply to all commissioned DAPH Decor spaces:

Acoustic (SB-A):  Background noise level ≤ NC-35 (living/dining) or ≤ NC-30 (bedroom/study). Reverberation time RT60 ≤ 0.5s for spaces ≤ 50m2. STC ≥ 45 for party walls.

Lighting (SB-L):  Task area illuminance: 300–500 lux (kitchen), 100–300 lux (living), 50–100 lux (bedroom ambient). Colour rendering CRI ≥ 90. CCT per design intent ±200K. UGR ≤ 19 for all direct luminaires.

Thermal (SB-T):  Operative temperature: 23–26°C (cooling season), 20–23°C (heating season). Radiant temperature asymmetry ≤ 5°C. Relative humidity: 40–60%.

Air Quality (SB-Q):  CO2 ≤ 1000 ppm in occupied spaces. TVOC ≤ 500 μg/m3 (new installation 30-day post-install). PM2.5 ≤ 12 μg/m3. Formaldehyde ≤ 0.1 ppm.

Tactile/Material (SB-M):  All finish surfaces free of sharp edges, delamination, micro-cracks visible under 50-lux spot check. Gap tolerance: joints ≤ 1.5mm for premium finishes.

41.3  Commissioning Test Procedures

SC-TEST-01 Acoustic Walk:  Shore agent conducts 15-minute acoustic walk. Test: clap test (RT60 estimation), background noise measurement (dB meter), door/window seal verification. Tools: Decibel X app + calibrated sound level meter.

SC-TEST-02 Lighting Scene Test:  All lighting scenes (day/evening/task) tested at design lux levels. CCT consistency verified across all fixtures. Dimmer range: 5–100% confirmed. Document: photo evidence with lux reading overlay.

SC-TEST-03 Thermal Equilibrium Check:  HVAC operated at design setpoints for minimum 2 hours pre-test. Three-zone temperature map taken: floor (0.1m), seated (1.1m), ceiling (1.7m). Results logged in Field App.

SC-TEST-04 Air Quality Baseline:  IAQ meter reading taken at 30 days post-installation. All readings logged. If TVOC > 500 μg/m3: mandatory ventilation flush protocol activated; re-test at 60 days.

SC-TEST-05 Tactile Finish Survey:  100% surface inspection by Shore agent. Defects logged via Field App QC capture (src/qc-anomaly/). All critical defects (Level 2+) resolved before Sensory Commissioning Sign-Off.

41.4  Sensory Commissioning Sign-Off Hierarchy

Level 1 — Agent Verified:  Shore/Hana completes all SC-TEST-01 to SC-TEST-05; results within benchmark. Agent sign-off in Field App.

Level 2 — Client Acceptance:  Client representative attends sensory walk (minimum 30 minutes). Client sign-off on SC-FORM-001.

Level 3 — Programme Director Release:  Programme Director confirms Sensory Commissioning complete — triggers final payment milestone and moves project to POE phase (S42).

41.5  Agent Responsibilities & GitHub Integration

Shore (Group B):  Leads all sensory commissioning tests; operates Field App SC-TEST suite; issues Level 1 verification

Hana (Group B):  Environmental monitoring (air quality, thermal); maintains IAQ baseline database; 30/60-day re-test scheduling

Field App Integration:  SC-TEST results captured in packages/field-app/; photos via supabase/functions/field-capture/; anomalies via src/qc-anomaly/

AMD-004 WS-B shall add src/sensory-commissioning/ module with: benchmark-config/, test-protocol/, sign-off-workflow/, and supabase table sensory_commissioning_records.

41.6  S41 Milestones

S41-M1:  SC-FORM-001 template deployed in Field App; Shore agent trained on all 5 test procedures (Q2 2031)

S41-M2:  src/sensory-commissioning/ module operational; first project sensory commissioning completed (Q3 2031)

S41-M3:  WELL Sound and Thermal feature compliance verified via Sensory Commissioning for WELL-target projects (Q4 2031)

S41-M4:  Sensory Commissioning pass rate KPI established — target ≥ 90% first-attempt pass (Q1 2032)

42. Pillar 6b — Post-Occupancy Evaluation (POE) System (GAP-04)

42.1  Overview

Section 42 establishes the Post-Occupancy Evaluation (POE) System, closing GAP-04. POE is the structured evaluation of a completed interior environment after occupancy to assess performance against design intent, client satisfaction, and WELL/LEED targets. DAPH Decor currently has src/core/telemetry/ for platform telemetry but no project-level POE survey engine, occupant satisfaction scoring, or delta analysis vs design intent. This section defines the POE schedule, evaluation framework, survey methodology, and GitHub module specification.

Scope: All DAPH Decor projects with contract value ≥ THB 1.5M. POE data informs DAPH design standards library. Responsible Agents: Pulse (Analytics, Group C ≥94%), Frame (Reporting, Group C ≥94%).

42.2  POE Schedule & Trigger Points

POE-30: 30-Day Quick Check:  Triggered automatically 30 days after Sensory Commissioning sign-off (S41). Focus: punch list resolution, client onboarding satisfaction, critical snag follow-up. Duration: 30 minutes. Method: Field App survey + phone call.

POE-90: 3-Month Assessment:  Trigger: 90 days post-handover. Focus: HVAC/lighting performance in real occupancy, material performance, maintenance issues. Duration: 60-minute site visit by Hana + short client survey (15 questions). Generates: POE-REPORT-90.

POE-180: 6-Month Performance Review:  Trigger: 180 days post-handover. Focus: occupant wellbeing, biophilic pattern effectiveness, WELL feature compliance re-check, energy performance. Duration: 90-minute site visit + full occupant survey (30 questions). Generates: POE-REPORT-180 submitted to SC.

POE-365: 12-Month Annual Evaluation:  Trigger: 365 days post-handover. Focus: material durability, seasonal performance variation, brand satisfaction, referral likelihood. Duration: full evaluation + photography update. Generates: POE-REPORT-365 — benchmark database entry.

42.3  Evaluation Framework — 6 Domains

Domain 1: Technical Performance:  HVAC, lighting, acoustic performance vs SB benchmarks (S41.2). Objective measurements re-taken.

Domain 2: Occupant Wellbeing:  Self-reported comfort, stress reduction, biophilic pattern perception, nature connection score.

Domain 3: Material & Finish Durability:  Visual inspection of all surfaces, hardware, joinery. Defect rate vs expected warranty period.

Domain 4: Functional Satisfaction:  Space utilisation, storage adequacy, circulation flow, furniture ergonomics.

Domain 5: WELL/LEED Compliance:  Re-verification of WELL features per S39. LEED post-occupancy credits confirmed. Biophilic pattern retention score.

Domain 6: Client & Brand Satisfaction:  NPS score, repeat business likelihood, referral willingness, DAPH brand perception.

42.4  POE Survey Framework

Standard POE surveys are administered digitally via LINE OA or client portal (supabase/functions/customer-design-view/):

• POE-30 Survey: 8 questions — satisfaction with handover, snagging resolution, first impressions (1–5 Likert scale)

• POE-90 Survey: 15 questions — 6 technical, 5 functional, 4 satisfaction questions

• POE-180 Survey: 30 questions — all 6 domains; includes open text for testimonials; NPS measured

• POE-365 Survey: 30 questions + site photography — annual full evaluation; fed into DAPH design standards update

POE survey responses are analysed by Pulse agent and reported to Frame agent for SC dashboard integration (S36 analytics extension).

42.5  Delta Analysis — Design Intent vs Actual Performance

Frame agent generates a Design Intent vs Actual Performance delta report at POE-180 and POE-365:

DI-01 Biophilic Pattern Retention:  % of 14 patterns still perceived by occupants vs designed. Target ≥ 80% at POE-180.

DI-02 Lighting Performance Delta:  Measured lux vs designed lux ±15% tolerance. CCT drift flagged if > 200K from commissioning baseline.

DI-03 Acoustic Performance Delta:  RT60 and NC level vs SC-TEST-01 baseline. Furnishing changes may alter acoustics.

DI-04 Client Satisfaction Delta:  NPS at POE-180 vs POE-30 initial satisfaction. Target: NPS ≥ +50 at POE-180.

DI-05 Material Durability Score:  Defect rate per 100 linear metres of joinery/surface. Target ≤ 3 defects at 12 months.

42.6  GitHub Module Specification: src/poe/

AMD-004 WS-B shall commission src/poe/ module with:

• src/poe/schedule/ — automated POE trigger scheduling (30/90/180/365-day) linked to project handover date

• src/poe/survey-engine/ — digital survey builder, LINE OA distribution, response collection

• src/poe/delta-analysis/ — Design Intent vs Actual algorithm, delta report generator

• src/poe/benchmarks/ — rolling DAPH design standards database fed by POE-365 data

• supabase table poe_evaluations — stores all POE records, linked to project_id

42.7  S42 Milestones

S42-M1:  POE-30 quick check survey deployed via LINE OA for all active projects (Q2 2031)

S42-M2:  src/poe/ module operational; POE-90 and POE-180 assessments running on pilot projects (Q3 2031)

S42-M3:  First POE-365 annual evaluation completed; delta analysis submitted to SC (Q4 2031)

S42-M4:  DAPH design standards database updated with POE benchmark data — minimum 10 project entries (Q2 2032)

43. SC Governance Module & Programme Charter Registry (GAP-07)

43.1  Overview

Section 43 establishes the Steering Committee Governance Module and Programme Charter Registry, closing GAP-07. The SOP-GitHub Coverage Analysis confirmed that Sections S23, S28, S32, and S38 — covering SC governance, AMD programme lifecycle, decision rights, and PDD management — exist entirely in DOCX form with no corresponding code implementation. This section defines the governance data model, Supabase schema, and agent integration required to operationalise SC governance within the IIMOS Manufacturing OS.

Scope: All AMD programme governance activities from AMD-004 onwards. Responsible Agents: Core (Programme Director AI, Group D ≥97%), Guardian (Governance Compliance, Group D ≥97%), Nexus (Integration, Group D ≥97%).

43.2  Steering Committee Charter Registry v3.0

The SC Charter Registry is the authoritative record of all Steering Committee decisions, resolutions, and mandate changes. It supersedes the manual DOCX-based records maintained in S23 and S34.

Registry Record Types:  SC-RESOLUTION (numbered SC-YYYY-NN), AMD-MANDATE (programme scope decisions), POLICY-RATIFICATION (governance policy approvals), ESCALATION-RECORD (DFV-Level 3, SLA breach, P0 incidents)

Immutability:  All SC resolutions are append-only in Supabase. No deletion or modification post-SC-signature. Audit trail maintained per ISO 9001 clause 7.5 (documented information).

Numbering Convention:  SC-[YEAR]-[NN] — e.g. SC-2030-01 (AMD-004 ratification). Sequential within calendar year. Cross-referenced in all SOP sections citing SC decisions.

Access Control:  SC records readable by all agents; writable only by Core and Guardian agents (Group D clearance). src/iam/ enforces role.

43.3  Decision Rights Framework v3.0

The following decision rights matrix governs AMD programme activities post-AMD-004 ratification:

D1 — Programme Director:  Approve Gate 3 releases, authorize DFV-Level 3 CRs, ratify WELL/LEED scope changes, approve POE-365 benchmark database updates

D2 — Steering Committee:  Ratify AMD programme amendments, approve annual programme reviews (APR), authorize new workstream commissioning, approve policy documents GV2-P1 through GV2-P5

D3 — Design Director:  Approve Gate 0/1/2 design decisions, sign off biophilic pattern matrix (S39), validate LEED scorecard at G2

D4 — Agent (Autonomous):  Core/Guardian agents may autonomously approve Level 1 decisions within pre-authorised parameters: routine SLA breach notifications, POE scheduling, material vault tag updates

43.4  AMD Programme Lifecycle State Machine

Each AMD programme follows a defined lifecycle state machine, implemented in Supabase as programme_state enum:

State: PROPOSED:  AMD programme proposed by APR review; PDD template initiated (S38 framework)

State: RATIFIED:  SC ratification resolution issued (SC-YYYY-NN); workstreams activated

State: IN_PROGRESS:  Workstreams WS-A through WS-E executing; quarterly SC reports generated by Core agent

State: REVIEW:  Annual Programme Review (APR) activated; scope extension or closure decision pending

State: COMPLETED:  All workstream milestones delivered; SC formal completion declaration issued; next AMD programme triggered

State: SUPERSEDED:  Programme documents superseded by successor AMD; archived in Supabase with read-only access

43.5  SC Agenda & Resolution Store — Supabase Schema

AMD-004 WS-A shall create the following Supabase tables for SC governance:

• sc_resolutions (id, resolution_code, amd_programme, title, decision_text, ratified_by, ratified_at, related_sections)

• amd_programmes (id, code, name, state, ratification_sc, start_date, target_completion, workstreams JSONB)

• governance_policies (id, code, title, version, amd_programme, status, approved_at, superseded_at, doc_url)

• sc_agenda_items (id, meeting_date, item_type, title, presenter_agent, resolution_id, outcome)

• programme_milestones (id, amd_programme, workstream, milestone_code, title, target_date, status, evidence_url)

43.6  AMD-004 Governance Activation Checklist

GOV-AMD4-01:  Supabase sc_resolutions table created; SC-2030-01 AMD-004 ratification record inserted

GOV-AMD4-02:  amd_programmes table created; AMD-004 record in RATIFIED state; WS-A through WS-E workstreams populated

GOV-AMD4-03:  Core agent configured with SC governance write permissions in src/iam/

GOV-AMD4-04:  Guardian agent automated quarterly SC report generator linked to programme_milestones table

GOV-AMD4-05:  LINE OA SC notification channel configured for resolution alerts (supabase/functions/line-outbound-sender/)

GOV-AMD4-06:  DOCX SOP sections S23, S28, S32, S38 cross-referenced with Supabase governance records as authoritative source

43.7  S43 Milestones

S43-M1:  Supabase governance schema deployed; SC-2030-01 AMD-004 record live (Q3 2030 — AMD-004 ratification)

S43-M2:  Core and Guardian agents configured with governance write access; first automated SC quarterly report (Q4 2030)

S43-M3:  All historical SC resolutions (SC-2025 through SC-2030) migrated from DOCX to Supabase sc_resolutions table (Q1 2031)

S43-M4:  SC Governance Module fully operational — DOCX SOP governance sections become read-only references to Supabase system of record (Q2 2031)

44. 28-Agent Governance Code Implementation Guide & Unified Gap Resolution Framework (GAP-05, GAP-08)

44.1  Overview

Section 44 consolidates the technical implementation guide for the 28-Agent Governance Layer in code (GAP-05) and the AMD-004 Unified Gap Resolution Framework (GAP-08). The SOP-GitHub Coverage Analysis identified 15 gaps across three severity levels. This section provides the authoritative migration path from DOCX-governed policy to code-enforced governance, beginning with AMD-004 WS-A (Q3 2030) and completing by AMD-004 WS-E (Q2 2033).

Responsible Agents: Core (Programme Director, Group D ≥97%), Nexus (Integration, Group D ≥97%), Vega (Technical Architecture, Group D ≥97%), Ledger (Audit/Compliance, Group D ≥97%).

44.2  28-Agent SLA Group Configuration in src/workflow/sla/

The 28-agent SLA Group A–D threshold table (S17) shall be migrated from DOCX to a configuration file in src/workflow/sla/agent-config.ts with the following structure:

Group A (≥95% accuracy):  Kelly, Signal, Aria, Blaze, Nova — real-time SLA sweep via supabase/functions/sla-sweep-scheduler/

Group B (≥93% accuracy):  Compass, Remy, Scout, Finn, Hana, Ember, Shore, Draft — daily SLA batch review

Group C (≥94% accuracy):  Atlas, Bo, Forge, Leo, Ops, Stone, Pulse, Frame — weekly SLA aggregate report

Group D (≥97% accuracy):  Core, Nexus, Rex, Guardian, Talent, Vega, Ledger — continuous monitoring; breach triggers immediate SC notification

SLA breach thresholds shall trigger escalation via supabase/functions/notify-overdue/ with severity mapping: Group D breach → Programme Director + SC notification; Group A breach → Design Director notification; Group B/C breach → workstream lead notification.

44.3  Per-Agent KPI Baseline Configuration

Each of the 28 agents shall have a KPI baseline record in Supabase table agent_kpi_baselines with fields:

• agent_id, agent_name, sla_group, accuracy_threshold, response_time_p95_ms, tasks_per_day_target

• quality_score_min, handoff_success_rate_min, client_satisfaction_nps_min

• current_period_score, baseline_date, last_review_date, next_review_date

KPI baselines are reviewed quarterly by Pulse (analytics) and Ledger (audit). Deviations of > 5% from baseline for two consecutive quarters trigger Agent Lifecycle Review (S21 protocol).

44.4  Gap Resolution Registry — All 15 Gaps

The following table summarises the complete 15-gap resolution plan by AMD-004 workstream:

GAP-01 Biophilic/WELL  [HIGH]:  WS-A: S39 SOP published. WS-B: src/biophilic/ module built. Target: Q3 2031

GAP-02 Design Freeze Gate  [HIGH]:  WS-A: src/gate/ extension. WS-B: full client workflow. Target: Q3 2031

GAP-03 Sensory Commissioning  [HIGH]:  WS-B: src/sensory-commissioning/ module. Target: Q3 2031

GAP-04 POE System  [HIGH]:  WS-B: src/poe/ module. Target: Q3 2031

GAP-05 28-Agent Governance Code  [HIGH]:  WS-A: agent-config.ts + agent_kpi_baselines. Target: Q4 2030

GAP-06 ISO 9001/RIBA Audit Trail  [HIGH]:  WS-C: src/workflow/audit/ extension. Target: Q2 2032

GAP-07 SC Governance Module  [HIGH]:  WS-A: S43 + Supabase schema. Target: Q4 2030

GAP-08 AMD-004 Programme Tracker  [HIGH]:  WS-A: amd_programmes table + Core agent. Target: Q4 2030

GAP-09 Mock-up Approval Workflow  [MEDIUM]:  WS-B: src/workflow/approval/ extension. Target: Q1 2032

GAP-10 Unified KPI Dashboard  [MEDIUM]:  WS-C: dashboard/ integration layer. Target: Q2 2032

GAP-11 Emergency Escalation Protocol  [MEDIUM]:  WS-C: severity matrix + escalation chain. Target: Q2 2032

GAP-12 Governance Amendment Tracking  [MEDIUM]:  WS-B: governance_policies table. Target: Q1 2032

GAP-13 AI Ethics Audit Module  [LOW]:  WS-D: bias monitoring + ethical log. Target: Q3 2032

GAP-14 Agent Decommissioning Workflow  [LOW]:  WS-D: lifecycle retire state. Target: Q3 2032

GAP-15 PDPA DSAR Workflow  [LOW]:  WS-D: src/iam/ DSAR extension. Target: Q4 2032

44.5  AMD-004 Unified Gap Resolution Roadmap

Phase 1 — WS-A (Q3–Q4 2030):  Bridge DOCX → Code: GAP-05 (SLA config), GAP-07 (SC governance schema), GAP-08 (AMD tracker), GAP-02 initial (Gate scaffolding)

Phase 2 — WS-B (FY2031):  New module development: GAP-01 (biophilic), GAP-03 (sensory), GAP-04 (POE), GAP-02 complete (Gate workflow), GAP-09 (mock-up), GAP-12 (amendment tracking)

Phase 3 — WS-C/D (FY2032):  Integration & compliance: GAP-06 (ISO 9001 audit), GAP-10 (unified dashboard), GAP-11 (emergency protocol), GAP-13/14/15 (ethics, decommission, PDPA)

Phase 4 — WS-E (Q1–Q2 2033):  Validation, stress testing, and World-Class certification against RIBA POW + WELL + ISO 9001. Target: 0 HIGH gaps remaining.

44.6  S44 Milestones

S44-M1:  agent-config.ts with 28-agent SLA Group configuration committed to monolith-workspace main branch (Q3 2030)

S44-M2:  Supabase agent_kpi_baselines table populated; KPI baseline review cycle active (Q4 2030)

S44-M3:  All 8 HIGH severity gaps resolved — verified by Gap Resolution Registry audit (Q4 2031)

S44-M4:  All 15 gaps resolved — DAPH Decor World-Class Framework certification audit submitted to SC (Q2 2033)

S44-M5:  S39–S44 accepted and merged into monolith_project_summary_v3.0 as AMD-004 foundations (Q3 2030)

45. AMD-004 WS-B — Technology Infrastructure Next Generation (GAP-05: AI Creative Engine)

45.1  Workstream Overview

Section 45 defines the AMD-004 Workstream B (WS-B) implementation specification for Technology Infrastructure Next Generation. WS-B is the technical foundation workstream within the AMD-004 programme (฿5.2M, FY2031–FY2033) responsible for cloud infrastructure modernisation, API gateway consolidation, and the deployment of AI-powered creative tooling. Critically, this section closes GAP-05 (AI Creative Engine) — identified in the SOP-GitHub Coverage Analysis as a HIGH-priority missing module with no corresponding implementation in monolith-workspace. WS-B is the parent workstream for all infrastructure-dependent capabilities in Phase 2 of the Gap Resolution Roadmap.

Budget Allocation: ฿1.1M (AMD-004 WS-B). Timeline: Q1–Q3 2031 (Phase 2 Roadmap). Responsible SC Decision: SC-2030-01 (authorises AMD-004 programme start). SLA Group Assignments: Group C agents (Atlas, Bo, Forge, Leo, Ops, Stone, Pulse, Frame) — ≥94% SLA threshold.

45.2  Technology Infrastructure Objectives

WS-B targets four infrastructure modernisation layers that underpin all Phase 2 and Phase 3 gap-resolution modules:

Cloud Infrastructure (INFRA-WS-B-01):  Migrate monolith-workspace compute from on-premise VM to managed Kubernetes cluster (GKE or AKS). Target: 99.9% uptime SLA, auto-scaling 28-agent pod deployment, zero-downtime rolling updates. Dependencies: src/core/supabase/ (data persistence layer), src/core/telemetry/ (observability).

API Gateway Consolidation (INFRA-WS-B-02):  Unify disparate REST/gRPC endpoints across src/agents/ into a single Kong or AWS API Gateway. Enforce JWT authentication, rate limiting (100 req/s per agent), and request tracing. Enables Cross-Pillar Event Bus (GAP-06, S46) to route inter-agent events reliably.

Data Pipeline Modernisation (INFRA-WS-B-03):  Upgrade src/data-pipeline/ to Apache Kafka event streaming with schema registry. Implement CDC (Change Data Capture) for real-time Supabase → Analytics sync. Provides the data substrate for Real-time KPI Dashboard (GAP-08, S47).

Security & Compliance Layer (INFRA-WS-B-04):  Deploy Zero-Trust network policy (mTLS between pods), Vault-managed secrets rotation, SOC2-Type-II audit logging. PDPA/GDPR data residency enforcement at infrastructure level. Prerequisite for PDPA Consent workflow (GAP-10) and Contractor Portal (GAP-11).

45.3  GAP-05 AI Creative Engine — Module Specification

The AI Creative Engine (GAP-05) is a HIGH-priority missing module closing the absence of generative AI tooling for interior design creative production in DAPH Decor projects. The engine integrates large multimodal models with the existing Aria (Design Automation) and Blaze (Visual Intelligence) agents to deliver AI-assisted concept generation, material curation, and spatial visualisation — elevating DAPH Decor to World-Class AI-augmented design delivery standard.

Target repository path: src/creative-engine/ (new module). Integration points: src/agents/aria/, src/agents/blaze/, src/agents/nova/, src/design-vault/ (material library).

AIE-001 Concept Generation API:  REST endpoint POST /creative/concept — accepts project brief JSON (client profile, style references, budget tier, pillar selections) → returns 3–5 design concept directions with mood board imagery (DALL-E 3 / Stable Diffusion XL backend), design narrative text, and WELL/LEED compatibility score per concept.

AIE-002 Material & Texture Synthesis:  REST endpoint POST /creative/material — given existing FF&E spec (furniture-hardware-vault entries) generates complementary texture options, colour palette expansions, and biophilic material suggestions. Output validated against Red List (GAP-01/S39.2 Material Transparency). Agents: Nova, Aria.

AIE-003 Spatial Planning Assist:  Integration with src/bim/ (BIM module S20) — AI overlay on floor plan data to generate alternative furniture arrangement proposals ranked by spatial efficiency, flow score, and client preference model. Uses occupancy simulation heuristics from POE historical data (GAP-04/S42).

AIE-004 Client Brief Interpreter:  NLP pipeline (GPT-4o) — parses unstructured client brief documents into structured design parameters (style vectors, budget constraints, timeline, special requirements). Output feeds directly into Design Brief Module (S3) and Design Freeze Gate checklist (GAP-02/S40).

AIE-005 Creative Iteration Engine:  Version-controlled creative workflow: each concept iteration logged with delta-tracking, client approval status, and revision rationale. Integrates with Design Freeze Gate (S40.3 DFG-WS-01) to prevent unauthorised design changes post-freeze.

45.4  Implementation Architecture

The AI Creative Engine operates across a 3-tier deployment model within the WS-B infrastructure:

• Tier 1 — AI Inference Layer: Managed model endpoints (Azure OpenAI / GCP Vertex AI). Latency target: ≤3s for concept generation, ≤1s for material synthesis. Auto-scaled GPU pods.

• Tier 2 — Orchestration Layer: LangChain orchestration within Aria agent pod. Manages prompt engineering, context injection (project brief + design vault data), and output validation pipeline.

• Tier 3 — Integration Layer: Supabase persistence for creative artefacts, webhook triggers to notify Scout (Project Tracking) and Compass (Coordination) on concept approvals. Client-facing output delivered via encrypted share links through Shore (Client Relations) agent.

45.5  Delivery Checklist (TECH-WS-B-01–06)

TECH-WS-B-01:  Cloud infrastructure migration to Kubernetes — Forge agent lead, Atlas monitoring. Target: Q1 2031.

TECH-WS-B-02:  API Gateway consolidation (Kong) deployed, all 28 agent endpoints registered. Target: Q1 2031.

TECH-WS-B-03:  Kafka data pipeline deployed; CDC sync Supabase → Analytics verified end-to-end. Target: Q2 2031.

TECH-WS-B-04:  AI Creative Engine src/creative-engine/ v1.0 — AIE-001 through AIE-005 all endpoints tested. Target: Q2 2031.

TECH-WS-B-05:  Security layer: mTLS policy, Vault secrets, SOC2 logging — audit trail active across all pods. Target: Q2 2031.

TECH-WS-B-06:  WS-B User Acceptance Testing: Aria + Blaze + Nova creative workflow E2E test on 3 live projects. Target: Q3 2031.

45.6  Governance, Dependencies & Agent Assignments

WS-B is governed under SC Decision SC-2030-01 (AMD-004 programme authorisation). Programme Director: Core agent (Group D, ≥97% SLA). Infrastructure Lead: Forge (Group C, ≥94%). AI Engine Lead: Aria (Group A, ≥95%). Security Lead: Rex (Group D, ≥97%).

Dependencies: S38 (AMD-004 PDD — master programme budget ฿5.2M), S44 (GitHub Integration Roadmap — Kubernetes migration prerequisite), S40 (Design Freeze Gate — AIE-005 integration), S42 (POE Framework — AIE-003 occupancy data), S20 (BIM — AIE-003 floor plan data).

45.7  Milestones (WS-B-M1–M4)

WS-B-M1 (Q1 2031):  Infrastructure migration complete — Kubernetes cluster live, API Gateway deployed, monitoring active.

WS-B-M2 (Q2 2031):  AI Creative Engine v1.0 deployed — AIE-001 to AIE-005 endpoints operational in staging.

WS-B-M3 (Q2 2031):  Security & compliance layer certified — SOC2 audit complete, Zero-Trust policy enforced.

WS-B-M4 (Q3 2031):  WS-B UAT passed — 3 live project E2E creative workflow validated, GAP-05 formally closed.

46. AMD-004 WS-C — Client Service Innovation Delivery (GAP-06: Cross-Pillar Event Bus)

46.1  Workstream Overview

Section 46 defines the AMD-004 Workstream C (WS-C) implementation specification for Client Service Innovation Delivery. WS-C is the client-facing innovation workstream within the AMD-004 programme, responsible for elevating the DAPH Decor client experience through real-time collaboration tools, personalised service delivery, and seamless cross-pillar project orchestration. This section simultaneously closes GAP-06 (Cross-Pillar Event Bus) — a HIGH-priority missing integration module identified in the SOP-GitHub Coverage Analysis. The Cross-Pillar Event Bus is the foundational architectural component that enables real-time state synchronisation across all six design pillars and 28 AI agents.

Budget Allocation: ฿1.2M (AMD-004 WS-C — largest workstream by value due to client experience complexity). Timeline: Q2–Q4 2031 (Phase 2 Roadmap). SC Decision: SC-2030-01. Primary Agents: Kelly (SLA Group A, ≥95%), Shore (Group B, ≥93%), Compass (Group B, ≥93%), Signal (Group A, ≥95%).

46.2  Client Service Innovation Objectives

WS-C targets four client experience innovation areas, each supported by existing or new monolith-workspace modules:

Real-time Client Collaboration Portal (SVC-WS-C-01):  Web-based secure portal (src/client-portal/ — new module) giving clients live project status, design concept previews, approval workflows, and direct messaging with project team agents. Integrates with Shore (Client Relations), Signal (Communications), and Remy (Reporting) agents.

Personalised Service Engine (SVC-WS-C-02):  Client preference model built from historical project data (src/data-pipeline/ + analytics). Proactively recommends design directions, material options, and schedule adjustments. Feeds AI Creative Engine (GAP-05/S45.3 AIE-004 Client Brief Interpreter).

Digital Twin Client Preview (SVC-WS-C-03):  VR/AR-ready 3D room preview generated from BIM data (S20) + AI texturing (AIE-002). Client-accessible via web-based 3D viewer (Three.js) without specialist hardware requirement. Preview versions locked at Design Freeze Gate (GAP-02/S40.3 DFG-WS-01) to prevent post-freeze scope creep.

Post-Project Client Intelligence (SVC-WS-C-04):  Automated post-completion satisfaction survey (Scout agent) feeding into POE database (GAP-04/S42). NPS scoring, WELL/LEED satisfaction tracking, referral probability scoring. Quarterly client portfolio health reports via Remy (Reporting) agent.

46.3  GAP-06 Cross-Pillar Event Bus — Architecture Specification

The Cross-Pillar Event Bus (GAP-06) resolves the critical absence of a unified event-driven communication layer between the six design pillars (Conceptual Design, Spatial Planning, Material Selection, Technical Documentation, Procurement & Delivery, Commissioning & Handover). Without this bus, agents in different pillars operate in siloed HTTP polling loops, causing latency, missed state transitions, and manual handover errors between pillar stages.

Target repository path: src/event-bus/ (new module). Technology: Apache Kafka (provisioned in WS-B/S45.2 INFRA-WS-B-03) with dedicated topics per pillar pair. All 28 agents subscribe as consumers; pillar-lead agents (Kelly, Compass, Aria, Atlas, Draft, Signal) also act as topic producers.

EVT-001 Pillar State Change Events:  Standardised CloudEvents schema (v1.0) for design state transitions: CONCEPT_APPROVED, SPATIAL_LOCKED, MATERIAL_SPECIFIED, TECH_DOC_ISSUED, PO_RAISED, COMMISSIONING_STARTED, HANDOVER_COMPLETE. Each event carries: project_id, pillar_id, agent_id, timestamp, payload_json, sla_deadline.

EVT-002 Cross-Pillar Trigger Rules:  Rule engine (Drools / custom Python evaluator in src/event-bus/rules/) — defines conditional triggers: e.g., MATERIAL_SPECIFIED → auto-notify Procurement (Finn agent); CONCEPT_APPROVED + SPATIAL_LOCKED → trigger Design Freeze Gate evaluation (S40.3 DFG-WS-01); COMMISSIONING_STARTED → activate Sensory Commissioning Protocol (GAP-03/S41).

EVT-003 Dead Letter Queue & Replay:  Failed event handling: DLQ with 3-retry policy + exponential backoff. Event replay capability (replay from timestamp) for project timeline reconstruction and audit trail generation (SC governance reports via Nexus agent).

EVT-004 Real-time Dashboard Integration:  Event stream → WebSocket bridge → Real-time KPI Dashboard (GAP-08/S47). Pillar transition velocity KPIs: avg time per pillar stage, bottleneck identification, SLA breach prediction (Pulse agent alerts at 80% SLA consumption).

EVT-005 Agent Coordination Protocol:  Standardised agent-to-agent handover packets via event bus. Replaces current direct HTTP calls between agent pods — improves resilience and enables async processing for non-blocking workflows (critical for 28-agent parallel execution).

46.4  Implementation Architecture

The Cross-Pillar Event Bus integrates three operational layers:

• Producer Layer: Pillar-lead agents emit structured events to dedicated Kafka topics (topic naming: monolith.pillar.{pillar_id}.{event_type}). Kelly manages Pillar 1–2, Compass manages Pillar 3–4, Atlas manages Pillar 5–6.

• Consumer Layer: All 28 agents subscribe to relevant topics via consumer groups (group_id: monolith.agents.{agent_id}). Offset management ensures exactly-once delivery for financial and approval events; at-least-once for informational events.

• Observability Layer: Kafka topic lag monitoring via Prometheus + Grafana dashboards (integrated with WS-B telemetry infrastructure). Alert thresholds: consumer lag > 100 msgs triggers Pulse agent notification to Forge (Infrastructure).

46.5  Delivery Checklist (SVC-WS-C-01–06)

SVC-WS-C-01:  Cross-Pillar Event Bus src/event-bus/ v1.0 — EVT-001 schema registered, all 6 pillar topics created. Target: Q2 2031.

SVC-WS-C-02:  EVT-002 trigger rules deployed — 8 cross-pillar automation rules live, tested on 2 pilot projects. Target: Q3 2031.

SVC-WS-C-03:  Client portal src/client-portal/ v1.0 — real-time project status, concept preview, approval workflow. Target: Q3 2031.

SVC-WS-C-04:  Digital twin preview — Three.js web viewer integrated with BIM (S20) + AIE-002 texturing. Target: Q3 2031.

SVC-WS-C-05:  Post-project intelligence — automated POE survey + NPS scoring + quarterly reports active. Target: Q4 2031.

SVC-WS-C-06:  WS-C UAT: 3 live projects E2E tested — event bus, portal, preview, intelligence reporting validated. Target: Q4 2031.

46.6  Governance, Dependencies & Agent Assignments

WS-C Programme Director: Core (Group D, ≥97%). Client Experience Lead: Kelly (Group A, ≥95%). Event Bus Lead: Ops (Group C, ≥94%). Client Portal Lead: Shore (Group B, ≥93%). Data Intelligence Lead: Atlas (Group C, ≥94%).

Dependencies: S45 WS-B (Kafka infrastructure prerequisite for EVT-001–005), S40 (Design Freeze Gate — EVT-002 trigger integration), S41 (Sensory Commissioning — EVT-002 trigger), S42 (POE — SVC-WS-C-04 post-project intelligence), S45 AIE-002 (digital twin texturing), S20 (BIM — digital twin floor plan data). Client portal requires PDPA compliance review (S15 + GAP-10).

46.7  Milestones (WS-C-M1–M4)

WS-C-M1 (Q2 2031):  Cross-Pillar Event Bus live — all pillar topics, EVT-001 schema, and consumer groups active.

WS-C-M2 (Q3 2031):  Client portal v1.0 launched — real-time status, preview, approval workflow, pilot client group onboarded.

WS-C-M3 (Q3 2031):  EVT-002 trigger rules live — 8 cross-pillar automations verified on 2 pilot projects, GAP-06 closed.

WS-C-M4 (Q4 2031):  WS-C UAT passed — all 6 checklist items complete, client NPS target ≥70 achieved on pilot projects.

47. Real-time KPI Dashboard (GAP-08) — AMD-004 WS-D Phase 1 Roadmap Completion

47.1  Overview & Phase 1 Significance

Section 47 closes GAP-08 (Real-time KPI Dashboard) — the final HIGH-priority gap in Phase 1 of the Gap Resolution Roadmap, completing all six Phase 1 targets (GAP-01 through GAP-04, GAP-07, GAP-08). With this section, the MONOLITH DAPH Decor programme achieves the Phase 1 coverage target of 68% (up from the baseline 56% recorded in the September 2026 SOP-GitHub Coverage Analysis). The Real-time KPI Dashboard is the central operations visibility layer for the 28-agent programme, consolidating SLA performance, project health, financial tracking, and client satisfaction metrics into a single unified interface accessible to the Steering Committee and Programme Directors.

This section falls under AMD-004 Workstream D (Data & Analytics Maturity Enhancement, ฿0.9M, S38.8.4). Timeline: Q3–Q4 2030 (Phase 1 — earliest delivery, enabling SC oversight from programme start). Primary Agents: Atlas (Analytics Intelligence, Group C ≥94%), Ledger (Financial Tracking, Group D ≥97%), Pulse (Performance Monitoring, Group C ≥94%), Nexus (System Integration, Group D ≥97%).

47.2  Dashboard Architecture

The Real-time KPI Dashboard is built on three integrated layers that leverage existing monolith-workspace infrastructure and the new WS-B data pipeline (S45.2 INFRA-WS-B-03):

Layer 1 — Data Collection:  Event streams from Kafka (WS-B/S45) + direct Supabase queries (src/core/supabase/). Data sources: agent SLA logs (all 28 agents), project milestone events (Pillar Event Bus S46.3), financial transactions (Ledger agent), client interaction logs (Shore/Kelly agents), POE survey results (Scout agent). Refresh cadence: real-time (Kafka) + 15-min batch (Supabase).

Layer 2 — Analytics & Aggregation:  Dedicated analytics service in src/analytics/ (existing module, extended under WS-D). Pre-computed KPI aggregations: rolling 7/30/90-day SLA averages per agent, project health index (weighted: timeline 40% + budget 30% + client satisfaction 30%), pillar coverage delta tracking, AMD programme milestone burn-rate.

Layer 3 — Visualisation & Alerting:  React-based dashboard (src/dashboard/ — new module) served via WS-B API Gateway. Role-based views: SC view (programme KPIs, phase completion, risk register), Programme Director view (agent SLA, project health, financial burn), Agent supervisor view (individual agent metrics, queue depth, SLA countdown). Alert engine: Pulse agent broadcasts SC-prioritised alerts at defined thresholds.

47.3  KPI Framework — Core Metrics

The dashboard tracks four KPI categories mandatory for World-Class AI Agent programme governance:

SLA Performance KPIs (KPI-001–007):  Per-agent SLA compliance rate (Group A ≥95%, B ≥93%, C ≥94%, D ≥97%). Weekly SLA breach count, mean time to recovery (MTTR), agent availability uptime. Pillar coverage completeness: current % per pillar vs Phase 1/2/3 targets. Dashboard alert: RED if any agent group SLA drops below threshold for 3 consecutive days.

Project Health KPIs (KPI-008–014):  Active project count, on-time delivery rate (target ≥90%), budget variance (target ≤5%), design freeze compliance (% projects hitting DFG gate S40 without scope creep), client approval turnaround (target ≤48hrs for concept approval). Design iteration count per project (AI Creative Engine S45.3 AIE-005 tracking).

Financial Performance KPIs (KPI-015–019):  AMD programme spend vs plan: WS-A through WS-E monthly burn rate vs ฿5.2M budget. Project revenue recognition timeline, client invoice ageing (Ledger agent), cost-per-delivered-section (AMD workstream efficiency metric). SC-2030-01 to SC-2030-05 gate budget consumption tracking.

Client Experience KPIs (KPI-020–024):  NPS score (target ≥70), client satisfaction index per project (post-POE survey S42), WELL/LEED certification achievement rate, repeat client rate, referral rate. Real-time client portal engagement (active sessions, approval response time).

47.4  Phase 1 Gap Closure Summary

With Section 47 accepted, Phase 1 of the Gap Resolution Roadmap is formally complete. The following HIGH-priority gaps are now covered by corresponding SOP sections and GitHub module specifications:

GAP-01 (Biophilic Module):  Closed by S39 — Biophilic Design Framework, WELL v2 features, src/biophilic/ spec, BIO-WS-01–05.

GAP-02 (Design Freeze Gate):  Closed by S40 — Design Freeze Gate Protocol, DFG-WS-01–06, src/design-freeze/ spec.

GAP-03 (Sensory Commissioning):  Closed by S41 — 5-sense commissioning protocol, SCP-WS-01–05, src/sensory-commissioning/ spec.

GAP-04 (POE Framework):  Closed by S42 — Post-Occupancy Evaluation Framework, POE-WS-01–05, src/poe/ spec.

GAP-07 (SC Governance Dashboard):  Closed by S43 — SC Governance Module, GOV-AMD4-01–06, src/sc-governance/ spec.

GAP-08 (Real-time KPI Dashboard):  Closed by S47 (this section) — KPI Framework KPI-001–024, src/dashboard/ spec, WS-D delivery.

47.5  Delivery Checklist (KPI-WS-D-01–05)

KPI-WS-D-01:  Kafka data pipeline connected to analytics layer — all 28 agent SLA streams live. Target: Q3 2030.

KPI-WS-D-02:  Analytics service extended — KPI-001 to KPI-024 pre-computed aggregations verified. Target: Q3 2030.

KPI-WS-D-03:  Dashboard src/dashboard/ v1.0 deployed — SC view, Programme Director view, Agent view active. Target: Q4 2030.

KPI-WS-D-04:  Alert engine via Pulse agent — 12 alert rules live, SC escalation tested (SC-2030-01 governance chain). Target: Q4 2030.

KPI-WS-D-05:  Phase 1 coverage verification report published — GAP-01 to GAP-08 formal closure confirmed by Atlas agent. Target: Q4 2030.

47.6  Governance, Dependencies & Agent Assignments

WS-D is governed under SC-2030-01 (AMD-004 programme authorisation). Analytics Lead: Atlas (Group C, ≥94%). Dashboard Lead: Frame (Group C, ≥94%). Financial KPI: Ledger (Group D, ≥97%). Alert Management: Pulse (Group C, ≥94%). System Integration: Nexus (Group D, ≥97%). SC Reporting: Vega (Group D, ≥97%).

Phase 1 dependencies: S38 (AMD-004 PDD — programme budget and SC gate), S39–S43 (Phase 1 gap sections — data sources for coverage KPIs), S45 WS-B (Kafka infrastructure for real-time data ingestion), src/core/telemetry/ (existing telemetry → KPI feed), src/core/supabase/ (SLA and project data store).

47.7  Milestones (KPI-M1–M4)

KPI-M1 (Q3 2030):  KPI data pipeline and analytics layer live — all agent SLA streams ingesting, KPI-001–024 computed.

KPI-M2 (Q4 2030):  Dashboard v1.0 launched — SC and Programme Director views deployed, first SC review cycle completed.

KPI-M3 (Q4 2030):  Alert engine active — Pulse agent broadcasting SLA alerts, GAP-08 formally closed.

KPI-M4 (Q4 2030):  Phase 1 Roadmap completion certificate issued — coverage confirmed at ≥68%, SC-2030-01 Phase 1 gate passed.

Section 48 — AMD-004 WS-E: Human Capital & Change Management

Section 48 documents Workstream E (WS-E) of the AMD-004 Decor AI Agent Programme — the human capital and change management workstream responsible for embedding the 28-agent AI architecture into day-to-day operations through structured training and organisational change. WS-E is the final workstream of AMD-004, budget THB 0.6M, delivery Q1–Q2 2032.

48.1  ภาพรวม WS-E (Workstream E Overview)

WS-E ครอบคลุมมิติด้านทุนมนุษย์ของโครงการ AMD-004: การฝึกอบรมบุคลากร การรับรองการใช้เครื่องมือ AI และการบริหารการเปลี่ยนแปลงเพื่อให้สถาปัตยกรรม 28 AI Agent ฝังรากอยู่ในกระบวนการปฏิบัติงานจริง WS-E เป็น Workstream สุดท้ายของ AMD-004 ที่รับประกันว่าทีมงานมีความพร้อมในการดำเนินงานอย่างยั่งยืน หลังจากการติดตั้งระบบเทคนิคเสร็จสมบูรณ์ใน WS-A ถึง WS-D

Programme:  AMD-004 Decor AI Agent Architecture — Workstream E

Authorising document:  SC-2030-01 (AMD-004 Programme Definition Document, Section 38)

Budget:  THB 0.6M

Timeline:  Q1–Q2 2032

Owner:  Talent (Group D, SLA ≥97%)

Support agents:  Core (Group D, ≥97%), Hana (Group B, ≥93%), Nova (Group A, ≥95%)

48.2  ขอบเขตงาน (Scope of Work)

WS-E ครอบคลุมงาน 4 สาขาหลัก ได้แก่ (1) การออกแบบและดำเนินโครงการฝึกอบรม (2) การรับรองการใช้เครื่องมือ AI สำหรับบุคลากรทุกระดับ (3) กรอบการบริหารการเปลี่ยนแปลงองค์กร และ (4) การวัดผลการนำระบบไปใช้จริง (Adoption Metrics)

• ออกแบบหลักสูตรฝึกอบรม 4 ชุด (TRN-001–004) สำหรับบุคลากรทุกบทบาท — Agent Operators, Designers, Client Managers, SC Members

• จัดทำระบบการรับรอง AI Tool Certification สำหรับการใช้งาน Agent ในงาน Interior Design Workflow

• วิเคราะห์ผู้มีส่วนได้เสียและออกแบบแผนการสื่อสาร (CHG-001–002) ครอบคลุมทุก Stakeholder Group

• สร้างกลไกจัดการความต้านทานต่อการเปลี่ยนแปลง (CHG-003) และวัดผล Adoption (CHG-004)

• ออกแบบ Onboarding Program สำหรับ New Joiners เพื่อให้ครอบคลุม AMD-004 Architecture ตั้งแต่วันแรก

• สร้าง Knowledge Base และ SOP Quick Reference สำหรับ 28 AI Agents — ภาษาไทยและภาษาอังกฤษ

48.3  งบประมาณและกรอบเวลา (Budget & Timeline)

WS-E มีงบประมาณ THB 0.6M ซึ่งเป็นส่วนหนึ่งของงบประมาณรวม AMD-004 ทั้งหมด THB 5.2M โดยอนุมัติภายใต้ SC-2030-01 ดำเนินการใน Q1–Q2 2032 ซึ่งเป็นระยะสุดท้ายของโครงการ

WS-E Total Budget:  THB 0.6M

Training Design & Development:  THB 0.18M (30% of WS-E)

Training Delivery & Facilitation:  THB 0.15M (25% of WS-E)

Change Management Consulting:  THB 0.12M (20% of WS-E)

Materials, Platform & Certification System:  THB 0.09M (15% of WS-E)

Adoption Monitoring & Evaluation:  THB 0.06M (10% of WS-E)

Q1 2032 Activities:  Stakeholder analysis, curriculum design, pilot delivery (TRN-001–002)

Q2 2032 Activities:  Full rollout (TRN-003–004), change management closure, adoption metrics baseline

48.4  Training Programme (TRN-001–004)

โปรแกรมการฝึกอบรม WS-E ประกอบด้วย 4 ชุดการเรียนรู้ครอบคลุมบุคลากรทุกบทบาทในองค์กร ตั้งแต่ทีมปฏิบัติการ Agent Operations ไปจนถึงทีมบริการลูกค้าและคณะกรรมการ SC

TRN-001 Agent Operations Training:  หลักสูตร 16 ชั่วโมง — สถาปัตยกรรม 28 AI Agents, SLA Groups A–D, Orchestration Workflow, Escalation Procedures. กลุ่มเป้าหมาย: Project Managers, Design Leads. รูปแบบ: Workshop 2 วัน + E-learning Self-paced. ผู้รับผิดชอบ: Talent + Core.

TRN-002 AI Tool Certification:  การรับรองมาตรฐาน 3 ระดับ (Bronze/Silver/Gold) สำหรับการใช้งาน AI Tools ในกระบวนการออกแบบ Interior Design — Concept Generation, Material Selection, Spatial Planning. กลุ่มเป้าหมาย: Designers, Creative Leads. ผู้รับผิดชอบ: Nova + Hana.

TRN-003 Design Process Re-engineering:  Workshop 8 ชั่วโมง — การปรับกระบวนการออกแบบใหม่โดยใช้ AI-augmented workflow ครอบคลุม Biophilic Design Integration (GAP-01), Material Sustainability (covered in Pillar 2–5), POE Feedback Loop (GAP-03/04). กลุ่มเป้าหมาย: All Design Staff. ผู้รับผิดชอบ: Talent.

TRN-004 Client-Facing AI Usage:  หลักสูตร 4 ชั่วโมง — การสื่อสารกับลูกค้าเกี่ยวกับ AI-assisted Design, Client Portal Walkthrough, AI Transparency Guidelines. กลุ่มเป้าหมาย: Client Managers, Account Leads. ผู้รับผิดชอบ: Nova.

48.5  Change Management Framework (CHG-001–004)

กรอบการบริหารการเปลี่ยนแปลงของ WS-E ใช้แนวทาง ADKAR (Awareness–Desire–Knowledge–Ability–Reinforcement) ปรับให้เหมาะสมกับบริบทการนำ AI มาใช้ในงานออกแบบตกแต่งภายใน

CHG-001 Stakeholder Analysis:  วิเคราะห์และจัดลำดับ Stakeholders ทั้งหมดตามระดับผลกระทบและความพร้อมรับการเปลี่ยนแปลง ครอบคลุม SC Members, Programme Director, Design Teams, Client-facing Staff, IT Operations. ผลลัพธ์: Stakeholder Map + Engagement Strategy. กำหนดส่ง: Q1 2032.

CHG-002 Communication Plan:  แผนการสื่อสารครอบคลุม: Timeline การประกาศเปิดตัว AMD-004, FAQs สำหรับบุคลากรทุกกลุ่ม, Progress Updates รายไตรมาส, Success Story Sharing. ช่องทาง: All-hands meetings, Intranet, Line Official, SC Reports. กำหนดส่ง: Q1 2032.

CHG-003 Resistance Management:  กลไกระบุและจัดการความต้านทาน: Anonymous Feedback Channels, Champion Network (1 ต่อทีม), Escalation Path สำหรับความกังวลที่ซับซ้อน, 30/60/90-day Check-ins. ผู้รับผิดชอบ: Hana (Group B, ≥93%). กำหนดดำเนินการ: ตลอด Q1–Q2 2032.

CHG-004 Adoption Metrics:  ตัวชี้วัดการนำระบบไปใช้จริง: Training Completion Rate ≥90%, Certification Pass Rate ≥80%, AI Tool Active Usage ≥70% of Design Staff within 90 days, Client Satisfaction Score ≥4.2/5.0 post-AI integration, Agent SLA Achievement ≥ target levels per Group A–D. ผู้รับผิดชอบ: Talent + Pulse.

48.6  รายการตรวจสอบ WS-E (TRN-WS-E-01–05)

TRN-WS-E-01:  Training Needs Analysis completed — all roles mapped to training modules TRN-001–004, gap analysis validated by Programme Director. Target: Q1 2032.

TRN-WS-E-02:  TRN-001 & TRN-002 pilot delivery completed — minimum 20 participants, feedback score ≥4.0/5.0, curriculum adjustments incorporated. Target: Q1 2032.

TRN-WS-E-03:  TRN-003 & TRN-004 full rollout completed — all eligible staff certified, AI Tool Certification Bronze achieved by 100% of Design Staff. Target: Q2 2032.

TRN-WS-E-04:  Change Management Framework CHG-001–004 executed — Stakeholder Map published, Communication Plan active, Resistance Management channels operational, Adoption Metrics baseline recorded. Target: Q2 2032.

TRN-WS-E-05:  WS-E Closure Report submitted to SC — Training Completion ≥90%, Adoption Metrics baseline confirmed, Knowledge Base published (TH/EN), WS-E formally closed under SC-2030-01. Target: Q2 2032.

48.7  Milestones WS-E-M1–WS-E-M4

WS-E-M1 (Q1 2032):  Training programme designed and piloted — TRN-001 & TRN-002 pilot complete, CHG-001 Stakeholder Analysis published, Communication Plan activated.

WS-E-M2 (Q1 2032):  Full training rollout commenced — TRN-003 & TRN-004 delivery started, CHG-003 Resistance Management channels operational, CHG-002 mid-programme communications live.

WS-E-M3 (Q2 2032):  All training streams completed — 100% staff coverage achieved, AI Tool Certification issued, CHG-004 Adoption Metrics 30-day baseline recorded.

WS-E-M4 (Q2 2032):  WS-E formally closed — TRN-WS-E-01–05 all ticked, WS-E Closure Report accepted by SC, AMD-004 Programme ready for Programme Closure gate (Section 49).

Section 49 — AMD-004 Programme Closure & Phase 2 Gateway

Section 49 is the formal Programme Closure section for AMD-004 Decor AI Agent Architecture. It consolidates all five workstreams (WS-A through WS-E), confirms the Phase 1 completion certificate covering GAP-01/02/03/04/07/08, and establishes the Phase 2 Readiness Gate for GAP-05/06/09/10/11/12. Total programme investment: THB 5.2M.

49.1  ภาพรวม AMD-004 Programme Closure

การปิดโครงการ AMD-004 (Programme Closure) ถือเป็นจุดสิ้นสุดของ Phase 1 ของการพัฒนา Decor AI Agent Architecture โดย MONOLITH DAPH ครอบคลุมระยะเวลาดำเนินงานตั้งแต่ Q3 2030 ถึง Q2 2032 รวม 8 ไตรมาส งบประมาณรวม THB 5.2M และผลลัพธ์คือการยกระดับ AI Coverage จาก 56% เป็น 68% ผ่านการปิด GAP 6 รายการจาก 15 รายการ (GAP-01/02/03/04/07/08)

Programme:  AMD-004 Decor AI Agent Architecture — MONOLITH DAPH

Authorising SC Resolution:  SC-2030-01

Programme Start:  Q3 2030 (WS-A & WS-D commencement)

Programme End (Phase 1):  Q2 2032 (WS-E closure)

Total Budget:  THB 5.2M (all 5 workstreams)

Phase 1 Coverage Achievement:  56% → 68% (+12 percentage points)

GAPs Closed in Phase 1:  GAP-01, GAP-02, GAP-03, GAP-04, GAP-07, GAP-08 (6 of 15)

Programme Director:  Core (Group D, SLA ≥97%)

49.2  สรุปทุก Workstream (WS-A through WS-E)

AMD-004 ประกอบด้วย 5 Workstream ที่ดำเนินการต่อเนื่องกัน ตั้งแต่การวางโครงสร้างพื้นฐานทางกฎหมาย ไปจนถึงการพัฒนาทักษะบุคลากร ทุก Workstream เชื่อมโยงและส่งต่อผลลัพธ์ระหว่างกัน

WS-A Corporate Governance & Regulatory Alignment:  THB 0.8M | Q3–Q4 2030 | Status: Completed. Output: SC-2030-01 Programme Resolution, Regulatory Compliance Framework, 28-agent Governance Charter. Owner: Guardian (Group D, ≥97%).

WS-B Technology Infrastructure Next Generation:  THB 1.1M | Q1–Q3 2031 | Status: Completed. Output: Kafka event bus, Supabase multi-tenant schema, Microservices mesh, API Gateway, Cloud infrastructure. Owner: Nexus (Group D, ≥97%). GAP-05 partial.

WS-C Client Service Innovation Delivery:  THB 1.2M | Q2–Q4 2031 | Status: Completed. Output: Client Portal v2.0, AI-assisted Design Consultation Module, CRM-Agent integration, NPS tracking. Owner: Scout (Group B, ≥93%). GAP-06 partial.

WS-D Real-time Analytics & KPI Dashboard:  THB 0.9M | Q3–Q4 2030 | Status: Completed. Output: KPI Framework (KPI-001–024), Real-time Dashboard, Alert Engine, Phase 1 Completion Certificate. Owner: Atlas (Group C, ≥94%). GAP-08 closed.

WS-E Human Capital & Change Management:  THB 0.6M | Q1–Q2 2032 | Status: Completed (Section 48). Output: Training Programme TRN-001–004, AI Tool Certification, Change Management Framework CHG-001–004, Adoption Metrics baseline. Owner: Talent (Group D, ≥97%).

49.3  งบประมาณรวม THB 5.2M (Programme Budget Summary)

งบประมาณรวม AMD-004 อนุมัติโดย SC ภายใต้ SC-2030-01 แบ่งตาม Workstream ดังนี้ รวม THB 5.2M ครอบคลุมระยะดำเนินการ 8 ไตรมาส (Q3 2030 – Q2 2032)

WS-A Corporate Governance:  THB 0.8M (15.4% of total)

WS-B Technology Infrastructure:  THB 1.1M (21.2% of total)

WS-C Client Service Innovation:  THB 1.2M (23.1% of total)

WS-D Analytics & KPI Dashboard:  THB 0.9M (17.3% of total)

WS-E Human Capital & Change Mgmt:  THB 0.6M (11.5% of total)

Programme Contingency (6.5%):  THB 0.6M (reserved under SC-2030-01)

TOTAL AMD-004 PROGRAMME:  THB 5.2M

Programme contingency THB 0.6M ถูกบริหารโดย Core (Group D) ภายใต้การกำกับของ SC การใช้จ่าย Contingency ทุกรายการต้องผ่านการอนุมัติ SC และบันทึกใน Programme Change Log

49.4  Phase 1 Completion Certificate (GAP-01/02/03/04/07/08)

ใบรับรองการสำเร็จ Phase 1 ยืนยันการปิด GAP ทั้ง 6 รายการที่กำหนดไว้ใน Phase 1 Roadmap ซึ่งยกระดับ AI Coverage ของ MONOLITH DAPH จาก 56% เป็น 68%

GAP-01 Biophilic Design Intelligence:  CLOSED — Section 39, Pillar 1 Biophilic Integration SOP. Agent: Blaze (Group A, ≥95%). Coverage contribution: +2%. src/biophilic/

GAP-02 Design Freeze Gate Enforcement:  CLOSED — Section 40, Pillar 2 Design Freeze Gate SOP. Agent: Signal (Group A, ≥95%). Coverage contribution: +2%. src/design-freeze/

GAP-03 Sensory Commissioning Protocol:  CLOSED — Section 41, Pillar 6 Sensory Commissioning SOP. Agent: Ember (Group B, ≥93%). Coverage contribution: +1%. src/sensory/

GAP-04 Post-Occupancy Evaluation (POE):  CLOSED — Section 42, POE Framework & Feedback Loop SOP. Agent: Shore (Group B, ≥93%). Coverage contribution: +2%. src/poe/

GAP-07 SC Governance Dashboard:  CLOSED — Section 43, SC Governance Module SOP. Agent: Vega (Group D, ≥97%). Coverage contribution: +2%. src/sc-governance/

GAP-08 Real-time KPI Dashboard:  CLOSED — Section 47, WS-D KPI Framework SOP. Agent: Frame (Group C, ≥94%). Coverage contribution: +3%. src/dashboard/

Phase 1 Coverage Verification: Atlas (Group C, ≥94%) ดำเนินการตรวจสอบ Coverage ผ่าน KPI-018 (SOP Coverage Score) และ KPI-019 (Gap Closure Rate) ยืนยัน Coverage ≥68% ภายใน Q4 2030 (KPI-WS-D-05). Phase 1 Completion Certificate ออกโดย Core (Group D) และเสนอต่อ SC เพื่อรับทราบ

49.5  Phase 2 Readiness Gate (GAP-05/06/09/10/11/12)

Phase 2 Readiness Gate กำหนดเงื่อนไขเริ่มต้น Phase 2 ที่มุ่งยกระดับ AI Coverage จาก 68% เป็น 80% ครอบคลุม GAP 6 รายการ ได้แก่ GAP-05, GAP-06, GAP-09, GAP-10, GAP-11, GAP-12 การผ่าน Phase 2 Gate ต้องได้รับการอนุมัติจาก SC ก่อนเริ่มงบประมาณ Phase 2

GAP-05 AI Creative Engine (Cross-Pillar AI):  OPEN — Phase 2 Target. WS-B infrastructure prerequisite met. Requires: AI Creative Engine spec completion, SC approval for Phase 2 budget. Responsible Agent: Kelly (Group A, ≥95%). Target: Phase 2 Q1–Q2 2033.

GAP-06 Cross-Pillar Event Bus Integration:  OPEN — Phase 2 Target. WS-B Kafka infrastructure in place. Requires: Event schema definition, agent subscription model, full integration testing. Responsible Agent: Compass (Group B, ≥93%). Target: Phase 2 Q2–Q3 2033.

GAP-09 Sustainable Material Intelligence:  OPEN — Phase 2 Target. Medium priority. Requires: Material database integration, sustainability scoring model. Responsible Agent: Forge (Group C, ≥94%). Target: Phase 2 Q1 2033.

GAP-10 Contractor & Vendor Management AI:  OPEN — Phase 2 Target. Medium priority. Requires: Vendor API integration, procurement workflow automation spec. Responsible Agent: Rex (Group D, ≥97%). Target: Phase 2 Q2 2033.

GAP-11 Spatial Analytics & Occupancy Intelligence:  OPEN — Phase 2 Target. Medium priority. Requires: IoT sensor integration spec, spatial analytics model. Responsible Agent: Bo (Group C, ≥94%). Target: Phase 2 Q3 2033.

GAP-12 Multi-language Client Communication:  OPEN — Phase 2 Target. Medium priority. Requires: NLP model fine-tuning for Thai/EN/CN design terminology. Responsible Agent: Remy (Group B, ≥93%). Target: Phase 2 Q2 2033.

Phase 2 Gate Criteria: (1) Phase 1 Completion Certificate issued and SC-acknowledged, (2) WS-E Closure confirmed (Section 48/49), (3) Phase 2 Business Case submitted with budget estimate for 6 remaining HIGH GAPs, (4) SC Resolution SC-2032-XX authorising Phase 2 budget and timeline, (5) Phase 2 Programme Director nominated and onboarded.

49.6  รายการตรวจสอบปิดโครงการ (AMD4-CLOSE-01–05)

AMD4-CLOSE-01:  All 5 Workstream Closure Reports received and accepted by SC — WS-A through WS-E formal closure confirmed. Target: Q2 2032.

AMD4-CLOSE-02:  Phase 1 Completion Certificate issued — Coverage ≥68% verified by Atlas (KPI-WS-D-05), GAP-01/02/03/04/07/08 formal closure documented. Target: Q2 2032.

AMD4-CLOSE-03:  Programme Financial Closure — all WS-A–E budgets reconciled, Contingency utilisation reported, final financial statement submitted to SC. Target: Q2 2032.

AMD4-CLOSE-04:  Knowledge Transfer & Documentation — all SOP sections (S38–S49) accepted, Knowledge Base published (TH/EN), GitHub repository main branch tagged v2.5-Phase1-Complete. SHA reference: 14b90bc. Target: Q2 2032.

AMD4-CLOSE-05:  Phase 2 Readiness Gate passed — Phase 2 Business Case approved by SC, SC-2032-XX resolution issued, Phase 2 Programme Director in post. Target: Q3 2032.

49.7  AMD-004 Programme Timeline Summary

สรุปไทม์ไลน์รวมของโครงการ AMD-004 ตั้งแต่เริ่มต้นจนถึงการผ่าน Phase 2 Gate ครอบคลุม 10 ไตรมาส (Q3 2030 – Q3 2032)

Q3–Q4 2030:  WS-A Corporate Governance (THB 0.8M) + WS-D Analytics & KPI Dashboard start (THB 0.9M). SC-2030-01 passed. GAP-08 closure work commenced.

Q1–Q4 2031:  WS-B Technology Infrastructure (THB 1.1M, Q1–Q3). WS-C Client Service Innovation (THB 1.2M, Q2–Q4). GAP-05/06 infrastructure foundations laid.

Q3–Q4 2030 (parallel):  WS-D delivery: KPI framework KPI-001–024 built, Dashboard src/dashboard/ deployed, GAP-08 formally closed, Phase 1 Completion Certificate KPI-M4 issued.

Q1–Q2 2032:  WS-E Human Capital & Change Management (THB 0.6M). TRN-001–004 delivered, CHG-001–004 executed, AMD4-CLOSE-01–05 completed.

Q2 2032:  AMD-004 Programme formally closed. Phase 1 Completion Certificate SC-acknowledged. Coverage 68% confirmed. S38–S49 SOP package complete.

Q3 2032 (target):  Phase 2 Gate passed — SC-2032-XX resolution. Phase 2 programme commences targeting Coverage 80% by Q4 2033 (GAP-05/06/09/10/11/12).

Section 50 — Phase 2 Programme Definition Document (PDD)

Section 50 establishes the Programme Definition Document (PDD) for Phase 2 of the MONOLITH DAPH Decor AI Agent Programme. Phase 2 targets coverage improvement from 68% to 80% by closing GAP-05, GAP-06, GAP-09, GAP-10, GAP-11, and GAP-12, authorised under SC Resolution SC-2032-XX. Total Phase 2 budget estimate: THB 6.0M, delivery target Q4 2033.

50.1  ภาพรวม Phase 2 PDD (Phase 2 Overview)

Phase 2 ของโครงการ MONOLITH DAPH Decor AI Agent Programme มีวัตถุประสงค์เพื่อเพิ่มความครอบคลุม ของ SOP จาก 68% (ผลสำเร็จ Phase 1) ไปเป็น 80% โดยการปิด 6 Gap ลำดับต่อไปจากทะเบียน Gap 15 ข้อ ได้แก่ GAP-05 (AI Creative Engine), GAP-06 (Cross-Pillar Event Bus), GAP-09 (Material Intelligence), GAP-10 (Contractor/Vendor Integration), GAP-11 (Spatial Analytics), และ GAP-12 (Multi-language Support)

Coverage target:  68% (Phase 1 achieved) → 80% (Phase 2 target)

Authorisation:  SC Resolution SC-2032-XX (Q3 2032)

Budget estimate:  THB 6.0M (includes 10% contingency)

Timeline:  Q1 2033 – Q4 2033 (4 quarters)

Gaps addressed:  GAP-05, GAP-06, GAP-09, GAP-10, GAP-11, GAP-12

Programme Director:  To be nominated by SC post-resolution

SOP sections created:  S50 (this PDD) + planned implementation sections S51–S56

50.2  SC Resolution SC-2032-XX

SC Resolution SC-2032-XX อนุมัติการเริ่มต้น Phase 2 ของโครงการ MONOLITH DAPH Decor AI Agent Programme ต่อจากการปิด Phase 1 อย่างเป็นทางการ โดยมีเงื่อนไขว่า Phase 1 Completion Certificate ได้รับการรับรองจากคณะกรรมการกำกับดูแล และ AMD-004 ทั้ง 5 Workstream ส่งมอบผลลัพธ์ครบถ้วน

Resolution reference:  SC-2032-XX

Issuing body:  MONOLITH DAPH Steering Committee (SC)

Resolution date:  Q3 2032 (target)

Pre-conditions:  Phase 1 gate passed: GAP-01/02/03/04/07/08 closed; AMD-004 AMD4-CLOSE-01–05 completed; Coverage 68% independently verified; SC-2030-01 Phase 1 obligations discharged

Phase 2 mandate:  Authorise THB 6.0M Phase 2 budget; nominate Phase 2 Programme Director; approve GAP-05/06/09/10/11/12 workplan; set coverage milestone 80% by Q4 2033

Reporting cycle:  Quarterly SC reporting; milestone gate at 75% coverage midpoint

Phase 3 pre-condition:  SC-2033-XX gate review upon Phase 2 completion

50.3  GAP-05 / GAP-06 / GAP-09 / GAP-10 / GAP-11 / GAP-12 Workplan

50.3.1  GAP-05: AI Creative Engine & Generative Design Workflow — High Priority

Owner agent:  Aria (Group A, SLA ≥95%) + Nova (Group A, ≥95%)

Budget:  THB 1.5M

Timeline:  Q1–Q3 2033

Deliverables:  src/creative-engine/ AI generative design module; style-transfer pipeline; Pillar 5 Creative Direction SOP S51; integration with Atlas (Group C) spatial context

Success criteria:  AI-assisted concept generation operational; 80% designer adoption rate; creative review cycle reduced 40%; GAP-05 formally closed

50.3.2  GAP-06: Cross-Pillar Event Bus & Real-time Integration — High Priority

Owner agent:  Signal (Group A, SLA ≥95%) + Core (Group D, ≥97%)

Budget:  THB 1.0M

Timeline:  Q1–Q2 2033

Deliverables:  src/event-bus/ message broker; cross-pillar event schema; Pub/Sub integration with Supabase; SOP S52 Event Bus Governance; audit trail EVENT-001–010

Success criteria:  Real-time event propagation across all 6 Pillars; sub-100ms event latency; zero data loss in event replay; GAP-06 formally closed

50.3.3  GAP-09: Material Intelligence & Procurement Integration — Medium Priority

Owner agent:  Forge (Group C, SLA ≥94%) + Remy (Group B, ≥93%)

Budget:  THB 0.8M

Timeline:  Q2–Q3 2033

Deliverables:  src/material-intelligence/ module; supplier API integrations; material carbon-footprint scoring; SOP S53 Material Intelligence; procurement workflow MAT-001–020

Success criteria:  Material specification auto-matched to approved supplier catalogue; procurement lead time reduced 30%; sustainability score integrated; GAP-09 closed

50.3.4  GAP-10: Contractor & Vendor Management Integration — Medium Priority

Owner agent:  Ledger (Group D, SLA ≥97%) + Compass (Group B, ≥93%)

Budget:  THB 0.7M

Timeline:  Q2–Q4 2033

Deliverables:  src/vendor/ contractor management module; contract lifecycle CNTR-001–050; SOP S54 Contractor & Vendor; Supabase vendor registry schema; performance scorecard integration with KPI-001–024

Success criteria:  All contractor engagements tracked in system; payment milestone automation; vendor SLA compliance rate ≥90%; GAP-10 closed

50.3.5  GAP-11: Spatial Analytics & Occupancy Intelligence — Medium Priority

Owner agent:  Atlas (Group C, SLA ≥94%) + Bo (Group C, ≥94%)

Budget:  THB 0.8M

Timeline:  Q3–Q4 2033

Deliverables:  src/spatial-analytics/ occupancy and space utilisation module; BIM integration layer; Pillar 6 spatial performance SOP S55; SPACE-001–015 analytics framework

Success criteria:  Real-time space utilisation dashboard; post-occupancy spatial score baseline set; Pillar 6 coverage gap addressed; GAP-11 closed

50.3.6  GAP-12: Multi-language & Localisation Support — Medium Priority

Owner agent:  Hana (Group B, SLA ≥93%) + Ember (Group B, ≥93%)

Budget:  THB 0.6M

Timeline:  Q3–Q4 2033

Deliverables:  src/localisation/ multi-language engine (Thai/English/Chinese baseline); SOP S56 Localisation & Language Policy; LANG-001–010 language packs; translation memory integration

Success criteria:  All client-facing outputs available in Thai and English; translation accuracy ≥95%; language switch latency ≤500ms; GAP-12 closed

50.4  Phase 2 Budget Estimate

ประมาณการงบประมาณ Phase 2 รวมทั้งสิ้น THB 6.0M แบ่งตาม Gap ที่จะปิด และรวมค่าสำรองฉุกเฉิน 10% (contingency THB 0.6M) สำหรับความเสี่ยงที่ไม่คาดฝัน

GAP-05 AI Creative Engine:  THB 1.5M

GAP-06 Cross-Pillar Event Bus:  THB 1.0M

GAP-09 Material Intelligence:  THB 0.8M

GAP-10 Contractor/Vendor:  THB 0.7M

GAP-11 Spatial Analytics:  THB 0.8M

GAP-12 Multi-language:  THB 0.6M

Contingency (10%):  THB 0.6M

Total Phase 2 estimate:  THB 6.0M

Approval required from:  SC Resolution SC-2032-XX

Budget release schedule:  Q1 2033: THB 2.5M (GAP-05+GAP-06); Q2 2033: THB 1.5M (GAP-09+GAP-10); Q3–Q4 2033: THB 2.0M (GAP-11+GAP-12+contingency)

50.5  Phase 2 Milestones P2-M1 through P2-M4

Phase 2 ดำเนินการผ่าน 4 milestones หลัก ครอบคลุม 4 ไตรมาส (Q1–Q4 2033) แต่ละ milestone มีเงื่อนไข gate review ก่อนปลดล็อคงบประมาณของ milestone ถัดไป

P2-M1 (Q1 2033):  Phase 2 Kickoff — SC-2032-XX ratified; Programme Director appointed; GAP-05 and GAP-06 workstreams commenced; onboarding complete; src/creative-engine/ and src/event-bus/ repositories initialised

P2-M2 (Q2 2033):  Mid-phase gate — GAP-06 Event Bus MVP delivered and tested; GAP-09 Material Intelligence build commenced; GAP-10 Contractor module design approved; coverage spot-check ≥70% confirmed; Q2 SC quarterly report submitted

P2-M3 (Q3 2033):  75% coverage gate — GAP-05 AI Creative Engine delivered; GAP-09 and GAP-10 modules UAT passed; GAP-11 Spatial Analytics commenced; GAP-12 Localisation build commenced; coverage independently verified at ≥75%

P2-M4 (Q4 2033):  Phase 2 Completion — GAP-11 Spatial Analytics and GAP-12 Localisation delivered; all 6 Phase 2 gaps formally closed (GAP-05/06/09/10/11/12); Coverage 80% verified; Phase 2 Completion Certificate issued; Phase 3 gate review initiated (SC-2033-XX)

50.6  Programme Governance (Phase 2)

การกำกับดูแลโครงการ Phase 2 อยู่ภายใต้โครงสร้าง SC Oversight เดิมที่สืบเนื่องจาก AMD-004 โดยมี Programme Director คนใหม่ที่ SC แต่งตั้งรับผิดชอบการดำเนินงานประจำวัน และรายงานต่อ SC ทุกไตรมาส

Steering Committee (SC):  Oversight authority; approves gate releases; resolves escalations

Phase 2 Programme Director:  Day-to-day programme leadership; P2-M1–P2-M4 milestone accountability; budget owner; nominated by SC via SC-2032-XX

Agent owners:  Per-gap owner agents as defined in Section 50.3 (Aria, Signal, Forge, Ledger, Atlas, Hana)

Governance agent — Nexus:  Group D, SLA ≥97% — Governance registry and compliance tracking

Governance agent — Guardian:  Group D, SLA ≥97% — Risk and escalation management

Governance agent — Vega:  Group D, SLA ≥97% — Financial controls and budget monitoring

Reporting cadence:  Monthly progress report to Programme Director; quarterly SC report with gate status; ad-hoc escalation for P0/P1 risks via Guardian

Change control:  Scope changes require SC written approval; budget variances >5% require SC notification; variances >15% require SC resolution amendment

50.7  Phase 2 Readiness Checklist

รายการตรวจสอบความพร้อมของโครงการก่อนเริ่ม Phase 2 อย่างเป็นทางการ รายการทั้งหมดต้องได้รับการยืนยันโดย Programme Director และ SC ก่อนเบิกจ่ายงบประมาณ Q1 2033

• P1-CHK-01: Phase 1 Completion Certificate acknowledged and filed — AMD4-CLOSE-01 executed

• P1-CHK-02: SC-2032-XX resolution formally passed and minuted

• P1-CHK-03: Phase 2 Programme Director nominated and onboarded

• P1-CHK-04: THB 6.0M Phase 2 budget released by finance — tranches per P2-M1 schedule

• P1-CHK-05: GAP-05 and GAP-06 workstream leads confirmed (Aria, Signal team)

• P1-CHK-06: GAP-09 and GAP-10 workstream leads confirmed (Forge, Ledger team)

• P1-CHK-07: GAP-11 and GAP-12 workstream leads confirmed (Atlas, Hana team)

• P1-CHK-08: Phase 2 governance structure established — Nexus registry initialised

• P1-CHK-09: Phase 2 risk register opened — Guardian agent active P2 risk monitoring

• P1-CHK-10: src/ repository branches prepared for Phase 2 modules (creative-engine, event-bus, material-intelligence, vendor, spatial-analytics, localisation)

• P1-CHK-11: Supabase schema updated with Phase 2 table definitions

• P1-CHK-12: Coverage baseline 68% independently verified before Phase 2 commencement

Readiness gate authority:  Phase 2 Programme Director + SC Chair co-sign

Target readiness date:  Q3 2032 (within 4 weeks of SC-2032-XX passage)

Section 51 — Phase 2 Procurement & Vendor Selection Framework (GAP-05 AI Creative Engine)

Section 51 establishes the procurement and vendor selection framework for GAP-05 (AI Creative Engine), the highest-budget item in Phase 2 at THB 1.5M. This section defines the competitive tender process, evaluation criteria, RFP structure, five-stage selection methodology, contract management requirements, and Phase 2 procurement readiness checklist. All procurement activities are authorised under SC Resolution SC-2032-XX and governed by the Phase 2 Programme Definition Document (S50).

51.1  ภาพรวมและขอบเขต (Overview & Scope)

ส่วนที่ 51.1 กำหนดขอบเขตการจัดซื้อจัดจ้างสำหรับ GAP-05 AI Creative Engine ซึ่งประกอบด้วย 5 Module ได้แก่ AIE-001 (Concept Generation), AIE-002 (Style Transfer), AIE-003 (Asset Rendering), AIE-004 (Quality Assurance), และ AIE-005 (Integration Gateway) การจัดซื้อนี้เป็นส่วนหนึ่งของ Phase 2 Programme ที่มีเป้าหมายเพิ่ม SOP Coverage จาก 68% เป็น 80%

Section:  S51 (Phase 2 Procurement Framework — GAP-05)

Authorisation:  SC Resolution SC-2032-XX; Phase 2 PDD S50.2

Scope:  GAP-05 AI Creative Engine — 5 modules: AIE-001, AIE-002, AIE-003, AIE-004, AIE-005

Budget:  THB 1.5M (Phase 2 allocation; contingency covered by Phase 2 THB 0.6M reserve)

Lead agent:  Aria (Group A, SLA ≥95%) — Creative Engine owner

Supporting agents:  Nova (Group A, ≥95%) — AI model QA; Signal (Group A, ≥95%) — integration; Atlas (Group C, ≥94%) — spatial context

Timeline:  P2-M1 kickoff (Q1 2033) → P2-M2 vendor award (Q2 2033) → P2-M3 UAT (Q3 2033)

SOP section created:  S51 (this Procurement Framework); implementation SOP to follow in S52+

Reference:  inject_s51.py · SC-2032-XX · AMD-004 WS-A (Aria delivery baseline)

51.2  กลยุทธ์การจัดซื้อ (Procurement Strategy)

กลยุทธ์การจัดซื้อสำหรับ GAP-05 ใช้วิธี Restricted Tender เนื่องจากมูลค่าสัญญา THB 1.5M อยู่ในเกณฑ์ที่กำหนด กระบวนการจัดซื้อต้องได้รับการอนุมัติจาก SC ก่อนออก RFP และต้องมีผู้เสนอราคา ที่มีคุณสมบัติครบถ้วนอย่างน้อย 3 ราย

Procurement method:  Restricted Tender (value THB 1.5M; ≥3 qualified vendors required)

Tender reference:  RFP-GAP05-001

Approval authority:  Phase 2 Programme Director + SC Chair (SC-2032-XX mandate)

Market approach:  Pre-qualification questionnaire (PQQ) issued to AI/ML vendor longlist

Procurement phases:  Phase A — PQQ & longlist (P2-M1, 2 weeks); Phase B — RFP issue & response (P2-M1+2w to P2-M1+6w); Phase C — Evaluation & shortlist (P2-M1+7w to P2-M1+9w); Phase D — Demo & BAFO (P2-M1+10w to P2-M1+12w); Phase E — Award & contract (P2-M2, week 13–16)

Vendor longlist target:  Minimum 5 vendors; AI generative design, interior design vertical preferred

Module packaging:  Single-vendor award preferred (AIE-001–005 integrated); split award permitted for AIE-003 (rendering) if integration SLA met

Exclusions:  Vendors with conflict of interest with MONOLITH DAPH clients; vendors unable to demonstrate 99.5% uptime SLA; vendors without ISO/IEC 27001 data security certification

• AIE-001 Concept Generation: generative AI design concept creation from brief input

• AIE-002 Style Transfer: automated style application across design deliverables

• AIE-003 Asset Rendering: high-fidelity 3D render generation pipeline

• AIE-004 Quality Assurance: automated AI output validation and scoring

• AIE-005 Integration Gateway: API connector to Supabase, Atlas spatial, Signal event bus

51.3  เกณฑ์การประเมินผู้ขาย (Vendor Evaluation Criteria)

เกณฑ์การประเมินผู้ขายแบ่งเป็น 4 หมวด โดยคะแนนรวม 100 คะแนน ผู้ขายต้องผ่านคะแนนขั้นต่ำ 70/100 เพื่อผ่านเข้าสู่รอบ Demo และ Best and Final Offer (BAFO)

Minimum passing score:  70 / 100 (technical + commercial combined)

Criterion A — Technical capability (40 pts):  AI model performance benchmarks (15 pts); integration compatibility with Supabase + event bus (10 pts); security & data governance (ISO 27001) (8 pts); scalability & API throughput ≥500 req/min (7 pts)

Criterion B — Commercial (20 pts):  Total cost of ownership within THB 1.5M (10 pts); payment milestone alignment (5 pts); pricing transparency & no hidden costs (5 pts)

Criterion C — Operational readiness (25 pts):  SLA uptime guarantee ≥99.5% (10 pts); response time ≤200ms (P95) (8 pts); AI model accuracy ≥85% on DAPH test dataset (7 pts)

Criterion D — Track record & references (15 pts):  Interior design / creative industry deployments (8 pts); client references ≥2 live implementations (4 pts); team qualifications & Thai language support (3 pts)

Disqualification criteria:  Score

Evaluation panel:  Aria (chair, technical lead); Nova (AI QA assessor); Signal (integration assessor); Core (governance); Ledger (commercial/finance)

Conflict of interest:  Panel members must declare and recuse per SC governance rules (S43)

51.4  กรอบ RFP (RFP Framework — RFP-GAP05-001)

เอกสาร RFP-GAP05-001 คือชุดเอกสารประกวดราคาหลักสำหรับ GAP-05 AI Creative Engine ประกอบด้วย 3 ส่วนหลัก: Technical Proposal, Proof of Concept (PoC), และ Commercial Proposal ผู้ขายต้องส่งเอกสารครบทั้ง 3 ส่วนภายในกำหนดเวลาที่ระบุ

Document reference:  RFP-GAP05-001

Issue date:  P2-M1 + 2 weeks (target Q1 2033 week 3)

Submission deadline:  P2-M1 + 6 weeks (4-week response window)

Clarification window:  P2-M1 + 2w to P2-M1 + 4w (Q&A period; responses published to all bidders)

Technical Proposal requirements:  AI model architecture description; benchmark results on standard datasets; AIE-001–005 module delivery plan; security & compliance certifications; team CV and experience; proposed SLA commitments

Proof of Concept (PoC) requirements:  Live demonstration of AIE-001 Concept Generation on DAPH sample brief; AIE-002 style transfer on 3 reference interior design images; API response time log (minimum 50 requests, P95 ≤200ms); PoC acceptance criteria: AI output scored ≥3.5/5 by Aria panel

Commercial Proposal requirements:  Itemised pricing per module AIE-001–005; milestone payment schedule (30/40/30 split); ongoing maintenance and support costs (Year 2+); THB pricing; VAT-inclusive total

Submission format:  Sealed digital submission via designated SC procurement portal; PDF + native editable

Late submissions:  Not accepted; automatic disqualification

RFP evaluation timeline:  Week 1–2: administrative compliance check (Aria + Core); Week 3–4: technical scoring (Aria, Nova, Signal); Week 5: commercial scoring (Ledger); Week 6: consolidated scorecards + shortlist recommendation to Programme Director

51.5  กระบวนการคัดเลือก 5 ขั้นตอน (5-Stage Selection Process)

กระบวนการคัดเลือกผู้ขาย GAP-05 ประกอบด้วย 5 ขั้นตอนเพื่อให้ได้ผู้ขายที่มีคุณภาพสูงสุด ในงบประมาณที่กำหนด แต่ละขั้นตอนมีเกณฑ์ Pass/Fail หรือ Minimum Score ที่ชัดเจน

Stage 1 — Administrative Screening:  Mandatory pass/fail; checklist: complete submission package, valid entity registration, ISO/IEC 27001 certificate, no conflict of interest declaration, signed non-disclosure agreement; Timeline: P2-M1+6w to P2-M1+7w; Outcome: qualified / disqualified

Stage 2 — Technical Evaluation:  Scoring against Criteria A + C + D (maximum 80 pts combined); minimum score to advance: 56/80 (70%); conducted by evaluation panel with independent moderation; Timeline: P2-M1+7w to P2-M1+9w

Stage 3 — Shortlist Demonstration:  Maximum 2 vendors shortlisted; live PoC demonstration to full evaluation panel + Programme Director; PoC scored by Aria-led panel (3.5/5 minimum acceptance); Vendor Q&A session (30 min per vendor); Timeline: P2-M1+10w (2-day vendor demo event)

Stage 4 — Best and Final Offer (BAFO):  Shortlisted vendors submit revised commercial proposal; clarification of SLA commitments; negotiation window: 5 business days; final consolidated scorecard: Technical (70%) + Commercial (30%) weighted; Timeline: P2-M1+11w to P2-M1+12w

Stage 5 — SC Endorsement & Award:  Programme Director recommendation report to SC; SC endorsement required (SC-2032-XX mandate); contract award letter issued within 5 business days of SC endorsement; contract execution: P2-M2 target; Timeline: P2-M2 (Q2 2033)

Award criteria:  Highest combined score (technical 70% + commercial 30%), subject to PoC acceptance

Tie-break:  Aria panel qualitative assessment of vendor AI model roadmap and long-term partnership fit

No-award clause:  If no vendor achieves minimum 70/100, RFP may be re-issued with revised scope; Programme Director reports to SC within 10 business days

51.6  การบริหารสัญญาและ SLA KPI (Contract Management & SLA KPIs)

สัญญา GAP-05 AI Creative Engine เป็น Time-and-Materials Contract พร้อม Milestone Payments กำหนด SLA KPI ที่ชัดเจนเพื่อให้ Aria และทีมสามารถกำกับดูแลผู้ขายได้ตลอดช่วงสัญญา และมีบทปรับในกรณีที่ผู้ขายไม่ปฏิบัติตามเงื่อนไข

Contract type:  Time-and-Materials with fixed milestone deliverables and SLA KPIs

Contract value:  THB 1.5M (ceiling price; variations require Programme Director approval)

Payment schedule:  30% on contract award (P2-M2); 40% on UAT acceptance (P2-M3); 30% on go-live and Phase 2 milestone sign-off (P2-M4)

Contract duration:  6 months delivery + 12 months warranty/support from go-live

SLA KPI — Uptime:  ≥99.5% monthly uptime for AIE-001–005 services

SLA KPI — Response time:  P95 ≤200ms for API calls; P99 ≤500ms

SLA KPI — AI model accuracy:  ≥85% on DAPH production dataset (monthly benchmark by Nova)

SLA KPI — Error rate:  ≤0.5% failed AI generation requests per 10,000 calls

SLA KPI — Security:  Zero critical vulnerabilities (CVSS ≥7.0) in quarterly pen-test

Penalty — Uptime breach:  0.5% of monthly contract value per 0.1% below 99.5% threshold; cap at 5% per month; 3 consecutive months breach triggers termination review

Penalty — Delay beyond P2-M3:  0.5% of contract value per week delay; cap at 10%; delay >8 weeks triggers SC notification and contract review

Governance — Contract manager:  Aria (primary); Core (governance oversight); Ledger (financial monitoring)

Reporting cycle:  Monthly vendor SLA report to Aria; quarterly review to Programme Director; milestone gate reviews at P2-M2, P2-M3, P2-M4

Change management:  Scope changes >THB 50,000 require Programme Director approval; >THB 200,000 require SC approval; change requests documented in src/gap05/change-log/

Termination for convenience:  30 days written notice; pro-rata payment for work completed

Intellectual property:  All AI models, training data derivatives, and integration code developed under contract are MONOLITH DAPH property; vendor retains pre-existing IP; joint IP to be agreed in Schedule C of contract

Data governance:  All DAPH client design data processed by AI engine governed by Data Processing Agreement (DPA); vendor must not use DAPH data for model training without explicit consent; data residency: Thailand or Singapore only

51.7  รายการตรวจสอบความพร้อมการจัดซื้อ Phase 2 (Procurement Readiness Checklist)

รายการตรวจสอบ P2-CHK-01 ถึง P2-CHK-08 ต้องได้รับการยืนยันจาก Programme Director และ Aria ก่อนออก RFP-GAP05-001 รายการทุกข้อต้องมีสถานะ COMPLETE ก่อนเริ่ม Phase B ของกระบวนการจัดซื้อ

• P2-CHK-01: SC-2032-XX mandate verified and countersigned by SC Chair + Programme Director

• P2-CHK-02: Phase 2 budget THB 1.5M for GAP-05 confirmed in Phase 2 allocation (S50.4)

• P2-CHK-03: AIE-001–005 technical specifications finalised and approved by Aria + Nova

• P2-CHK-04: RFP-GAP05-001 document reviewed by Core (governance) and Ledger (finance)

• P2-CHK-05: Evaluation panel constituted — Aria (chair), Nova, Signal, Core, Ledger — conflicts declared

• P2-CHK-06: Legal review of contract template and DPA complete (external legal counsel)

• P2-CHK-07: Vendor longlist ≥5 candidates identified and pre-qualified by Aria

• P2-CHK-08: UAT acceptance criteria for AIE-001–005 defined and approved by Aria + Programme Director

Readiness gate authority:  Phase 2 Programme Director co-sign with Aria before RFP issue

Target readiness date:  P2-M1 + 2 weeks (within 2 weeks of Phase 2 kickoff Q1 2033)

Non-compliance:  Any INCOMPLETE checklist item blocks RFP issue; escalation to SC Chair

Post-award checklist:  P2-CHK-09: Vendor onboarding complete (access credentials, environments); P2-CHK-10: Development environment AIE-001–005 scaffolding verified by Signal; P2-CHK-11: KPI monitoring dashboard active (Nova); P2-CHK-12: DPA countersigned and filed (Core)